Directions from Seniors   2013-2017 implementation Plan (Working Document )

Key

CDO-S, Community Development Officer – Seniors

CDO-I, Community Development Officer – Inclusion

NDO, Neighbourhood Development Officer

ND, Neighbourhood Development

SUP, Strategic Urban Planning

MCS, Manager Cultural Services

CEO, Community Engagement Office r

MVRC, Melville Volunteer Resource Centre

CDC- ND, Community Development Coordinator Neighbourhood Support

Report on Actions

| Action | Service Area Responsible | Contact Officer |  | Timeframe |  | Related Documents | Measurable Targets | Achievements |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Strategy 1: To create opportunities for vulnerable seniors through engagement and social participation |  |  |  |  |  |  |  |  |
| To provide opportunities that enhances social participation for seniors including isolated seniors, those from a culturally and linguistically diverse background, those with varying abilities and older men. | Neighbourhood Development | - CDO-S |  | Commencing 2014/15 Ongoing | Stakeholder Management Relationship Framework Community Engagement Guidelines Cultural Vitality Plan |  | - Community Wellbeing Survey Results - Over 80 people attending Seniors Forums |  |
| To promote a diverse range of intergenerational and inclusive activities within the City of Melville | Neighbourhood Development Cultural Services Leisure Services | -CDO-S -MSC |  | 2014-2015 | Stakeholder Management Relationship Framework Community Engagement Guidelines Cultural Vitality Plan Health and Wellbeing Plan |  | - An intergenerational event to be held within the CoM. |  |
| To provide a variety of opportunities for seniors to engage in decision making | Neighbourhood Development | -CDO-S -CEO |  | Commencing 2014/15 Ongoing | Health & Wellbeing Plan Stakeholder Management Relationship Framework Community Engagement Guidelines |  | - Hold a workshop for community feedback - MSC stories |  |
| CDO – S to do presentations at relevant community groups to advertise and promote ways of engagement and community participation | Neighbourhood Development | -CDO-S |  | 2013/14 Ongoing | Community Plan Stakeholder Management Relationship Framework Community Engagement Guidelines Neighbourhood Plans |  | -6 presentations per year to community groups -Seniors are satisfied with events, results collected through surveys |  |
| Support and Promote Community groups within the CoM | Neighbourhood Development | - CDO-S |  | Ongoing | Neighbourhood Plans Cultural Vitality Plan |  | - Visit 6 community groups per year and do presentations around City of Melville Services |  |
| Work Closely with the Melville Volunteer Resource Team to promote opportunities for seniors to volunteer | Neighbourhood Development | - CDO-S -MVRC |  | Ongoing |  |  | - An increase of senior volunteers. Measure through MVRC |  |
| Continue to liaise within the Senior Citizens centres to promote activities and usage as well as attract new members | Neighbourhood Development | -CDO-S -NDO’s and |  | Ongoing |  |  | -A higher usage of the Citizens centres |  |
| Form a partnership with Bicton Men’s shed to target more vulnerable and isolated men |  | - CDO-S |  |  |  |  | - A higher number of men attend the men’s shed |  |
| Strategy 2: To support people living independently in their own home for as long as possible |  |  |  |  |  |  |  |  |
| To support seniors by referring to and advocating for existing programs that enable and teach new skills on house and garden maintenance, for example garden share programs | Neighbourhood Development | - CDO-S | Ongoing |  |  |  | - Feedback through surveys |  |
| To support service providers to introduce new and additional services within Melville through advocacy promotion and support funding applications | Neighbourhood Development | - CDO-S -CDC-NS | Ongoing |  |  |  | -A higher number of grants applied for and approved for senior community groups |  |
| To review the access to the Seniors Assistance Fund it ensure it considers the growing ageing population | Neighbourhood Development | CDO- S CDC- East | 2014-2015 |  |  |  | -All CoM senior residents have equal access to the SAF, promote through events, website |  |
| To ensure issues of design for accessibility, access to transport and home modification options for new and renovated building developments within the City is considered. | Planning | -SUP | 2013-2017 |  |  |  |  |  |
| To continue the MASN meetings for not for profit organisations within the CoM. | Neighbourhood Development | -CDO- S | Ongoing |  |  |  | -Support local organisations in delivering senior services for the City -25-35 people present at each MASN meeting |  |
| To support not for profit organisations with promotions of their new programs etc. | Neighbourhood Development | - CDO- S | Ongoing |  |  |  | Large email mail outs through database Promotion through the CoM website |  |
| To look at garden share and water wise programs and assistance for residents within the CoM | Neighbourhood Development | - CDO- S | 2014-2015 |  |  |  | -A greater knowledge base of garden share and water wise project |  |
| To work together with Medicare Local to identify where the gaps are | Neighbourhood Development | - CDO- S -Health and Wellbeing Coordinator | 2014-2015 |  |  |  |  |  |
| Strategy 3: To ensure our seniors are well informed |  |  |  |  |  |  |  |  |
| To ensure information is accessible, updated and distributed in various formats and locations | Neighbourhood Development Marketing and Media | - CDO- S |  | Ongoing |  |  |  |  |
| To continue sharing and delivering information to different organisations and seniors service providers | Neighbourhood Development | -Marketing Officer |  | Ongoing |  |  | - Between 30-35 people to attend MASN meetings |  |
| To develop different strategies to engage with seniors from culturally and linguistically diverse backgrounds | Neighbourhood Development | -CDO- S - NDO’s |  | Ongoing |  |  | - hold a workshop with CALD senior residents to find out preferred methods of engagements |  |
| To provide relevant information at all major senior events | Neighbourhood Development | -All ND staff |  | Ongoing |  |  | - information provided at both large and small events |  |
| To extend partnerships with senior peak body agencies for cross promotions | Neighbourhood Development | - CDO- S |  | Ongoing |  |  | - develop and form 2 strong partnerships per year |  |
| To make sure that website content is reviewed on a 3 monthly basis | Neighbourhood Development | - CDO- S |  | Ongoing |  |  | - Information on the website is always current and in date |  |
| To work with the Inclusion officer to ensure that material for seniors is accessible | Neighbourhood Development | - CDO- S |  | Ongoing |  |  | -information is available in various formats as requested -Promotion of national relay service to community groups |  |
| Hold the Healthy Lifestyle Expo for over 55’s with the CoC and CoF | Neighbourhood Development | - CDO- S |  | 2014 2015 |  |  | - 600-700 seniors to attend |  |
| Ensure that the Wiki is up to date with current information for Customer Service | Neighbourhood Development | - CDO- S |  | Ongoing |  |  | - All seniors events and information are on the WIKI (customer service noticeboard) |  |
| Strategy 4: For seniors to access appropriate and affordable housing options including adequate aged care facilities without leaving the City of Melville |  |  |  |  |  |  |  |  |
| To promote accessibility and connections to community services in order to influence the independence and quality of life of older people | Neighbourhood Development | - CDO-I |  | Ongoing |  |  | - more seniors remain in the CoM |  |
| To advocate with relevant agencies for an increase in High Care Facilities to keep pace with population increases | Neighbourhood Development Planning | - CDO- S -SUP |  | 2014-16 |  |  | - Work together with State government to look at housing options for seniors |  |
| To ensure the Town Planning Scheme includes aged care accommodation developments | Planning | - Strategic Urban Planning |  | 2013-15 |  |  | - Aged care accommodation are included in the |  |
| To ensure issues of design for accessibility, access to transport and home modification options for new and renovated building developments within the City are considered | Neighbourhood Development Planning | - CDO- S -SUP |  | 2014-15 |  |  | -Age friendly checklist distributed and available to residents |  |
| To ensure that the CoM is informed and up to date with Department of Health and Ageing policies and procedures for High and low care facilities | Neighbourhood Development | - CDO- S |  | Ongoing |  |  | -CoM outcomes are more in line with the Dept of Ageing policies |  |
| To work closely with other local governments to collaborate and share ideas around housing options | Neighbourhood Development | - CDO- S |  | 2014-15 |  |  | - The ability to feedback different options around seniors housing to planning |  |
| Run a seniors forum around housing and housing options within the CoM. | Neighbourhood Development Planning | - CDO- S - SUP |  | 2014-15 |  |  | - high number of attendance at the forum |  |
| Keep seniors informed with changes and progress on developments for high density housing within the CoM in line with the Local Planning Strategy | Neighbourhood Development Planning | - CDO- S -SUP |  | Ongoing |  |  | - have an annual forum around Seniors Housing at Local planning strategy. |  |
| Strategy 5: To advocate for continual improvements in accessible transport and pedestrian access |  |  |  |  |  |  |  |  |
| To promote the City’s Footpath Upgrade Program to our seniors | Neighbourhood Development Tech Services | - CDO- S |  | 2013-2014 |  | Corporate Plan People Places and Participation | -Less complaints about footpaths |  |
| To advocate seniors concerns regarding bus routes, shelters and services to the Department of Transport | Neighbourhood Development Travel Smart | -CDO- S -CDO-I -Travel smart |  | 2013-2016 |  |  | - More accessible transport options for seniors |  |
| To Promote community transport options and concessions within the City of Melville | Neighbourhood Development Travel Smart | -CDO- S - Travel smart |  | 2013-014 |  |  | - more people use public transport |  |
| To Collaborate with agencies and other local governments to improve footpaths, pedestrian crossings and parking accessibility | Neighbourhood Development Travel Smart | -CDO- S -CDO-I -Travel smart |  | 2013-14 |  |  | -Quarterly meeting with other Local governments – seniors officers |  |
| Work closely with the CDO-I to see if there are accessibilty issues that we could address together | Neighbourhood Development | -CDO- S -CDO-I |  | 2014-2016 |  |  |  |  |
| Look at the outcomes from the community bus review | Neighbourhood Development | -CDC- East - CDO-S |  | 2013-14 |  |  | -Increase use of bus through community groups |  |
| Provide education around alternative transport and transport routes | Travel Smart | -Travel smart |  | 2014-15 |  |  | -More seniors using public transport |  |
| Improve seating on identified pedestrian walkways | Tech Services | -Manager Tech services |  | 2014-15 |  |  | - 10% More seating available |  |
| Other Actions |  |  |  |  |  |  |  |  |
| Continue with WHO membership criteria |  | - CDO-S |  |  |  |  |  |  |