| ACTION | Responsible | Plan | Proposed Timeframe | Review Mechanism | Resources |
| --- | --- | --- | --- | --- | --- |
| 1. | Implement & monitor recommendations of the City of Unley Ageing Strategy The following actions related to SAAFEC in particular: Tab on website re ageing community profile for internal and external use Investigate methods of meeting increased demand for HACC services Develop Age-Friendly Communications Strategy Council involvement in support services for residents of aged care facilities Investigate possible strategies for increasing transport to social activities Install hearing loops in all Community Centres Review Community Grants Program Provide information on Council website in other languages Workshop with community centres & libraries to develop programs & events that encourage cross-generational and multicultural interaction | Manager Community Projects (projects contained within the Strategy will be allocated to responsible officers) | City of Unley Ageing Strategy 2012-2014 | 2012-2014 | The Unley Ageing Strategy will be used to inform Annual Business Plans across the organisation. The Strategy will be reviewed and updated in 2014. | Projects will be referred to Council for funding each year. |
| ACTION | Responsible | Plan | Proposed Timeframe | Review Mechanism | Resources |
| 2. | Implement and monitor recommendations of DDA (Disability Discrimination Act) Plan The following action related to SAAFEC in particular: Improve signage throughout council area | Manager Community Projects (projects contained within the Plan will be allocated to responsible officers) | City of Unley DDA Plan – Access For All 2012-2016 | 2012-2016 | Every three months, Managers and Team Leaders will report on the outcomes of actions against the Plan’s performance indicators to the Aged and Disability Advisory Group. The overall “Access for All” Plan will be reviewed after three years. | Projects contained within the Plan will be allocated to responsible officers via the Annual Business Plans of each Council department. |
| 3. | Implement and monitor recommendations of ERA (Eastern Region Alliance) Ageing Strategy The following actions related to SAAFEC in particular: Explore implementation of regional Passenger Network Provide regional volunteering opportunities to Baby Boomers | Manager Community Projects ERA Ageing Workgroup (projects contained within the Plan will be allocated to responsible officers) | ERA Ageing Strategy 2012-2014 | 2012-2014 | The Eastern Region Alliance Ageing Group will be responsible for monitoring the progress of the ERA Ageing Strategy. An annual Information Report to the ERA Executive with copies of the Information Report to the Elected Members at each Council. | Resource contributions by partner Councils are fair and equitable and based upon population size and capacity to contribute (ERA). |
| ACTION | Responsible | Plan | Proposed Timeframe | Review Mechanism | Resources |
| 4. | Develop an age-friendly communication strategy | Manager Governance and Strategic Projects Manager Community Projects Manager Community Services | City of Unley Engagement Toolkit City of Unley Ageing Strategy | June 2013 | The City of Unley Ageing & Disability Strategy Review Team | Staff time Consultation costs External consultant |
| 5. | Undertake public seating audit | Manager Assets & Sustainable Landscapes Asset Officer | Open Space Asset Management Plan 2012-2016 | This four year plan is currently in consultation phase, set to be finalised in 2012 | This action has been identified as an improvement initiative and will be in the action plan. | Staff to undertake audit. |

| ACTION | Responsible | Plan | Proposed Timeframe | Review Mechanism | Resources |
| --- | --- | --- | --- | --- | --- |
| 6. | Implement and monitor actions of the Community Services Action Plan 2012 The following actions related to SAAFEC in particular: Provide regional volunteering opportunities to Baby Boomers Disseminate information on available community services to Community Centres Increase interaction between customer service and community services departments Increased acknowledgement of volunteers by senior management | Manager Community Services | Community Services Action Plan 2012 | 2012 | These actions will be reviewed as part of the monitoring and review of the Community Services Action Plan 2012. The Action Plan is reviewed quarterly. | Staff time |
| 7. | Review and development of new Open Space & Recreation Strategy | Manager Community Development Recreation & Open Space Coordinator | Open Space & Recreation Strategy | 2014 |  | Staff time Consultation costs External consultant. |

| Actions to be considered in future planning: |
| --- |
| ACTION | RESPONSIBLE |
| 1. | Develop new Events Program | Manager Community Development, Manager Community Projects |
| 2. | Provide training in mental health, dementia, etc. for Environmental Health staff | Manager of Environmental Health Team |
| 3. | Increase public computer & internet access in Community Centres | Manager Community Development, Community Centres Team Leader |
| 4. | Develop an adult learning strategy for Community Centres | Manager Community Development, Community Centres Team Leader |
| 5. | Develop customer service procedures for Community Centres | Manager Community Development, Community Centres Team Leader |
| 6. | Regular training updates in customer service for Community Centres staff | Manager Community Development, Community Centres Team Leader |
| 7. | Consultation with Retirement Village residents re possible future development of master-plan for Ridge Park | Manager Community Development, Recreation and Open Space Coordinator |