OCM20090910-AGENDA ITEM 17.2

City of Cockburn

Age- Friendly Strategic Plan

#### (Based on World Health Organisation Global Age-Friendly Cities Guide)

March 2008

Updated June 2009

Contents

EXECUTIVE SUMMARY	5

Identified Needs	5

Accommodation Needs	6

Table 10.0 Identified Shortfall in Supported Accommodation Need	6

Accommodation Strategies	6

Vision for an Age-Friendly City	7

Outcomes	8

Outdoor Spaces and Buildings	8

Transportation	8

Housing	8

Social Participation	8

Respect and Social Inclusion	8

Civic Participation and Employment	8

Communication and Information	9

Community and Health Services	9

1.	CITY OF COCKBURN AGE- FRIENDLY STRATEGIC PLAN	9

2.	GLOBAL AGEING TREND	9

2.1.	Initiatives Supporting an Ageing Population in Australia	10

3.	DEMOGRAPHIC INFORMATION	11

3.1.	Local Perspective Today	11

Table 1.0 Total number of people within the City of Cockburn for the relevant identified age groups in 2006.	11

3.2.	Population Projections	13

Australian	13

Western Australia	13

City of Cockburn	13

Table 2.0 Population projections for the City of Cockburn published by the Western Australian Planning Commission November 2005 in the Western Australia Tomorrow Population Projections for Local Government Areas 2004 to 2021.	13

4.	CURRENT SERVICES IN THE CITY OF COCKBURN	15

4.1.	Aged Care Accommodation	15

High Level Care	15

Low Level Care	15

4.2.	Current Aged Care Accommodation in the City of Cockburn	16

Table 3.0 Current Aged Care Accommodation facilities in the City of Cockburn	16

4.3.	Retirement Villages	17

4.4.	Retirement Villages in the City of Cockburn	17

Table 4.0 Retirement Villages in the City of Cockburn	17

4.5.	Respite	18

Table 5.0 Respite facilities in the City of Cockburn	18

4.6.	Community Services	18

Community Aged Care Packages	18

Extended Aged Care at Home (EACH)	19

Home and Community Care Programs	19

4.7.	Community Services in the City of Cockburn	19

Table 6.0 Community Services for Seniors	20

4.8.	Social and Recreation Groups in the City of Cockburn	21

4.9.	Feedback Regarding Existing Services	22

5.	THE CHANGING NEEDS OF AUSTRALIA’S AGEING POPULATION	22

5.1.	Diversity	23

Table 7.0 Description of diversity of needs by Age sub groups	23

5.2.	Cultural Diversity	24

5.3.	Need for Core Activity Assistance	25

Table 8.0 Need for Core Activity Assistance in 2006 in Cockburn District	25

5.4.	Identified Needs for Cockburn Seniors	26

6.	IDENTIFIED ACCOMMODATION NEEDS FOR COCKBURN SENIORS	27

6.1.	Supported Accommodation Need for City of Cockburn 2006-2021	27

Table 9.0 Supported Accommodation Need for City of Cockburn 2006-2021	27

6.2.	Identified Shortfall in Supported Accommodation Need 2006-2021	28

Table 10.0 Identified Shortfall in Supported Accommodation Need 2006-2021	28

6.3.	Independent Retirement Accommodation Need	28

6.4.	Respite Accommodation Need	28

6.5.	Home Based Accommodation Need	29

6.6.	Accommodation Strategies	29

7.	VISION FOR AN AGE-FRIENDLY CITY	30

8.	STRATEGIES TO DEVELOP AN AGE- FRIENDLY CITY	31

8.1.	Outdoor Spaces and Buildings	31

8.2.	Transportation	31

8.3.	Housing	32

8.4.	Social Participation	32

8.5.	Respect and Social Inclusion	33

8.6.	Civic Participation and Employment	34

8.7.	Communication and Information	34

8.8.	Community and Health Services	34

9.	REFERENCES	36

10.	APPENDIX	37

Appendix 1: Summary of Relevant Initiatives in Australia	37

The National Strategy for an Ageing Australia	37

Generations Together: Western Australia’s Active Ageing Strategy	37

The Active Ageing Benchmark Indicators	38

Transitions in Ageing	38

Local Government Trends	38

Ageing in Place	38

Appendix 2:  Aged Care Facilities within a 15km radius of Cockburn Central	39

Appendix 3:  Aged Friendly Implementation Plan Updated June 2009	42

#### Janelle Munro

#### 4th Leg Consulting

# EXECUTIVE SUMMARY

In March 2004, Bertram Healthcare Consulting was contracted by the City of Cockburn to undertake a Strategic Plan for Seniors. The Strategic Plan outlined community services, senior citizen’s groups and accommodation facilities and identified current and future needs for senior’s living within the Cockburn District.

In October 2007 this plan was reviewed in line with the World Health Organisation (WHO) guidelines for Global Age- friendly Cities.

Population ageing and urbanization are the culmination of successful human development during last century and are two global trends that together comprise major forces shaping the 21st century. Average life expectancy at birth has increased by 20 years since 1950 to 66 years and is expected to extend a further 10 years by 2050.

The number of people aged 60 and over as a proportion of the global population will double from 11% in 2006 to 22% by 2050. By then, there will be more older people than children (aged 0–14 years) in the population for the first time in human history.

Federal, State and Local Governments have launched various initiatives to support the principles of active ageing and to promote an age friendly environment. Older people in particular require supportive and enabling living environments to compensate for physical and social changes associated with ageing. This calls for changes in attitudes, policies and practices across all levels of government.

# Identified Needs

During the consultation undertaken at the time of the original 2004 report the following issues were consistently highlighted in the think tank, surveys and focus groups:

- Insufficient affordable housing options and respite services

- Insufficient  home help services

- Access and funding issues related to current services

- Social isolation

- Lack of affordable and culturally appropriate social and recreational services

- Lack of coordination of information and services supporting ‘healthy ageing’

- Lack of promotion of services that council provide

- Inadequate safety and security for some seniors both in home and the community

- Inadequate affordable access to public spaces, services and events

These needs have been developed into a comprehensive strategic plan for the City of Cockburn that reflects the principles and best practice outlined in the Global Age Friendly Cities: A Guide developed by the World Health Organisation.

# Accommodation Needs

The need for the ageing population in the City of Cockburn to have access to affordable suitable housing options that allow them to age comfortably and safely within the community to which they belong was targeted as an outcome during the development of the Global Age-Friendly Strategic Plan and was investigated more comprehensively in the Age Friendly Accommodation Report.

## Table 10.0 Identified Shortfall in Supported Accommodation Need

|  | 2006 | Projected need 2011 | Projected need 2016 | Projected need 2021 |
| --- | --- | --- | --- | --- |
| Targeted Beds for Supported Accommodation | 449 | 563 | 722 | 950 |
| Identified beds(includes current plus new developments) | 365 | 515 | 515 | 515 |
| Shortfall | 84 | 48 | 207 | 435 |

# Accommodation Strategies

The following are incorporated in the Housing Outcome area and Community and Health services outcome area of this Age Friendly Strategic Plan:

Strategy 1:  That the City of Cockburn continues to expand the range of community services available to support people to remain in their current accommodation as long as possible.

This includes:

- increasing the community care packages currently available

- applying for Extended Aged Care at Home (EACH)

- continuing the current range of services

- explore feasibility of a range of emergency and ongoing respite services

Strategy 2: That the City of Cockburn explores further the feasibility of a joint venture for the vertical development on the Phoenix Central site in relation to both supported accommodation and self funded retirement accommodation.

The current Phoenix Central redevelopment was looked at as a possible suitable environment for future accommodation development. The site may be able to sustain some vertical development that could provide a range of accommodation options in keeping with ageing in place. There are some drawbacks to vertical development including the cost for the developer, the size of the project required to make it financially viable for them and the suitability of access for use by an ageing population. There is also the consideration for council that there will be a cost if a joint venture with a not for profit organization is progressed as they are exempt from paying rates.

There is scope to include a development for independent funded retirement accommodation on the current Phoenix Central site. This would be in keeping with the growing trend for the ageing population to down size into affordable housing that is neither isolated nor age specific. Future development of the site along Spearwood Avenue may be able to include a supported accommodation facility to compliment retirement accommodation.

Strategy 3: That the City of Cockburn identifies suitable opportunities to develop supported accommodation as an integral component of all future redevelopments.

It will be crucial that the City of Cockburn actively target supported accommodation development in any future redevelopment in order to meet the identified accommodation needs.

# Vision for an Age-Friendly City

The City of Cockburn is committed to ensuring that the community is an accessible and inclusive community in which all council functions, facilities and services (both in-house and contracted) are open, available and accessible for all people, providing the ageing population with the same opportunities, rights and responsibilities enjoyed by all other people in the community.

The City of Cockburn supports the development of an age-friendly city that adapts its structures and services to be accessible to and inclusive of older people with varying needs and capacities. It strives to develop policies, services, settings and structures that support and enable people to age actively by:

- recognizing the wide range of capacities and resources among older people;

- anticipating and responding flexibly to ageing-related needs and preferences;

- respecting their decisions and lifestyle choices;

- protecting those who are most vulnerable; and

- promoting their inclusion in and contribution to all areas of community life.

Eight outcomes have been considered in developing the Age friendly City Strategic plan.

These outcome areas provide a framework for translating the principles of the World Health Organisation global age-friendly cities into tangible and achievable results.

## Outcomes

### Outdoor Spaces and Buildings

Outcome:  That the ageing population in the City of Cockburn has access to age friendly built environments that support independence, quality of life and safety for older people and positively affect their ability to “age in place”.

### Transportation

Outcome:  That the ageing population in the City of Cockburn has access to affordable and equitable transport to support social and civic participation and access to community and health services.

### Housing

Outcome: That the ageing population in the City of Cockburn has access to affordable suitable housing options that allow them to age safely and be socially supported within the community to which they belong.

### Social Participation

Outcome:  That the ageing population in the City of Cockburn has affordable and equitable access to activities and events that support social participation and fosters well being and social integration.

### Respect and Social Inclusion

Outcome: That the ageing population in the City of Cockburn are recognized and included as valuable members in the social, civic and economic life of the city.

### Civic Participation and Employment

Outcome: That the ageing population in the City of Cockburn has access to opportunities to continue to contribute to their communities, through paid employment or voluntary work if they so choose, and to be engaged in the political process.

### Communication and Information

Outcome: That relevant information is readily accessible to older people with varying capacities and resources.

### Community and Health Services

Outcome: That the ageing population in the City of Cockburn has access to affordable quality community support services and health care.

# CITY OF COCKBURN AGE- FRIENDLY STRATEGIC PLAN

In March 2004, Bertram Healthcare Consulting was contracted by the City of Cockburn to undertake a Strategic Plan for Seniors. The Strategic Plan outlined community services, senior citizen’s groups and accommodation facilities and identified current and future needs for senior’s living within the Cockburn District.

In October 2007 this plan was reviewed in line with the World Health Organisation (WHO) guidelines for Global Age- Friendly Cities.

The City of Cockburn supports the development of an age-friendly city that adapts its structures and services to be accessible to and inclusive of older people with varying needs and capacities. It strives to develop policies, services, settings and structures that support and enable people to age actively by:

- recognizing the wide range of capacities and resources among older people;

- anticipating and responding flexibly to ageing-related needs and preferences;

- respecting their decisions and lifestyle choices;

- protecting those who are most vulnerable; and

- promoting their inclusion in and contribution to all areas of community life.

# GLOBAL AGEING TREND

The World Health Organisation (WHO) Brasilia Declaration on Ageing in 1996 stated “healthy older people are a resource for their families, their communities and the economy”.

Making cities more age-friendly promotes the wellbeing and contributions of older urban residents and keeps cities thriving. An age-friendly city optimizes opportunities for health, participation and security in order to enhance quality of life as people age.

An age-friendly city does not only meet the needs of the ageing population but supports the entire community by:

- Providing buildings and streets that enhance mobility and independence of people with disabilities, families and ageing population.

- Supporting secure neighbor hoods that allow children, younger women and older people to venture outside in confidence to participate in physically active leisure and in social activities.

- Assisting with community support and health services for older members to alleviate stress for families.

- Encouraging and supporting the participation of older people in volunteer or paid work.

- Extending the ability of older people to contribute to the local economy.

Older people in particular require supportive and enabling living environments to compensate for physical and social changes associated with ageing. This necessity was recognized as one of the three priority directions of the Madrid International Plan of Action on Ageing endorsed by the United Nations in 2002.

## Initiatives Supporting an Ageing Population in Australia

Global ageing calls  for changes in attitudes, policies and practices at all levels in all sectors so that the enormous potential of ageing in the twenty-first century may be fulfilled.

The following initiatives have been introduced at various levels of government to support the principles of an age- friendly environment:

- Aged Care Act 1997 and the Aged Care Principles.

- National Strategy for an Ageing Australia released in December 1997 by the Australian Government.

- Generations Together A Guide to the Western Australian Active Ageing Strategy was launched in March 2004.

- The Active Ageing Benchmark Indicators released in March 2006 by The Department of Community Development (Office for Seniors Interest and Volunteering).

- Transitions in Ageing released in 2005 by the Office of Seniors Interests and Volunteering.

- Planning for an Ageing Community is a dedicated website developed by The Australian Local Government Association (ALGA) and the Department of Health and Ageing.

- Ageing Toolbox was developed by ALGA to assist local government in planning for an ageing community.

Summaries of these initiatives can be found in Appendix 1 with relevant links to the full reports.

# DEMOGRAPHIC INFORMATION

Australia’s population is ageing and the evidence for this demographic change is undeniable. Falls in fertility, increasing life expectancy and the effect of the ‘baby boomer’ generation moving through older age groups, has contributed to an increase in the number and proportion of people aged over 65 years. The change in demographics will require a proactive and innovative approach to population ageing that is responsive to the needs and aspirations of all Australians.

## Local Perspective Today

The City of Cockburn has been experiencing strong population growth across all age groups, with the population growth for over 65 year olds increasing at approximately the same rate as the rest of the Cockburn population.

## Table 1.0 Total number of people within the City of Cockburn for the relevant identified age groups in 2006.

| Population for City of Cockburn 2006 Census | Male | Female | Total |
| --- | --- | --- | --- |
| Middle Age group 45 to 64 | 8576 | 8763 | 17339 |
| Younger old age group 65 to 74 | 2175 | 2182 | 4357 |
| Older old age group 75 plus | 1,280 | 1,864 | 3,144 |
| Total Senior population over 45 | 12031 | 12809 | 24840 |
| Total of all population | 37,053 | 37,420 | 74,473 |
| Percentage of population Aged Over 45 |  |  | 33% |

Australian Bureau of Statistics 2006 Census of Population and Housing Cockburn (C)

The majority of seniors aged between 50 and 65 years old, currently live in Hamilton Hill and older suburbs such as Spearwood, Coolbellup, Bibra Lake, Munster and Jandakot although a significant number reside in newer suburbs such as Banjup.

The following diagrams outline the percentage distribution by age and the overall current population figures by age and sex for the City of Cockburn and allow for a comparison of the proportions of the ageing population across the various suburbs.

Key for following tables as a

Percentage of the total population

Across the City of Cockburn

Diagram 1.0 Percentage aged 55-64 years in 2006 in Cockburn District

| Actual Population | Male | Female | Total |
| --- | --- | --- | --- |
| 55-59 years | 2,048 | 2,044 | 4,092 |
| 60-64 years | 1,531 | 1,493 | 3,024 |

Diagram 2.0 Percentage aged 65-74 years in 2006 in Cockburn District

| Actual Population | Male | Female | Total |
| --- | --- | --- | --- |
| 65-69 years | 1,209 | 1,184 | 2,393 |
| 70-74 years | 970 | 994 | 1,964 |

Diagram 3.0 Percentage aged 75 years and over in 2006 in Cockburn District

| Actual Population | Male | Female | Total |
| --- | --- | --- | --- |
| 75-79 years | 672 | 802 | 1,474 |
| 80-84 years | 370 | 553 | 923 |
| 85-89 years | 172 | 330 | 502 |
| 90-94 years | 52 | 140 | 192 |
| 95-99 years | 8 | 31 | 39 |
| 100 years and over | 0 | 6 | 6 |

Based on Place of Usual Residence, 2006Cockburn (C) (Local Government Area) by Census Collection District and population figures

## Population Projections

### Australian

The latest population projections released by the Australian Bureau of Statistics (ABS).indicate that by 2051 Australia's population is expected to increase to between 25 and 33 million people, with around 44% to 48% being older than 50 years.

- 2051 slightly more than one in four Australians will be aged 65 years and over

- 2051 people aged 85 years and over will make up 6% to 8% of Australia's population

### Western Australia

- 2006 	Number of seniors	340,531	Percentage of population	17%

- 2011	Number of seniors	424,369	Percentage of population	19%

- 2021	Number of seniors	602,680	Percentage of population	24%

Sources (electronic data) Australian Bureau of Statistics - Projections WA Series B 2004-2051 MFP all ages.xls

### City of Cockburn

## Table 2.0 Population projections for the City of Cockburn published by the Western Australian Planning Commission November 2005 in the Western Australia Tomorrow Population Projections for Local Government Areas 2004 to 2021.

|  | 2004 | 2006 | 2011 | 2016 | 2021 |
| --- | --- | --- | --- | --- | --- |
| 45-49 | 5400 | 5700 | 6700 | 7500 | 7900 |
| 50-54 | 4800 | 5100 | 6100 | 7000 | 7700 |
| 55-59 | 4000 | 4400 | 5200 | 6100 | 6900 |
| 60-64 | 2900 | 3200 | 4400 | 5100 | 6000 |
| 65-69 | 2400 | 2600 | 3200 | 4400 | 5100 |
| 70-74 | 1800 | 2000 | 2500 | 3100 | 4300 |
| 75-79 | 1300 | 1400 | 1800 | 2400 | 2900 |
| 80-84 | 820 | 910 | 1200 | 1500 | 2000 |
| 85 plus | 550 | 640 | 900 | 1200 | 1600 |
| Total Aged Over 45 | 26370 | 24150 | 32000 | 38300 | 44400 |
| Total Population in Cockburn | 73900 | 77900 | 90700 | 102600 | 113900 |
| Percentage Aged of 45 | 36% | 31% | 35% | 37% | 39% |

Australian Bureau of Statistics 2006 Census of Population and Housing Cockburn (C) report states the actual percentage of people aged over 45 in Cockburn in 2006 was greater than projected at 33% of the total population instead of 31%.

Population projections show that older populations will continue to be concentrated in local government areas along the Australian coastline. Generally, when seniors move, it is usually only within the immediate local area to be closer to family for increasing support needs or into more appropriate living arrangements.

As the proportion of older people increases over the coming decades the needs of the population will change. Utilisation patterns and preferences will evolve and there will be increased expectation that local government will accommodate those changing needs. Already, there are a number of emerging service areas, including health and wellbeing programs, continuing education and housing.

# CURRENT SERVICES IN THE CITY OF COCKBURN

It is important for local councils to understand the needs of seniors now and into the future. A common starting point is to compile a register of local council services and programs (also incorporating non-council provided services) and identify gaps and relevance to the next generation of seniors.

Today, councils undertake a broad range of services to meet the needs of their seniors’ population. Key service initiatives include library services, home and community care, volunteering services, community grants, recreation and leisure services, carers support and seniors’ centres.

An update of the audit from the original report in 2004 was completed including facilities, services and activities provided by the City of Cockburn, Government, Non Government Organisations and Private Business.

## Aged Care Accommodation

Government-funded aged care homes are approved by the Australian Government to care for people. The introduction of Accreditation Standards for all Aged Care providers commenced in 1999 and requires all providers to demonstrate their ability to meet 44 standards within the accreditation framework. The principles of accreditation are built on a model of continuous quality improvement, systems and processes. The Aged Care Standards and Accreditation Agency Ltd assesses homes and monitors them to make sure they comply with the standards.

All aged care homes must provide a specified range of care and services at no additional cost to residents. These requirements vary according to whether the resident has ‘low-care’ or ‘high-care’ needs. There are some specified levels of care and services that all residents receive and additional ones that are provided for high-level care residents.

### High Level Care

This is for people who need almost complete assistance with most daily living activities. It includes accommodation services such as meals, laundry and room cleaning as well as personal care. Medical needs are managed by nursing staff. High level care was previously known as Nursing home care.

### Low Level Care

This is for people who need some help, but do not have very complex ongoing care need. It includes accommodation-related services (furnishings, bedding, general laundry, some toiletries, cleaning services, all meals, maintenance of buildings and grounds, and the provision of staff on call to provide emergency assistance) and personal care services ( assistance with the activities of daily living, such as bathing, going to the toilet, eating, dressing, moving around, maintaining continence or managing incontinence, rehabilitation support, and assistance in obtaining health and therapy services.)

## Current Aged Care Accommodation in the City of Cockburn

The following facilities are located within the Cockburn area and provide a mix of accommodation services for the population. Sourced from www.agedcareaustralia.gov.au

## Table 3.0 Current Aged Care Accommodation facilities in the City of Cockburn

| DETAILS | HIGH CARE | LOW CARE | RESPITE | Ageing in place |
| --- | --- | --- | --- | --- |
| Villa Dalmacia Aged Care Facility (Villa Dalmacia Association) 27 Gorham Way SPEARWOOD, WA 6163 Phone: 08 9418 5222 Fax: 08 9434 1755 | 50 | 20 | yes | yes |
| Illawong Village Hostel (Bethanie Care) 1 Rodd Place HAMILTON HILL, WA Phone: 08 9418 6955 Fax: 08 9418 5303 |  | 39 | yes | no |
| Carrington Aged Care Facility (Aegis Group) 27 Ivermey Road HAMILTON HILL, WA 6163 Phone: 08 9337 2238 Fax: 08 9314 2648 | 60 | 43 | Yes | yes |
| Hale Hostel (Amana) (Locally known as Amana Living - Hale Hostel) 31 Waverley Road COOLBELLUP, WA 6163 Phone: 08 9424 6363 Fax: 08 9383 1251 |  | 40 | Yes | no |
| Brightwater - South Lakes Care Facility (Brightwater) 62 Bloodwood Circle SOUTH LAKE, WA 6164 Phone: 08 9417 6200 Fax: 08 9417 6299 |  | 30 | Yes | no |
| Frank Prendergast House (Southern Cross) 27 Pearson Drive SUCCESS, WA 6164 Phone: 08 94144600 Fax: 08 9414 6680 | 60 | 13 | No | yes |
| Total beds(approx only) | 180 | 185 |  |  |

## Retirement Villages

Independent Living Units or Retirement Villages are for people who need less care than that offered by aged care homes. These residential communities offer a range of services for independent older people, and are regulated by state and territory governments. The introduction and review of the Code of Practice for Retirement Villages has seen legislation applied to protect retirees entering into villages and affording a greater level of accountability and transparency by the owners and providers of village style accommodation. The legislation requires that village owners protect the retiree’s investment in the village and is accountable financially to a village committee.

## Retirement Villages in the City of Cockburn

Within the geographic boundaries of the City of Cockburn there are a number of retirement villages that offer a wide range of accommodation both in services and cost.

## Table 4.0 Retirement Villages in the City of Cockburn

| Amana Living (Hale House) | 9424 6384 | 37 Waverley Road Coolbellup | 49 units |
| --- | --- | --- | --- |
| Ellis Masonic Village | 94092322 | 12 Lavinia Crescent Coolbellup | 26 rental units |
| Illawong Village | 9418 6955 | 1 Rodd Place Hamilton Hill | 29 units |
| Lakeside Village | 9417 8526 | Lewington Gardens Bibra Lake | 288 Resident funded units |
| Success Village | 9414 3115 | 27 Pearson Drive Success | 137 Resident funded units |
| Total Available Units | 529 units |

Sourced from www.agedcareguide

There are limited low cost options available. Some villages provide opportunities for people to move into an associated supported aged care environment. Many of these units would have double occupancy but these figures were not available. It still remains much lower than the population projections would indicate.

## Respite

Not all of these services provide age specific services and respite remains a significant area of need throughout all of Western Australia.  Sourced from www.agedcareaustralia.gov.au

## Table 5.0 Respite facilities in the City of Cockburn

| Activ Foundation Inc. - Family Services | (08) 9387 0555 |
| --- | --- |
| Alzheimer's Australia WA | (08) 9388 2800 |
| Amana Living - Stay Home Program - HACC (previously Anglican Homes ) | (08) 9344 9200 |
| Brightwater - Balcatta - Community Respite House (Low Care) | 9344 8433 |
| Brightwater - Marangaroo Community Respite House (High Care) | 9247 9102 |
| Derbarl Yerrigan Health Service - HACC | (08) 9344 0444 |
| Mercy Aged Care - In Home Respite | (08) 9442 3498 |
| Multiple Sclerosis Respite Norbury House | (08) 9385 9574 |
| Neurocare | (08) 9346 7535 |
| Perth Home Care Services - Crisis Care Service | (08) 9204 7801 |
| Perth Home Care Services - HACC | (08) 9204 7800 |
| Perth Home Care Services - TOP (Time Off and Planning) | (08) 9204 7800 |
| Rockingham Respite Cottage | (08) 9528 2137 |
| Rocky Bay Inc | (08) 9383 5111 |
| TAPSS Community Care | (08) 9383 2663 |

## Community Services

It is important to remember that there is an increased trend in accommodation provision to support people within their current situation as long as possible through the provision of home based services

### Community Aged Care Packages

The Community Aged Care Packages are a Commonwealth Government funded scheme. These are planned and coordinated packages of care to assist people to remain living in their own home. The packages are specifically designed to cater to the individual and are flexible to meet varying needs including personal care, meal preparation, home help/cleaning, transport services .

### Extended Aged Care at Home (EACH)

This program provides an option for older people with high and complex care needs to be supported in their own homes. ACAT assessment is a prerequisite.

### Home and Community Care Programs

As with the Community Aged Care packages, the HACC program continues to expand and provide a range of service for all eligible people living within the community. The programs can enhance other areas of service provision in supporting individuals to remain at home for longer periods.

## Community Services in the City of Cockburn

Cockburn Community Care provides centre based day care services for the frail, aged and disabled at the Jean Willis Centre in Hamilton Hill. The Day Centre programmes provide a range of activities and outings, which are client focused to cater to the physical, social and emotional needs of all members. Lunch and refreshments are included in the day program. Transport is provided to and from the Centre in specially equipped vehicles, to allow easy access for people with physical disabilities.

Home Support Services assist people to remain living in their own home in the community. Assistance or support is provided with basic everyday tasks, such as Respite Care (for Carers of the Frail or Disabled person), domestic assistance and shopping assistance

Carer Support Service offers support and advocacy, information and assistance regarding respite options, fortnightly coffee morning, bi-monthly carer’s newsletter and carers Retreat.

Kwobarup Aboriginal Program is aimed specifically at our Aboriginal Community. The Kwobarup program offers a range of services to fail, aged and disabled Aboriginal people including Centre Based Respite, Home Help, Transport, cultural art program, activities and outings and information about other Aboriginal specific services provided in the community.

Community Aged Care Packages (CACP) 
These are planned and coordinated packages of care specifically designed to cater to the individual and are flexible to meet varying needs including personal care, meal preparation, home help/cleaning, transport services .

As the government direction in recent years has been to focus on supporting people to remain in their own homes there has been a marked increase in the availability of Community Aged Care Packages. This has also seen an increase in the number of providers becoming involved in the delivery of this type of service.  Some of the services listed below are not physically located in the City of Cockburn but provide a range of services to people within the City of Cockburn.

Safer City Service

Consultation findings from the 2004 report identified the need for the City to continue to support the City of Cockburn Safer Senior Service

Key activities that need to continue include:

- promoting the Safer Senior Subsidy Service

- educating and  informing seniors on safety & security risk minimisation including financial security;

(3) working in partnership with service agencies to prevent crime, fire and injury to seniors

Safety and security issues are generic issues impacting on the community across the nation and were repeatedly expressed by Cockburn seniors and service providers in the consultation strategy.  Seniors are a natural target for crime and according to consultation feedback some seniors are even frightened to answer the door or walk down the street or talk to anyone about financial advice in case they are ‘ripped off’.  Cockburn has some very good initiatives via the Safer Senior Service however anecdotal evident suggests that awareness of this service is not widespread.

Mobile Library Service

The City of Cockburn mobile library service for home bound residents was positively supported by the 2004 consultation findings. Community feed back identified the need for the City to continue to support this valuable community service.

Other services listed below are not necessarily located in the City of Cockburn but provide a range of Community services to people living within the City of Cockburn.

## Table 6.0 Community Services for Seniors

| Aged Care Services Australia | (08) 9329 1600 |
| --- | --- |
| Amana Living - Cities of Melville and Cockburn | (08) 9344 9200 |
| Baptist Care Home Care Services-South Metro | (08) 9528 5201 |
| Baptistcare | (08)94505744 |
| Baptistcare | (08) 9282 8600 |
| Brightwater At-Home Services - CACPs Western Suburbs | (08) 9489 5000 |
| Brightwater At Home Services South West | (08) 9593 9254 |
| Chung Wah Association - (Chinese ) | (08) 9328 3988 |
| Coolibah Aged Care Facility | (08) 9535 0304 |
| Derbarl Yerrigan Homecare Services - Community Aged Care Packages | (08) 9421 3888 |
| Dutch Aged Care WA Inc. - Community Aged Care Packages, The | (08) 9382 4186 |
| Italo-Australian Welfare & Cultural Centre Inc | (08) 9228-2220 |
| Mercy Aged Care - CACP | (08) 9419 7533 |
| Mercy Aged Care - Community Aged Care Packages | (08) 9442 3498 |
| Noel Bodycoat Care | (08) 92215344 |
| Pam Corker House | (08) 9733 1355 |
| Silver Chain Association-MSW HACC | 08 9242 0242 |
| Silver Chain Community Aged Care Packages | (08) 9242 0242 |
| Southern Cross Care | 9282 9966 |
| Southern Cross Community Care Services | (08) 9337 0150 |

Sourced from www.agedcareaustralia.gov.au

## Social and Recreation Groups in the City of Cockburn

There are a range of social and recreational options available for people in the area although the Seniors Community Action Group identified the need for a centrally located service that more fully met the needs of the current population.

Cockburn’s Regional Seniors Group

The Regional Seniors Group (RSG) was established in 2005 under the banner of the Cockburn Community Development Strategy. The Group consists of members representing the various Seniors Clubs within the Cockburn area. The RSG reports back bi-monthly to the Regional Community Development Group, the peak body of the Strategy.

The RSG defines a ‘Seniors Club’ as a group that:

- consists of community members over the age of 50

- promotes and supports the wellbeing of seniors by enhancing their lives

- encourages social inclusion amongst seniors through various annual events, workshops and activities

Seniors groups in the City of Cockburn include St Jerome’s Seniors, South Lake Seniors, Probus Club of Cockburn, Cockburn Prime Timers, Cockburn Senior Citizens, Coolbellup Leisure Club and Atwell Over 50’s. The City of Cockburn Seniors Centre Coordinator will provide administration support to the RSG and will work co-operatively with the RSG members and the Seniors Centre members in planning Active Ageing activities in the Interim Seniors Centre.

Happening Seniors Program 2006 - 2009

Happening Seniors is a program to encourage active ageing amongst the seniors of the City of Cockburn. There are four components to the Happening Seniors Program - Seniors Bulletin Board; Intergenerational Volunteering; Active Living Expo and the Living Strong Learning stream. A wide range of the Happening Seniors Active Ageing activities will operate from the City of Cockburn Interim Seniors Centre from August 2009.

## Feedback Regarding Existing Services

Feedback from the original report in 2004 from the focus groups and surveys revealed a number of service providers and seniors who were satisfied with current services and activities provided to seniors.  These positive responses on services and activities identified many opportunities for social and recreation groups for seniors, suitable recreational and physical courses, satisfaction with HACC service programs, safer city service and mobile library service provision, carer support through social mornings and carer support groups and ongoing learning opportunities for seniors.

It was also reported at the time that there were good networking and  relationships between service providers (HACC) and local GP’s and Medical Centres Aged Care Assessment Team (ACAT), continuity of service provision with agencies providing more than one service under the HACC program and a move towards personal centre care and comprehensive nursing assessment and care provision in the home. However current feedback has identified some difficulties in these areas.

# THE CHANGING NEEDS OF AUSTRALIA’S AGEING POPULATION

Contemporary services for seniors are designed for today’s older Australians and may not be appropriate or relevant for ageing “baby boomers”. Services in general are aimed at meeting physical needs after a problem develops, rather than preventing problems in the first place

Future seniors will seek access to activities and services that support their continued good health and independence. It is likely that demand for community-based, proactive, social based services and activities will intensify and that demand on local government to meet the health and community needs of older people will increase. Services aimed at older people will need to address physical, mental and social needs. The main demands are expected to be: health and aged care, home support services, subsidy of medical services, community transport and a range of cultural and recreation services.

The Productivity Commission, in its research study—Economic implications of an Ageing Australia, concluded that with the delivery of human services now representing 49% of total local government expenditure, local councils are more likely to face budgetary pressures from population ageing than from traditional activities such as road and infrastructure provision and maintenance.

## Diversity

An important dimension of the older population is the diversity of needs, interests and backgrounds. Older people are individuals and their experience of ageing will be influenced by a range of inter-related factors such as gender, lifestyle, location, socioeconomic circumstances, cultural backgrounds, education level and general health. The notion of productive, healthy life expectancy has different meanings for different groups. Much of the literature divides the larger group into three subgroups based on age and similar social circumstances.

## Table 7.0 Description of diversity of needs by Age sub groups

| Age group | Issues and Expectations |
| --- | --- |
| The ‘middle’ age group (now 45-64) were born between 1939 and 1958 Post war baby boomers, born in large numbers soon after the war Great social change in the 1960s and 1970s They will account for the large bulge in the population of ‘older old’ people (over 80 years) between 2026 and 2036. | Changes in transport and urban patterns, access to television and computers, together with increased working hours for many, have reduced physical activity in daily lives Health problems include overweight and obesity, mental disorders (including depression and anxiety), musculoskeletal problems and cardiovascular problems Increasing the number of years of healthy life should help to reduce health-related withdrawal from the workforce and increase workforce participation among mature age workers, which will benefit both the individual and the economy. |
| The ‘younger old’ age group (now aged 65-79 years) born in the period 1924-1938, during the economic restrictions of the Great Depression or Second World War Majority in this generation are living in their own homes, with low housing costs that have permitted a reasonable standard of living on the pension. Many of them provide care for their own parents, their spouse, a sick or disabled adult child, grandchildren, or combinations of these | Health problems include different forms of cancer, cardiovascular diseases, sensory disorders, musculoskeletal disorders and mental disorders. More than half over 70 years suffer from at least one chronic medical condition, one third require assistance with daily activities such as shopping, cooking and housework. Once ill, they need effective care including proper medication management, aids to maintain independence. The majority of this generation, however, still consider themselves to be in good health. Expectations and priorities are: staying in their own home as long as possible, staying mobile and independent, active participation in society high quality health care continued lifelong learning. Extra years of healthy life will allow ongoing participation in the paid workforce (for some) and in family and community life, increased independence, autonomy and mobility and decreased likelihood of admission to residential care |
| The ‘older old’ age group (over 80 years) This group represents the survivors of the generation born before 1923, who lived their formative teen and young adult years during the Depression and Second World War These numbers are expected to increase rapidly in the next 30 years. | Most people in this older old group suffer from multiple chronic diseases and have relatively high levels of disability. They have a steeply rising incidence of the brain disorders that become common only with advancing age (Alzheimer’s disease and other dementias; Parkinson’s disease and other gait disorders).A quarter of the men and one third of the women have two or more chronic health problems. Their needs include: support and aids to enhance their independence and mobility, support to stay in their own homes where possible access to high quality medical care Additional years of healthy life will mean increased independence, autonomy and mobility, with less likelihood of admission to residential care. |

## Cultural Diversity

A further influence on the profile of the ageing population is the significant cultural and linguistic background of the population. The Office for Seniors Interests and Volunteering undertook the Culturally and Linguistically Diverse Seniors: Community Participation Research Project to gather information from culturally and linguistically diverse (CALD) seniors about their involvement in the community and their perceived barriers to participating in community activities. The literature review found that the proportion of older Australians from culturally and linguistically diverse backgrounds is increasing at a faster rate than the increase in the number of older Australian born people.  The Australian Institute of Health and Welfare (2004) has projected that the number of older Australians from culturally and linguistically diverse backgrounds will increase by 66% over the fifteen years between 1996 and 2011.  The older Australian born population is expected to increase by only 23% in the same period.

By the year 2020, a substantial proportion of older people in Australia will have been born overseas in a non-English speaking country.  It is projected that the growth in this group will be dramatic (Hugo & Thomas, 2002).

The City of Cockburn has a substantial culturally diverse population and will need to take this into account when planning future services and supports.

## Need for Core Activity Assistance

The census figures for 2006 identified that 2,647 people in the City of Cockburn identified that they needed assistance as defined by the 'Core Activity Need for Assistance' variable.

This variable has been developed to measure the number of people with a profound or severe disability. People with a profound or severe disability are  defined as needing help or assistance in one or more of the three core activity areas of self-care, mobility and communication because of a disability, long term health condition lasting six months or more), or old age.

Some people did not record they needed assistance and it may be that the figures could be higher than the current identified need.

## Table 8.0 Need for Core Activity Assistance in 2006 in Cockburn District

|  | Need for assistance | Need for assistance not stated | No need for assistance | Total |
| --- | --- | --- | --- | --- |
| 45-54 years | 260 | 581 | 9,381 | 10,222 |
| 55-64 years | 323 | 379 | 6,417 | 7,119 |
| 65-74 years | 370 | 285 | 3,704 | 4,359 |
| 75-84 years | 560 | 193 | 1,640 | 2,393 |
| 85 years and over | 375 | 83 | 285 | 743 |
| Total | 2,647 | 4,742 | 67,084 | 74,473 |

Please note: Table 8.0 is Based on place of usual residence

## Identified Needs for Cockburn Seniors

Population ageing will impact on planning and service delivery, creating growing challenges for local government authorities.

During the consultation undertaken at the time of the original 2004 report the following issues were consistently highlighted in the think tank, surveys and focus groups:

- Insufficient affordable housing options and respite services

- Insufficient home help services

- Access and funding issues related to current services

- Social isolation

- Lack of affordable and culturally appropriate social and recreational services

- Lack of coordination of information and services supporting ‘healthy ageing’

- Lack of promotion of services that council provide

- Inadequate safety and security for some seniors both in home and the community

- Inadequate affordable access to public spaces, services and events

- Poor transport

The majority of seniors aged between 50 and 65 years old, currently live in Hamilton Hill and older suburbs such as Spearwood, Coolbellup, Bibra Lake, Munster and Jandakot although a significant number reside in newer suburbs such as Banjup.

Service mapping indicated that the majority of Seniors services are located in Spearwood and Hamilton Hill.  In the future there is a need to investigate whether additional satellite social and recreation facilities, and community health services should be provided in the vicinity of the significant number of seniors who live in Jandakot and Banjup.

# IDENTIFIED ACCOMMODATION NEEDS FOR COCKBURN SENIORS

The need for the ageing population in the City of Cockburn to have  access to affordable suitable housing options that  allow them to age comfortably and safely within the community to which they belong was targeted as an outcome during the development of the Global Age-Friendly Strategic Plan.  The extent of this need has been further investigated and included in summary form for this report. A full copy of the City of Cockburn Age Friendly Accommodation Report is available on request.

## Supported Accommodation Need for City of Cockburn 2006-2021

A key mechanism used by the Australian Government in planning residential aged care service provision is the planning target for levels of provision relative to population. In 2006, this target was 88 residential aged care places per 1,000 persons aged 70 and over. Of these 88 places, 40 were targeted to high-care places and 48 to low-care places. This planning target has applied since 2004.

The following figures are based on this planning target and population projections from Western Australian Planning Commission November 2005. The beds have not been divided into low and high care beds as there is some flexibility in how services allocate beds according to the need and funding at the time.

## Table 9.0 Supported Accommodation Need for City of Cockburn 2006-2021

(Western Australian Planning Commission November 2005 and ABS census data 2006)

|  | Persons 70 - 74 | Persons 75+ | Total Persons >70 | Targeted Beds |
| --- | --- | --- | --- | --- |
| Actual figures for 2006 | 1964 | 3136 | 5100 | 449 |
| Projected figures for 2011 | 2500 | 3900 | 6400 | 563 |
| Projected figures for 2016 | 3100 | 5100 | 8200 | 722 |
| Projected figures for 2021 | 4300 | 6500 | 10800 | 950 |

Only a small proportion of the older population of Australia is in residential aged care at any point in time. Use of residential aged care is higher for women than men and increases substantially for women with increased age.

## Identified Shortfall in Supported Accommodation Need 2006-2021

There are currently two new facilities planned for the area that will add a further 150 beds to the total and these have been included into the identified beds for 2011.

## Table 10.0 Identified Shortfall in Supported Accommodation Need 2006-2021

|  | 2006 | Projected need 2011 | Projected need 2016 | Projected need 2021 |
| --- | --- | --- | --- | --- |
| Targeted Beds for Supported Accommodation | 449 | 563 | 722 | 950 |
| Identified beds(includes current plus new developments) | 365 | 515 | 515 | 515 |
| Shortfall | 84 | 48 | 207 | 435 |

There are facilities located in nearby suburbs but these have not been included in this calculation.  Although some facilities are extremely close it is important to remember that older residents want to stay within a community that is familiar and to which they currently belong.

## Independent Retirement Accommodation Need

Although there is no identified figure to assess need for independent retirement options it appears that the 529 available options is not adequate to meet the current population of 12,620 (or the middle age group 45 to 64) or the projected population growth for this group especially considering the changing expectations to actively remain within the community both for living and working options. These post war baby boomers will account for the large bulge in the population of ‘older old’ people (over 80 years) between 2026 and 2036.

## Respite Accommodation Need

There is a limited suitable respite accommodation directly available across the entire metropolitan with waiting times for planned respite being longer than twelve months in most places. Emergency respite options are extremely limited. There is a possibility for increasing some carer respite through community services but this does not take into account short term respite options or emergency situations.

## Home Based Accommodation Need

It is important to remember that there is an increased trend in accommodation provision to support people within their current situation as long as possible through the provision of home based services. This means that the current community services provided by the City of Cockburn must continue to expand in order to meet this trend.

## Accommodation Strategies

The following strategies are incorporated in the Housing Outcome area and Community and health services Outcome area of the Age Friendly Strategic Plan:

Strategy 1:  That the City of Cockburn continues to expand the range of community services available to support people to remain in their current accommodation as long as possible.

This includes:

- increasing the community care packages currently available

- applying for Extended Aged Care at Home (EACH)

- continuing the current range of services

- Explore feasibility of a range of emergency and ongoing respite services

Strategy 2: That the City of Cockburn explores further the feasibility of a joint venture for the vertical development on the Phoenix Central site in relation to both supported accommodation and self funded retirement accommodation.

The current and projected figures for supported accommodation show a definite shortfall that will get significantly worse in the near future, with a projected shortfall of 207 beds in ten years time and 435 beds in 2021.  Planning for future development needs to commence immediately.

The current Phoenix Central redevelopment was looked at as a possible suitable environment for future accommodation development. Although this location does not fully support the best practice concept of ageing in place because of the overall available size of the site, it does have some features including proximity to community services such as library, shopping centre, medical services, cafes and recreational options.

The site may be able to sustain some vertical development that could provide a range of accommodation options in keeping with ageing in place. There are some drawbacks to vertical development including the cost for the developer, the size of the project required to make it financially viable for them and the suitability of access for use by an ageing population. There is also the consideration for council that there will be a cost if a joint venture with a not for profit organization is progressed as they are exempt from paying rates.

There is scope to include a development for independent funded retirement accommodation on the current Phoenix Central site. This would be in keeping with the growing trend for the ageing population to down size into affordable housing that is neither isolated nor age specific. Future development of the site along Spearwood Avenue may be able to include a supported accommodation facility to compliment retirement accommodation.  Increasing the land holding would be necessary and options may include a joint venture with a developer but further planning assessment would be necessary.

Strategy 3: That the City of Cockburn identifies suitable opportunities to develop supported accommodation as an integral component of all future redevelopments.

The recommendation for current development of supported accommodation facilities is a minimum of 6-8 hectares. There were no readily available sites identified by the Planning Department that could easily be used to support future accommodation needs. This lack of suitable locations raises concerns regarding the shortfall of accommodation in the near future.

It will be crucial that the City of Cockburn actively target supported accommodation development in any future redevelopment in order to meet the identified needs.

The above strategies are included in the Community and health services

and Housing outcome areas within the plan.

# VISION FOR AN AGE-FRIENDLY CITY

The City of Cockburn is committed to ensuring that the community is an accessible and inclusive community in which all council functions, facilities and services (both in-house and contracted) are open, available and accessible for all people, providing the ageing population with the same opportunities, rights and responsibilities enjoyed by all other people in the community.

The City of Cockburn supports the development of an age-friendly city that adapts its structures and services to be accessible to and inclusive of older people with varying needs and capacities. It strives to develop policies, services, settings and structures that support and enable people to age actively by:

- recognizing the wide range of capacities and resources among older people;

- anticipating and responding flexibly to ageing-related needs and preferences;

- respecting their decisions and lifestyle choices;

- protecting those who are most vulnerable; and

- promoting their inclusion in and contribution to all areas of community life.

# STRATEGIES TO DEVELOP AN AGE- FRIENDLY CITY

Eight outcomes have been considered in developing the Age friendly City Strategic plan.

These outcome areas provide a framework for translating the principles of the WHO global age-friendly cities into tangible and achievable results.  Please refer to the Age Friendly Implementation Plan for more detail in relation to the specific tasks that will be undertaken in the implementation of each strategy. The Implementation plan will be formally reviewed and updated once per annum and is attached as Appendix 3.

## Outdoor Spaces and Buildings

Outcome:  That the ageing population in the City of Cockburn has access to age friendly built environments that support independence, quality of life and safety for older people and positively affect their ability to “age in place”.

| STRATEGY | Time Frame | Resources |
| --- | --- | --- |
| To promote age friendly built environments and foster age friendly community planning and design | 2010 | Existing |
| To create safe and secure pedestrian environments | Ongoing | Footpath and Bike path strategy identifies resource needs |
| To support recreation facilities, parks and walkways that support access for the ageing population | 2009 | Sport and Recreation Plan identifies resource needs |
| To continue to provide information and services that focuses on preventing crime, fire and injury affecting older people | Ongoing | Existing |

## Transportation

Outcome:  That the ageing population in the City of Cockburn has access to affordable and equitable transport to support social and civic participation and access to community and health services.

| STRATEGY | Time Frame | Resources |
| --- | --- | --- |
| To improve the mobility and transport options available for seniors | 2009 | Seniors Centre Coordinator/ Travel Smart Officer |
| To provide an additional community bus to support access for seniors | Underway | $125,000 bus purchased 08/09 |

## Housing

Outcome: That the ageing population in the City of Cockburn has access to affordable suitable housing options that allow them to age safely and be socially supported  within the community to which they belong.

| STRATEGY | Time Frame | Resources |
| --- | --- | --- |
| That the City of Cockburn explores further the feasibility of a joint venture for the vertical development on the Phoenix Central site in relation to both supported accommodation and self funded retirement accommodation. | 2010 | Existing |
| That the City of Cockburn identifies suitable opportunities to develop supported accommodation as an integral component of all future redevelopments. | 2009 | Existing |
| To support the development of suitable affordable housing options | Ongoing | Consultant |
| To ensure where possible that appropriate services, amenities and activities are accessible within the surrounding community to support ageing in place. | Ongoing | Existing |

## Social Participation

Outcome:  That the ageing population in the City of Cockburn has affordable and equitable access to activities and events that support social participation and fosters well being and social integration.

| STRATEGY | Time Frame | Resources |
| --- | --- | --- |
| To provide an interim facility that provides and coordinates social and recreational activities for seniors until the Phoenix Central Civic Precinct Redevelopment has been completed | July 2009 | Capital Works and Fit out $600,000. Net Operational Cost after income $265,000 per annum |
| To provide a suitable facility in the Phoenix Central Civic Precinct Redevelopment that provides and coordinates social and recreational activities for seniors | 2011/12 | To be costed once concept plan is finalised |
| To investigate the social and recreational needs for seniors in the South Eastern Quadrant and provide a satellite service to meet the identified local need | 2013/14 | Consultant |
| To provide relevant activities that reflect the WA Active Ageing Strategy | 2009 | Interim Seniors Centre |
| To support equitable and affordable access to senior social groups and facilities | 2009 | Interim Seniors Centre/ Seniors Centre Coordinator |

## Respect and Social Inclusion

Outcome: that the ageing population in the City of Cockburn are recognized and included as valuable members in the social, civic and economic life of the city.

| STRATEGY | Time Frame | Resources |
| --- | --- | --- |
| To develop a media strategy that positively reflects the diversity of the ageing population | Ongoing | Existing |
| To continue to encourage and develop programmes and community activities that support intergenerational and family interactions | Ongoing | Existing and Grants |
| To support community education by providing opportunities for older people to share their knowledge, history and expertise with other generations | Ongoing | Existing |

## Civic Participation and Employment

Outcome: That the ageing population in the City of Cockburn has access to opportunities to continue to contribute to their communities, through paid employment or voluntary work if they so choose, and to be engaged in the political process.

| STRATEGY | Time Frame | Resources |
| --- | --- | --- |
| To establish regular consultation that increases senior participation in decision making including the Regional Seniors Group and other relevant groups | Ongoing | Seniors Centre Coordinator |
| To continue to support and encourage participation in the City of Cockburn’s Volunteer Resource Centre. | Ongoing | Existing |
| To continue to support and facilitate flexible employment opportunities for seniors within the City of Cockburn | Ongoing | Existing |

## Communication and Information

Outcome: That relevant information is readily accessible to older people with varying capacities and resources

| STRATEGY | Time Frame | Resources |
| --- | --- | --- |
| To provide information in appropriate and accessible formats to all seniors regarding current issues, services and events. | Ongoing | Interim Seniors Centre and Grant funding |
| To provide opportunities for seniors to participate in the use of new information technology. | Ongoing | Grant funding and Existing |
| To facilitate programmes to prepare and support seniors approaching retirement. | 2009 | Seniors Centre Coordinator |

## Community and Health Services

Outcome: That the ageing population in the City of Cockburn has access to affordable quality community support services and health care.

| STRATEGY | Time Frame | Resources |
| --- | --- | --- |
| That the City of Cockburn continues to expand the range of community services available to support people to remain in their current accommodation as long as possible. | Ongoing | Existing |
| To investigate and support affordable home based services for all seniors | Ongoing | Existing |
| To investigate the need for additional home based services not currently provided by HAAC or CACP | 2009/10 | Existing |
| To continue to support existing services such as HACC services, CACP, Safer City, and Mobile Library Service and ensure relevant standards and accreditation requirements are continually met. | Ongoing | Existing |
| To support outreach health services that improve access to affordable medical services | 2009/10 | Existing |
| To provide a Seniors Centre Coordinator to manage and facilitate services and information across the organization | Underway | Seniors Centre Coordinator appointed 2008 |

# REFERENCES

The National Strategy for an Ageing Australia – 2004 http://www.health.gov.au/internet/wcms/publishing.nsf/Content/ageing-ofoa-agepolicy-nsaa-nsaabk7.htm

Age-friendly built environments: Opportunities for Local Government Australian local Government Association

Awareness to action: Local government’s response to population ageing Australian local Government Association

Ageing-in-place > Implications for Local Government Australian local Government Association

Ageing Awareness and Action Survey Report 2006 Australian Local Government Association

Response to the senate enquiry into aged care, 28th July 2004  Dr Roderick McKay, Director of Aged Care Psychiatry, Braeside Hospital, Hope Healthcare and Regina McDonald, Area - Clinical Nurse Consultant, Aged Care Psychiatry

Ageing Gracefully An Overview of the Economic Implications of Australia’s Ageing Population Profile Prepared for the Commonwealth Department of Health and Aged Care February 2000

Promoting Healthy Ageing In Australia: Prime Minister’s Science, Engineering And Innovation Council

A review of healthy ageing research in Australia  report prepared for the Community services

Ministers’ advisory Council 2000

Securing the future of Aged Care for Australians Commonwealth of Australia 2007

Seniors Resources On line http://www.community.wa.gov.au/

Publications

World Health Organization's Global Age-friendly Cities Guide and Checklist

Active Ageing Benchmark Indicators

World Health Organization's Global Age-friendly Cities Guide and Checklist

Active Ageing Strategy, Generations Together: Report 2004 - 2008

Progress report of the Western Australian Active Ageing Strategy

Generations Together Summary 2007

# APPENDIX

## Appendix 1: Summary of Relevant Initiatives in Australia

### The National Strategy for an Ageing Australia

In December 1997 the Government released its National Strategy for an Ageing Australia.  In this report it is noted that the number of Australians over sixty-five years of age will more than double in the next thirty years. The report identified broad areas of change and a range of issues to be addressed. These include:

- an ageing workforce and the need for action as the supply of younger entrants drops dramatically but the demand for economic growth persists and competition in a global economy continues to increase;

- the need for adequate levels of, and sustainable sources of, retirement incomes to support retirement living;

- the need for positive individual and community attitudes to ageing;

- the need for age-friendly infrastructure and community support (including housing, transport and communications), to enable greater numbers of older Australians to participate in and remain connected to society;

- the importance of healthy ageing to enable a greater number of older people to remain healthy and independent for as long as possible; and

- a growing demand for accessible, appropriate and high quality health and aged care services.

### Generations Together: Western Australia’s Active Ageing Strategy

Generations Together: A Guide to the Western Australian Active Ageing Strategy was launched in March 2004. The Strategy provides a whole-of-government framework for responding to the challenges and opportunities presented by our ageing population and to the needs of today’s seniors.

The strategy includes five identified priority areas under which government initiatives will be developed. The priority areas are:

- Health and Wellbeing;

- Employment and Learning;

- Community Awareness and Participation;

- Protection and Security; and

- Planning and the Built Environment.

http://www.community.wa.gov.au/Communities/Seniors/Publications/Generations_Together_A_Progress_Report.htm

### The Active Ageing Benchmark Indicators

In March 2006, The Department of Community Development (Office for Seniors Interest and Volunteering) launched The Active Ageing Benchmark Indicators, which is the set of community indicators developed to report on the status of active ageing among Western Australia’s Seniors.  These benchmarks were developed in consultation with the World Health Organisation, Council on the Ageing (WA) and several other state government departments. This information will assist in providing the strategic direction for future initiatives.

http://www.community.wa.gov.au/Active_Ageing_Benchmark_Indicators.htm

### Transitions in Ageing

In 2005, the Office of Seniors Interests and Volunteering carried out an extensive consumer consultation process.   Transitions in Ageing is a major research project investigating the importance of various changes and events in the lives on Western Australians aged 65 years and over, collated through in-depth interviews and a telephone survey of 600 WA Seniors. It examines what they consider to be positive and negative influences on their lives and how their own perception of how well they are ageing tallies with the definition of successful ageing established through previous research.

Full report: http://www.community.wa.gov.au/

### Local Government Trends

The Australian Local Government Association (ALGA) www.alga.asn.au and the Department of Health and Ageing are working together to help local government meet the specific opportunities and challenges of an ageing population through the local government and population ageing project. The first step of the partnership was the development of an action plan to engage local government in a planned and coordinated national approach to population ageing issue

ALGA has established a separate website resource to assist local government to plan for an ageing population. The website Planning for an ageing community, showcases the latest news, research, data, information and innovative practice.

ALGA has also developed an “Ageing Toolbox” which can assist local government in planning for an ageing community.

### Ageing in Place

The principles of providing ageing in place were introduced as part of the reforms introduced by the Aged Care Act 1997 and the Aged Care Principles incorporating the Accreditation Grant Principles

Previously individuals had access to either nursing home or hostel level accommodation and when hostel residents care needs increased they were moved to a nursing home. The effect of moving can be highly distressing to both the resident and their family members. When managed effectively, ageing in place can have great benefits for the individual and their family in allowing them to remain in a familiar environment.

## Appendix 2:  Aged Care Facilities within a 15km radius of Cockburn Central

| Villa Dalmacia Aged Care Facility | Spearwood, WA | Less than 1 km |
| --- | --- | --- |
| Illawong Village Hostel | Hamilton Hill, WA | 2 km |
| Carrington Aged Care Facility | Hamilton Hill, WA | 2 km |
| John Mercer Lodge | Hilton, WA | 3 km |
| Hale Hostel (Locally known as Amana Living - Hale Hostel) | Coolbellup, WA | 4 km |
| Brightwater - South Lakes Care Facility | South Lake, WA | 7 km |
| Frank Prendergast House | Success, WA | 9 km |
| Italian Village Fremantle | White Gum Valley, WA | 4 km |
| St Francis Aged Care | Fremantle, WA | 6 km |
| Avalon Apartments | Murdoch, WA | 6 km |
| Braemar Village | Willagee, WA | 7 km |
| Braemar House | East Fremantle, WA | 7 km |
| Craigcare Melville | Melville, WA | 7 km |
| Pilgrim House | East Fremantle, WA | 7 km |
| St Ives Eldercare Melville | Myaree, WA | 8 km |
| Carinya Of Bicton | Bicton, WA | 8 km |
| Braemar Lodge | Bicton, WA | 8 km |
| Hillcrest Nursing Home | North Fremantle, WA | 8 km |
| Hillcrest Residence | North Fremantle, WA | 8 km |
| Regents Garden Four Seasons Booragoon | Booragoon, WA | 8 km |
| Dorothy Genders Hostel (Locally known as Amana Living - Dorothy Genders Hostel) | Mosman Park, WA | 9 km |
| River Sea Hostel | Mosman Park, WA | 9 km |
| Regents Garden - Bateman | Bateman, WA | 10 km |
| Dean Lodge | Bull Creek, WA | 10 km |
| Gordon Lodge | Bull Creek, WA | 10 km |
| Freshwater Bay Nursing Home | Mosman Park, WA | 10 km |
| Mosman Park Nursing Home | Mosman Park, WA | 10 km |
| Frederick Guest Hostel (Locally known as Amana Living - Frederick Guest House) | Bull Creek, WA | 10 km |
| Wearne Hostel | Cottesloe, WA | 11 km |
| Lefroy Hostel (Locally known as Amana Living - Lefroy Hostel) | Bull Creek, WA | 11 km |
| Adventist Residential Care | Rossmoyne, WA | 11 km |
| Sundowner Hostel (Locally known as Amana Living - Sundowner Hostel) | Cottesloe, WA | 12 km |
| Joseph Cooke Hostel | Rossmoyne, WA | 12 km |
| Leslie A Watson Nursing Home | Salter Point, WA | 13 km |
| Melvista Nursing Home | Nedlands, WA | 13 km |
| Margaret Hubery House | Shelley, WA | 13 km |
| Applecross Nursing Home | Applecross, WA | 13 km |
| Alfred Carson Lodge | Claremont, WA | 13 km |
| Peter Arney Home (Locally known as Amana Living - Peter Arney Home) | Salter Point, WA | 13 km |
| McDougall Park Nursing Home | Como, WA | 14 km |
| Canning Lodge | Willeton, WA | 14 km |
| Como House | Como, WA | 14 km |
| Meath Care Como | Como, WA | 15 km |
| Hollywood Village Nursing Home | Nedlands, WA | 15 km |
| Warrina Hostel | Nedlands, WA | 15 km |
| Weston Lodge | Nedlands, WA | 15 km |
| Elloura Lodge | Nedlands, WA | 15 km |
| Craigcare Como | Como, WA | 15 km |
| Collier Park Hostel | Como, WA | 15 km |
| Concorde Nursing Home | South Perth, WA | 16 km |
| Annesley Residential Aged Care Facility | Bentley, WA | 17 km |
| Trinity Lodge | Bentley, WA | 17 km |
| Agmaroy Nursing Home | Wilson, WA | 17 km |
| Castledare Retirement Village | Wilson, WA | 17 km |
| Hilltop Lodge | Bentley, WA | 17 km |
| Cygnet Lodge | Bentley, WA | 17 km |
| Tandara/Ningana Nursing Home | Bentley, WA | 17 km |
| Waminda Hostel | Bentley, WA | 17 km |
| Kensington Park Nursing Home | Kensington, WA | 18 km |
| Craigcare St James | St James, WA | 19 km |

## Appendix 3:  Aged Friendly Implementation Plan Updated June 2009

# Reviewed June 2009

# City of Cockburn

# Age- Friendly Strategic Plan

# Implementation

The Implementation plan has been collated as a guide for possible tasks to be undertaken. It reflects the issues collected during the initial consultation and suggestions from relevant research and staff that can be undertaken to develop an age-friendly community.

# Resources

World Health Organization Global Age-Friendly Cities: Guide has been used as the framework for the Strategic plan and the subsequent implementation plan. It was developed through consultation with older people who outlined what they thought an age-friendly city should be. About 1500 older people described the advantages and disadvantages faced in eight areas of city living that are outlined in the following document. Service providers were also consulted. It proposes easy ways and affordable measures to make a city more age-friendly.

Age-friendly built environments: Opportunities for Local Government, prepared by Australian Local Government Association. This document was developed by the ALGA to support Local Governments towards the development of age friendly built environments. www.alga.asn.au

Planning the local government response to ageing and place (2004) examines population ageing and its potential impact on local government. The publication includes a framework for assessing the social, environmental and economic impacts of ageing for councils. Local Government and Shires Associations of NSW www.lgsa.gov.au

A guide to Integrated Local Area Planning (1993) helps councils implement the ILAP process in their local areas. ALGA website www.alga.asn.au

An older Australia: Identifying areas for local government action (2004) acts as a starting point for discussion through the

identification of the key opportunities and challenges that require a local government response. ALGA website

www.alga.asn.au/ageing

LGA population ageing self completing diagnostic tool (2003) enables the local government practitioner to assess the relative impact ageing and migration patterns are likely to have on the local economy and local government finances. Available in the 2003 State of the Regions report. ALGA website www.alga.asn.au

Active Ageing: A Policy Framework (2002) is intended to inform discussion and the formulation of action plans that promote healthy and active ageing. WHO website www.who.int

Ottawa Charter for Health Promotion (1986) provides a framework for action to achieve health for all. Health promotion

action means: developing personal skills, creating supportive environments, strengthening community action, building healthy public policies and reorienting health services. WHO website /www.who.int

## Outdoor Spaces and Buildings

### The outside environment and public buildings have a major impact on the mobility, independence and quality of life of older people and affect their ability to “age in place”.  Global Age Friendly Cities

The feedback from the original report indicated concerns regarding:

Inadequate safety and security for some seniors both in home and the community

Poor condition of some roads and footpaths (ie more kerbs for gophers, road crossings, footpath signage for dual usage, rest benches and sheltered bus stops)

Unfriendly shopping centres for seniors to sit and feel part of the community

Lack of promotion of services that council provide for seniors (ie Safer City Program, Volunteer Support Centre, HACC programs, neighbour complaints)

## Outdoor Spaces and Buildings

Outcome:  That the ageing population in the City of Cockburn has access to age friendly built environments that support independence and quality of life of older people and positively affect their ability to “age in place”.

| Strategy | Tasks | Time frame | Cost | Responsibility | Status |
| --- | --- | --- | --- | --- | --- |
| To promote age friendly built environments and foster age friendly community planning and design |  Develop and adopt policies and practices that promote and support ‘active ageing’ | Ongoing | Ongoing Budgets, as appropriate | Manager Engineering Services, in conjunction with Manager Human Services | Commenced with Development of procedures and design of Interim seniors Centre |
|  |  Ensure that development, safety and master planning for parks, gardens and public spaces maintain an awareness of passive recreation opportunities for older people | Ongoing | Ongoing Budgets, as appropriate | Manager Engineering Services, in conjunction with Manager Human Services | Seniors Coordinator to raise awareness of active ageing |
| To create safe and secure pedestrian environments | Improve and maintain the road and footpath network | Ongoing | Ongoing Budgets, as appropriate | Manager Engineering Services, in conjunction with Manager, Human Services | Seniors Coordinator to raise awareness of Age Friendly plan |
|  |  Include requests by seniors for road and footpath improvements in the Engineering Services Capital Works program |  |  |  |  |
|  |  Include more kerbs for access by gophers, shop riders, wheelchairs and prams |  |  |  |  |
|  |  Develop dual usage footpaths with clear signage |  |  |  |  |
|  |  Repair cracks in pavements |  |  |  |  |
|  |  Develop signage for streets and businesses that is legible for both drivers and pedestrians |  |  |  |  |
|  | Improve street crossings | Ongoing | Ongoing Budgets, as appropriate | Manager Engineering Services, in conjunction with Manager, Human Services | Seniors Coordinator to raise awareness of Age Friendly plan |
|  |  Replace existing street signage with larger lettering, colour contrast, plain fonts and non reflective surfaces |  |  |  |  |
|  |  Ensure the design of roads and intersections take account of the mobility, visual and hearing capacity of all community members, not just the young and the agile |  |  |  |  |
|  |  Implement safety measures such as adequately timed lights, disability access compliance, clearly marked crosswalks at intersections and traffic-calming devices |  |  |  |  |
| To support recreation facilities, parks and walkways that support access for the ageing population | Develop a walking friendly environment | Ongoing | Ongoing Budgets, as appropriate | Manager Parks, in conjunction with Manager, Human Services. | Seniors Coordinator to raise awareness of Age Friendly plan |
|  |  Review the existing system of parks and tracks and identify ways to expand and improve connections |  |  |  |  |
|  |  Include rest benches, shaded sitting areas and sheltered bus stops |  |  |  |  |
|  |  Ensure that residents have access to walking and cycling tracks and community fitness centers. |  |  |  |  |
|  |  Maintain and create neighbourhood parks. |  |  |  |  |
|  |  Remove graffiti and rubbish |  |  |  |  |
| To continue to provide information and services that focuses on preventing crime, fire and injury affecting older people | Employ strategies for enhancing security through urban design techniques such as crime prevention through environment design (CPTED) | Ongoing | Ongoing Budgets, as appropriate | Ranger and Community Safety Services Manager, in conjunction with Manager, Human Services. | Seniors Coordinator and Aged and Disabled Services Manager to raise awareness of Age Friendly plan and Safer Senior services |
|  |  Consider and consult older people in the development of city and neighbourhood community safety plans |  |  |  |  |
|  |  Provide sufficient lighting |  |  | Ranger and Community Safety Coordinator in conjunction with Aged and Disabled Services Manager. |  |
|  |  Clean up and patrol vacant properties |  |  |  |  |
|  |  Continue community patrols in Cockburn |  |  |  |  |
|  |  Increase awareness of current Safer Senior Service |  |  |  |  |
|  |  Continue workshops |  |  |  |  |

## Transportation

### “Transportation, including accessible and affordable public transport, is a key factor influencing active ageing. In particular, being able to move about the city determines social and civic participation and access to community and health services.” Global Age Friendly Cities

This issue was highlighted consistently and passionately by many Cockburn seniors and service providers in the consultation findings.  About half of the survey respondents indicated the current transport system does not meet their needs.

Specific requests were made for:

- a direct and frequent bus from Coolbellup to Fremantle;

- a bus to/from Lakeside Village;

- bus service to/from Success Village;

- buses to stop directly outside entrances to Coolbellup and Kardinya shopping centers

- direct bus routes to Fremantle or Armadale

Many seniors indicated their appreciation of HACC transport and Dial a Ride service; however there still remains a critical shortage of buses to transport seniors (particularly non eligible HACC clients) for social groups and outings, medical appointments and shopping trips.

## Transportation

Outcome:  That the ageing population in the City of Cockburn has access to affordable and equitable transport to support social and civic participation and access to community and health services.

| Strategy | Tasks | Time frame | Cost | Responsibility | Status |
| --- | --- | --- | --- | --- | --- |
| To improve the mobility and transport options available for seniors |  Advocate and work with Transperth and stakeholders to ensure bus/train routes in areas of greatest need | 2009/10 | Included in role for Seniors Centre Coordinator | Manager Human Services, in conjunction with Coordinator Community Development. | Seniors Coordinator appointed Dec 2008. Travelsmart officer to commence in July 2009 |
|  |  Investigate joint venture bus shuttle service (Ref: City of Subiaco) | 2009/10 | Included in role for Travelsmart officer | Travel Smart Officer | Travelsmart officer will commence in July 2009 |
|  |  Educate seniors on how to best utilize Transperth bus service via Transperth’s Local Area Marketing and Travelsmart project (Ref: City of Melville). | 2010 | Included in role for Travelsmart officer | Seniors Centre Coordinator and Travelsmart officer | Travelsmart officer will commence in July 2009 |
|  |  Review Dial-a- ride service and role of City of Cockburn Community Care service in HAAC transport provision and community transport | 2011 | Existing | Aged and Disabled Services Manager, in conjunction with Manager, Human Services. | Planning stage |
|  |  Support existing programs(Jean Willis Centre) to meet some of the identified transport needs for seniors (including non eligible HACC clients) for social groups and outings, medical appointments and shopping trips if appropriate. | 2009 | Grant Funds | Aged and Disabled Services Manager, in conjunction with Manager, Human Services. | Commenced -Successful grant application for transport. Service commenced |
|  |  Provide coordination of community buses for seniors through the Seniors centre Coordinator position | 2009 | Included in role for Seniors Centre Coordinator | Seniors Centre Coordinator | Seniors Coordinator appointed Dec 2008. Community Bus purchased and service will commence in August 2009 when Seniors Centre is open |
|  |  Undertaking an audit of council owned buses that seniors currently access to identify usage patterns and facilitate access by all senior groups | 2008 | Existing | Manager Human Services | Report complete |
|  |  Develop criteria and procedures for use of community buses to ensure equitable access | 2009 | Included in role for Seniors Centre Coordinator | Seniors Centre Coordinator, in conjunction with Manager Human Services | Seniors Coordinator appointed Dec 2008 currently developing policy and procedure |

| To provide an additional community bus to support access for seniors |  Explore alternative funding grants for buses available for seniors groups including sponsorship by local businesses, corporations and Lotterywest funding | 2008/09 | $125,000 | Manager Human Services | Bus purchased |
| --- | --- | --- | --- | --- | --- |
|  |  Purchasing an additional bus to address shortages for seniors’ outings | 2008/2009 | $125,000 | Manager Human Services | Bus purchased |
|  |  Provide ongoing funding for management of buses | ongoing | Included in role for Seniors Centre Coordinator | Manager Human Services | Seniors Coordinator appointed Dec 2008 |

## Housing

#### “Housing is essential to safety and well-being. There is a link between appropriate housing and access to community and social services in influencing the independence and quality of life of older people. It is clear that housing and support that allow older people to age comfortably and safely within the community to which they belong are universally valued.”

#### Global Age Friendly Cities

The availability of affordable, accessible and suitable housing options is particularly important for older people, and will be a priority as the Australian population ages. The changing age profile, along with lifestyle and work pattern changes, will impact on future housing arrangements. It will therefore be important to provide flexible models of accommodation, encompassing a wide range of settings, while at the same time fostering supportive environments and independence.

The feedback from the original report indicated concerns regarding:

- Limited access to local aged care accommodation facilities providing low and high care

- Inadequate number of respite facilities and carer support services

- Limited ‘affordable and smaller’ housing options for seniors

- Limited Commonwealth funding and inflexibility of current price and volume contract system to meet future aged population needs in the home, hostel and nursing homes

## Housing

Outcome: That the ageing population in the City of Cockburn has access to affordable suitable housing options that allow them to age safely and be socially supported within the community to which they belong.

| Strategy | Tasks | Time frame | Cost | Responsibility | Status |
| --- | --- | --- | --- | --- | --- |
| To support the development of suitable affordable housing options |  Identify and explore opportunities for aged care accommodation in the City of Cockburn by developing an Age Friendly Accommodation Report | April 2008 | budgets, as appropriate | Manager Human Services, in conjunction with Director, Planning and Development | Accommodation report completed in April 2008 |
|  |  Explore accommodation needs and shortfalls for seniors accommodation (see recommendation from Age Friendly Accommodation Report) | April 2008 | budgets, as appropriate | Manager Human Services, in conjunction with Director, Planning and Development | Accommodation report completed in April 2008 |
|  |  Investigate possibility of vertical development of self funded retirement accommodation in Phoenix redevelopment (See recommendation from Accommodation Report) | 2010 | budgets, as appropriate | Manager Human Services, in conjunction with Director, Planning and Development | Need to appoint consultant to investigate in detail once master plan for Cockburn Civic Centre precinct complete |
|  |  Identify possible localities for future development that will support the principles of ageing in place (minimum of 8 – 10 hectares of broad acre parcels for retirement villages and residential aged care facilities, possibly in the South Yangebup/Northern Beeliar areas) (See recommendation from Accommodation Report) | Ongoing | Existing | Manager Human Services, in conjunction with Director, Planning and Development | Investigated green site locations none in existence in Cockburn. Possible redevelopment opportunities for up to 5hectares only |
|  |  Explore joint ventures with developers and Department of Housing and Works, to assist in developing retirement villages and low cost housing for seniors, who require independent living accommodation were feasible | 2010 | Budget as appropriate for consultant | Manager Human Services, in conjunction with Director, Planning and Development | If redevelopment site is identified then Need to appoint consultant to investigate in detail |
|  |  Identify incentives for residential accommodation providers and developers, to assist in developing facilities within the identified areas of need | 2010 | consultant | Manager Human Services in conjunction Manager Strategic Planning | Incentives documented but no sites available of sufficient size in Cockburn |
|  |  Convene a group of current and potential aged care providers and developers to facilitate maximum communication and coordinate the delivery of aged care services | 2010 | Existing | Manager Human Services in conjunction Manager Strategic Planning | Planning stage |
|  | Develop suitable planning policies and strategies that support Age friendly built environments as identified in the publication Age-friendly built environments: Opportunities for Local Government prepared by Australian Local Government Association | Ongoing | Ongoing Budgets, as appropriate | Manager Human Services, in conjunction with Director, Planning and Development | Implementation strategy needs to be developed |
|  | Examples: |  |  |  |  |
|  |  Develop a community information strategy to promote housing options for seniors | Ongoing | Included in role of Seniors Centre Coordinator | Seniors Centre Coordinator in conjunction with Manager Human Services | Information Workshops to commence once Seniors Centre is operational |
|  |  Support and/or resource demonstration projects that encourage innovation in design and diversity of housing choice for seniors | Ongoing | Existing | Manager Planning Services | Planning stage |
|  |  Streamline approval processes to facilitate the production of seniors’ housing developments, in particular residential aged care facilities | Ongoing | Existing | Manager Planning Services | Planning stage |
|  |  Develop an age friendly assessment procedure for housing development applications | Ongoing | Existing | Manager Planning Services | Planning stage |
|  |  Ensure seniors are consulted in the planning and location of aged housing developments | Ongoing | Existing | Manager Planning Services | Planning stage |
|  |  Promote universal design and ‘smart housing’ principles in housing developments | Ongoing | Existing | Manager Planning Services | Planning stage |
|  |  Establish mechanisms to encourage suitable housing outcomes for seniors | Ongoing | Existing | Manager Planning Services | Planning stage |
| To ensure where possible that appropriate services, amenities and activities are accessible within the surrounding community to support ageing in place. |  Apply for increased Community Aged Care Packages, Extended Aged Care at Home (EACH) and HAAC services (See recommendation for Accommodation Report) | ongoing | Grant Funds to be accessed, where available | Manager Human Services, in conjunction with Aged and Disabled Services Manager | Application submitted. unsuccessful will apply again next funding round |
|  |  Continue HACC program and explores other means of innovative care delivery | ongoing | Grant Funds to be accessed, where available | Manager Human Services, in conjunction with Aged and Disabled Services Manager | Continuous process |
|  |  Promote ageing-in-place as a preference for seniors | ongoing | Grant Funds to be accessed, where available | Manager Human Services, in conjunction with Aged and Disabled Services Manager | Continuous process |
|  |  Sponsor workshops that concern seniors—safety in the home, prevention of falls and injury prevention, care issues and home security | ongoing | Grant Funds to be accessed, where available | Seniors Centre Coordinator in conjunction with Manager Human Services | Will commence once seniors centre is operational |

## Social participation

#### Social participation and social support are strongly connected to good health and well-being throughout life. Participating in leisure, social, cultural and spiritual activities in the community, as well as with the family, allows older people to continue to exercise their competence, to enjoy respect and esteem, and to maintain or establish supportive and caring relationships. It fosters social integration and is the key to staying informed. -------The biggest concerns are affordability and accessibility, especially for people with disabilities, and awareness of activities and events. Having appropriate support in place to enable accessibility, particularly for people with mobility issues, is very important.

#### Global Age Friendly Cities

Think tank participants highlighted the need for council to provide more recreation and physical activities for seniors to strengthen mobility, cardiovascular systems and to keep lonely seniors engaged with the community.  Feedback from the surveys and focus groups indicated the main barriers to participation in physical activity were

cost (more affordable social activities required; inability for smaller ‘not incorporated’ social groups to access funding and transport, rentals viability of social/recreation groups/events)

transport, (lack of bus transport for group outings,

lack of information

Isolation & loneliness of seniors (some difficulties accessing social groups available)

more social events needed at night;

inappropriate council facilities becoming unsuitable/unsafe for senior activities;

Lack of services in new suburbs ( ie Atwell, Success, Yangebup etc)

Lack of affordable and culturally appropriate social and recreational services for culturally and linguistically diverse (CALD) seniors

## Social participation

Outcome:  That the ageing population in the City of Cockburn has affordable and equitable access to activities and events that support social participation and fosters well being and social integration.

| Strategy | Tasks | Time frame | Cost | Responsibility | Status |
| --- | --- | --- | --- | --- | --- |
| To provide an interim facility that provides and coordinates social and recreational activities for seniors until the Phoenix Central Civic Precinct Redevelopment has been completed | • Identify the time frame of the Phoenix redevelopment | 2008/09 |  | Manager, Human Services | Seniors Centre will be officially opening on the 31st of July 2009 |
|  | • Investigate feasibility of relocating seniors to civic centre. Management Plan complete and Council Decision received in June 2008 to relocate seniors to civic centre. Investigate feasibility of relocating seniors to civic centre. Management Plan complete and Council Decision received in June 2008 to relocate seniors to civic centre. | Council decision to relocate June 2009 Management Plan for centre completed Building Refurbishment completed June 2009 | $500,000 (Construction) $100,000 (Fit Out) $265,000 (Annual operational) | Manager, Human Services | All aspects of planning and building refurbishment complete. Furniture and equipment fit our underway and Seniors Centre will be officially opening on the 31st of July 2009 |
|  | • Develop an interim model for the seniors centre operation – | 2008/2009 | Consultant | Manager, Human Services | Management plan for centre Complete inclusive of model .All aspects of planning complete. |
|  | • Commence refurbishment of the civic centre for use as a seniors centre | 2008 | $500,000 (Construction) $100,000 (Fit Out) $265,000 (Annual operational) | Manager, Human Services | All aspects of planning and building refurbishment complete. Furniture and equipment fit our underway and Seniors Centre will be officially opening on the 31st of July 2009 |
|  | • Review operation of Seniors centre 6 and 12 months from commencement of operation | 2010 | Existing | Manager, Human Services | KPI’s being developed |
| To provide a suitable facility in the Phoenix Central Civic Precinct Redevelopment that provides and coordinates social and recreational activities for seniors | • Develop a best practice model for social inclusion that meets the need of the local senior residents | 2011/12 | TBC | Manager Human Services and Seniors Centre Coordinator | Planning stage |
|  | • To develop a Capital Works program to upgrade or build a new purpose built facility to meet the recreational and social needs of senior residents located in Hamilton Hill and Spearwood (Due to the majority of the current population of seniors being located in the Spearwood an Hamilton Hill) | 2011/12 | TBC | Manager Human Services | Planning stage |
| To investigate the social and recreational needs for seniors in the South Eastern Quadrant and provide a satellite service to meet the identified local need | • Monitor local needs and Identify opportunities for inclusion of space for seniors activities in new developments in the area (Due to most of the current seniors services being located in Spearwood and Hamilton Hill in the future dependant upon seniors population growth in the South East Quadrant there may be a need for satellite services to be located closer geographically to improve accessibility of services) | 2009 onwards | Included in role of Seniors Centre Coordinator | Manager Human Services and Seniors Centre Coordinator | Planning stage |
|  | • Consult with local seniors regarding their needs at the time of planning | ongoing | Included in role of Seniors Centre Coordinator | Manager Human Services and Seniors Centre Coordinator | Seniors Coordinator appointed Dec 2008 |
|  | • To ensure any facility developed meets the best practice standards at the time | 2011/12 | Budget as appropriate/ Consultant | Manager Human Services and Seniors Centre Coordinator | Planning stage |
| To provide relevant activities that reflect the WA Active Ageing Strategy | Coordinate regular recreational/physical activities for seniors | 2009 | Included in role of Seniors Centre Coordinator | Manager Human Services and Seniors Centre Coordinator | Seniors Centre will be officially opening on the 31st of July 2009 |
|  |  Encourage and support local recreation and leisure facilities to provide affordable physical activity classes for seniors including —fitness, strength, flexibility and balancing activities . To continue to offer appropriate and sustainable “Happening Seniors “ activities at the new Seniors Centre | ongoing | Included in role of Seniors Centre Coordinator | Manager Human Services and Seniors Centre Coordinator | Seniors Coordinator appointed Dec 2008 will progress once Seniors Centre is operational in July 2009 |
|  |  Coordinate social and recreation activities that integrate lonely male, frail, people with a disability, over 50’s and CALD seniors | ongoing | Included in role of Seniors Centre Coordinator | Manager Human Services and Seniors Centre Coordinator | Seniors Coordinator appointed Dec 2008 will progress once Seniors Centre is operational in July 2009. |
|  |  Support walking and cycling clubs to use the extensive pathways and parks in the city | ongoing | Existing | Manager Community Services and Recreations Services Coordinator | Commenced |
|  |  Promote special events and education seminars that support active living and increase awareness regarding health issues (e.g. Seniors’ Wellbeing Expo) | 2009 | Included in role of Seniors Centre Coordinator | Manager Human Services and Seniors Centre Coordinator | Seniors Coordinator appointed Dec 2008 will progress once Seniors Centre is operational in July 2009. |
|  | Support and attract counseling services |  |  |  |  |
|  |  access HACC funding for counseling services | 2010 | Grant Funds to be accessed, where available. | Aged and Disabled Services Manager | Planning stage |
| To support equitable and affordable access to senior social groups and facilities |  Hold a series of forums with Cockburn social groups to facilitate communication, cooperation and collaboration with the purpose of minimizing social isolation, providing access to wider range of people, activities and resources and gaining leverage for buying/funding power | 2008 onwards | Included in role of Seniors Centre Coordinator | Manager Human Services and Seniors Centre Coordinator | Seniors Coordinator appointed Dec 2008. Currently supporting the Regional Seniors Group to take on this role. |
|  |  Investigate and support opportunities for senior social groups to share resources and attend each other’s social group functions e.g. buses, bingo machines, carpet bowling equipment | 2009 | Included in role of Seniors Centre Coordinator | Manager Human Services and Seniors Centre Coordinator | Seniors Coordinator appointed Dec 2008. Currently supporting the Regional Seniors Group to undertake this task |
|  |  Investigate options to support local social groups that may be too small to gain incorporation or be eligible for HAAC funding including amalgamation of groups and/or alternative funding | 2010 | Included in role of Seniors Centre Coordinator | Manager Human Services and Seniors Centre Coordinator | Seniors Coordinator appointed Dec 2008. Currently supporting the Regional Seniors Group to undertake |
|  |  Support opportunities for social groups to work collaboratively on joint projects e.g. knitting for the homeless youth | 2010 | Included in role of Seniors Centre Coordinator | Manager Human Services and Seniors Centre Coordinator | Seniors Coordinator appointed Dec 2008. Currently supporting the Regional Seniors Group to undertake |
|  |  Develop a Code of Conduct for social and recreation groups using council facilities to establish equitable entry to groups | 2010 | Included in role of Seniors Centre Coordinator | Manager Human Services and Seniors Centre Coordinator | Planning stage |
|  |  ensure location for community events is convenient to older people in their neighbourhoods, with affordable, flexible transportation. | 2010 | Existing | Manager Community Services in conjunction with Manager Human Services | Planning stage |
|  |  Provide older people with the option of participating with a friend or caregiver | 2010 | Included in role of Seniors Centre Coordinator | Manager Human Services and Seniors Centre Coordinator | Planning stage |
|  |  Times of events are convenient for older people during the day | 2009 | Included in role of Seniors Centre Coordinator | Manager Human Services and Seniors Centre Coordinator | Seniors Coordinator appointed Dec 2008 will progress once Seniors Centre is operational in July 2009. |
|  |  Admission to an event is open (e.g. no membership required) and admission, such as ticket purchasing, is a quick, one-stop process that does not require older people to queue for a long time. | 2009 | Included in role of Seniors Centre Coordinator | Manager Human Services and Seniors Centre Coordinator | Seniors Coordinator appointed Dec 2008 will progress once Seniors Centre is operational in July 2009. |

Respect and social inclusion

#### Older people report experiencing conflicting types of behavior and attitudes towards them. On the one hand, many feel they are often respected, recognized and included, while on the other, they experience lack of consideration in the community, in services and in the family. This clash is explained in terms of a changing society and behavioral norms, lack of contact between generations, and widespread ignorance about ageing and older people. The respect and social inclusion of older people depend on more than societal change: factors such as culture, gender, health status and economic status play a large role. The extent to which older people participate in the social, civic and economic life of the city is also closely linked to their experience of inclusion.  						Global Age Friendly Cities

Many people in the original consultation identified isolation and  loneliness as key issues. This was also identified as a concern on the Seniors Community Actioin Plan 2005

## Respect and social inclusion

Outcome: that the ageing population in the City of Cockburn are recognized and included as valuable members in the social, civic and economic life of the city.

| Strategy | Tasks | Time frame | Cost | Responsibility | Status |
| --- | --- | --- | --- | --- | --- |
| To develop a media strategy that positively reflects the diversity of the ageing population | • To include a variety of positive images of older people that supports the diversity of the ageing population. | Ongoing | Ongoing budgets, as appropriate. | Seniors Centre Coordinator, in conjunction with Communication Manager | Planning stage |
|  | • Employ images of relevant age groups to support advertising for community events. | Ongoing | Ongoing budgets, as appropriate. | Seniors Centre Coordinator, in conjunction with Communication Manager | Commenced |
| To continue to encourage and develop programs and community activities that support intergenerational and family interactions | • Plan intergenerational programs through schools and early intervention | Ongoing | Ongoing Budgets, as appropriate | Seniors Centre coordinator, in conjunction with Early Childhood Services and Youth Services Manager | Seniors Coordinator appointed Dec 2008 |
|  | • Access funding to support intergenerational programs. Encourage events including grandparent days. | 2011 | Grant funding if accessible | Seniors Centre coordinator, in conjunction with Early Childhood Services and Youth Services Manager | Seniors Coordinator appointed Dec 2008 will investigate funding options |
| To support community education by providing opportunities for older people to share their knowledge, history and expertise with other generations | • Develop opportunities for the elderly to record their personal history and share experiences with younger generations. | Ongoing | Ongoing Budgets, as appropriate | Manager, Human Services, in conjunction with Manager, Library Services | Oral Histories project as required |

## Civic participation and employment

#### Older people do not stop contributing to their communities on retirement. Many continue to provide unpaid and voluntary work for their families and communities. In some areas, economic circumstances force older people to take paid work long after they should have retired. An age-friendly community provides options for older people to continue to contribute to their communities, through paid employment or voluntary work if they so choose, and to be engaged in the political process.

#### They would also like to see more efforts made to encourage civic participation and feel there are barriers to participation, including physical barriers and cultural stigmatization, surrounding participation by older people.

#### Global Age Friendly Cities

Consultation and continuous improvement are core themes of the Best Value Victoria Principles legislation that has recently been introduced in all Victorian local governments.  Think tank and focus group feedback highlighted the need for more opportunities to consult with seniors.   Processes such as regular surveys, think tanks and utilizing a Seniors Advisory Group will help City of Cockburn connect with this increasingly significant group of people and provide ongoing opportunities for seniors to contribute to the governance of their municipality.

Ongoing learning for seniors is vital to their wellbeing and connection to the community.  This recommendation builds on the Government’s Active Ageing Strategy and The State Aged Care Plan for Western Australia 2003-2008 (WA Aged Care Advisory Council).  Both plans have place high priority on ‘employment and learning and supporting professional development, education and training of the senior population.’

## Civic participation and employment

Outcome: That the ageing population in the City of Cockburn has access to opportunities to continue to contribute to their communities, through paid employment or voluntary work if they so choose, and to be engaged in the political process.

## Civic participation and employment

| Strategy | Tasks | Time frame | Cost | Responsibility | Status |
| --- | --- | --- | --- | --- | --- |
| To establish regular consultation that increases senior participation in decision making including the Regional Seniors Group and other relevant groups | • Undertake regular surveys and consultation opportunities undertake regular surveys and consultation opportunities | Ongoing | Included in role of Seniors Centre Coordinator | Community Development Coordinator in conjunction with Manager, Human services | Seniors Coordinator appointed Dec 2008 will undertake regular consultation through seniors centre, Regional Seniors Group |
|  | • Facilitate a Seniors think tank to include families and Carers. | 2012 | Included in role of Seniors Centre Coordinator | Manager Human Services and Seniors Centre Coordinator | Planning stage |
|  | • Invite seniors to partake in their local Resident Action Group; | ongoing | Included in role of Seniors Centre Coordinator | Manager Human Services and Seniors Centre Coordinator | Commenced |
|  | • Establish a rotating Seniors Advisory Group | ongoing | Included in role of Seniors Centre Coordinator | Manager Human Services and Seniors Centre Coordinator | Commenced |
| To continue to support and encourage participation in the City of Cockburn’s Volunteer Resource Centre. | • Support expos, workshops and seminars that build seniors’ capacity and knowledge (e.g. retirement planning)Support expos, workshops and seminars that build seniors’ capacity and knowledge (e.g. retirement planning) | Ongoing | Ongoing Budget, as appropriate | Seniors centre Coordinator | Seniors Coordinator appointed Dec 2008 will progress once Seniors Centre is operational in July 2009. |
|  | • Develop continuing learning opportunities | Ongoing | Ongoing Budget, as appropriate | Seniors centre Coordinator | Seniors Coordinator appointed Dec 2008 will progress once Seniors Centre is operational in July 2009. |
| To continue to support and facilitate flexible employment opportunities for seniors within the City of Cockburn | • Develop policies and procedures to support flexible working conditions, Develop a strategy for phased retirement. | Ongoing | Included in staff budgets | Manager, Human Services in conjunction with Manager, Human Resources | commenced |
|  | • Support staff involvement with retirement planning | Ongoing | Included in staff budgets | Manager, Human Services in conjunction with Manager, Human Resources | Commenced |

## Communication and Information

#### Staying connected with events and people and getting timely, practical information to manage life and meet personal needs is vital for active ageing. Rapidly evolving information and communication technologies are both welcomed as useful tools and criticized as instruments of social exclusion. Regardless of the variety of communication choices and the volume of information available, the central concern expressed is to have relevant information that is readily accessible to older people with varying capacities and resources. 						Global Age Friendly Cities

Strong responses were received from participants regarding the need for a central person to provide a ‘one stop shop’ for information.  This would address the ad hoc nature of information available to seniors and provide a valuable service to all groups including the active, frail, CALD, indigenous & Torres Strait Islanders.  This officer would also play a key role in strengthening cross-functional activity across council departments to solve issue relating to seniors.

Participants expressed concerns regarding:

Loneliness and isolation

Lack of information about relevant services and events

Lack of awareness of resources and available help

Poor coordination and dissemination

Limited skills and knowledge to be fully prepared for retirement

## Communication and information

Outcome: That relevant information is readily accessible to older people with varying capacities and resources

| Strategy | Tasks | Time frame | Cost | Responsibility | Status |
| --- | --- | --- | --- | --- | --- |
| To provide information in appropriate and accessible formats to all seniors regarding current issues, services and events. | • Develop a booklet on services for seniors and information on senior events to support interim seniors centre and existing programs Design to be managed internally | 2010 | $600 (for 2,000 copies) | Seniors Centre Coordinator in conjunction with Communications Manager | Seniors Coordinator appointed Dec 2008 will investigate funding options |
|  | • Create on City’s website under Human Services, Seniors Centre – webpage to upload events, photos activities etc. | 2009/10 | Included in role of Seniors Centre Coordinator | Manager, Human Services and Seniors Centre Coordinator | Seniors Coordinator appointed Dec 2008. In planning stage |
|  | • Recommendation to be adopted 2010/11 Budget for 2 Seniors Ball evenings increased from 1 per annum. | 2008 | $6,000 | Manager, Human Services | 2 seniors balls commenced 2008 |
| To provide opportunities for seniors to participate in the use of new information technology. | • Support provision of computer and technology courses in accessible environments | 2009/10 | Included in role of Seniors Centre Coordinator | Manager Human Services and Seniors Centre Coordinator | Seniors Coordinator appointed Dec 2008 will progress once Seniors Centre is operational in July 2009. |
|  | • Establish links to Distance Learning, TAFE and University of Third Age |  |  | Manager Human Services and Seniors Centre Coordinator | Seniors Coordinator appointed Dec 2008 will progress once Seniors Centre is operational in July 2009. |
| To facilitate programs to prepare and support seniors approaching retirement. | • Facilitate programs that support seniors approaching retirement | 2009/10 | Included in role of Seniors Centre Coordinator | Manager Human Services and Seniors Centre Coordinator | Seniors Coordinator appointed Dec 2008 will progress once Seniors Centre is operational in July 2009. |
|  | • Assist in the development of information packs and workshops on planning for retirement | 2010 | Grant funds | Manager Human Services and Seniors Centre Coordinator | Seniors Coordinator appointed Dec 2008 will progress once Seniors Centre is operational in July 2009. |
|  | • Provide information to help reduce the impact of grief, loss and depression both from a financial and emotional perspective | 2011 | Existing | Manager Human Services and Seniors Centre Coordinator | Seniors Coordinator appointed Dec 2008 will progress once Seniors Centre is operational in July 2009. |
|  | • Facilitate and coordinate a Retirement or Seniors Expo Day. | 2010/11 | Budget as appropriate | Manager Human Services and Seniors Centre Coordinator | Seniors Coordinator appointed Dec 2008 will progress once Seniors Centre is operational in July 2009. |

## Community and health services

#### Health and support services are vital to maintaining health and independence in the community. Public decision-makers and the private and voluntary sectors at the city level do have an influence on the number, range and location of services and on other aspects of the accessibility of facilities and services. Local service authorities also provide staff training and set service performance standards. Civil society plays a role in providing financial support and voluntary work. Access to health care as well as to a range of health services that are not strictly medical are major themes.

#### Global Age Friendly Cities

Cockburn’s consultation findings consistently highlighted the need for more home support services reflecting the nation’s shortfall in HACC funded services combined with an increase in demand.  Respondents indicated there weren’t enough home support services to remain at home and highlighted a shortage of respite and transport services for non-eligible and eligible HACC funded clients.

Seniors who are healthy/poor or unhealthy/asset rich are not eligible for HACC services and consequently can’t afford home support, respite or transport services delivered by private providers. This greatly affects their ability to function independently and to remain living in their own home.  In the long term by providing support to ‘age in place’ so seniors can remain in their own home should lessen the demand for high and low residential care.

The consultation findings also highlighted a lack of access to appropriate and affordable medical services.  The findings revealed a lack of -: (1) GP’s who are willing to make visits in the home, nursing homes or hostels and (2) affordable medical services such as podiatry, physiotherapy and psychological counseling

## Community and health services

Outcome: That the ageing population in the City of Cockburn has access to affordable quality community support services and health care.

| Strategy | Tasks | Time frame | Cost | Responsibility | Status |
| --- | --- | --- | --- | --- | --- |
| To investigate and support affordable home based services for all seniors | • Support Program Development Grants for organizations and individuals to establish pilot programs which are innovative and meet the needs of seniors in different and creative ways. These grants would form the basis of establishing need for future applications for government funding (Ref: City of Melville) | Ongoing | Grant Funds to be accessed, where available | Manager, Human Services in conjunction with Aged and Disabled Services Manager | Commenced |
| To investigate the need for additional home based services not currently provided by HAAC or CACP | • Identify any unmet need in this area and develop a model of service delivery to meet the unmet need if necessary | 2009/10 | Grant Funds to be accessed, where available | Manager, Human Services in conjunction with Aged and Disabled Services Manager | Planning Stage |
| To continue to support existing services such as HACC , CACP, Safer City, and Mobile Library Service, and ensure relevant standards and accreditation requirements are met. | • Provide ongoing training relevant to service delivery continue quality assurance planning and implementation. | Ongoing | Included in Grant Funded Program Budgets | Manager, Human Services in conjunction with Aged and Disabled Services Manager, Safer City Coordinator, Library Services Manager | commenced |
|  | • Access growth funding | Ongoing | Included in Grant Funded Program Budgets | Manager, Human Services in conjunction with Aged and Disabled Services Manager | Successful Application to HACC and growth funds received 2008/2009 |
|  | • Develop strategies to ensure the continuation of the highly regarded mobile library service, and Safer Seniors Service | Ongoing | Existing Budget | Manager, Human Services in conjunction with Manager Library Services and Safer City Coordinator | Commenced |
| To support outreach health services that improve access to affordable medical services | • Consult with Fremantle Division of General Practice and other stakeholder groups to increase availability of General Practitioners | 2010 | Included in Grant Funded Program Budgets | Manager Human Services in conjunction with Aged and Disabled Services Manager | Planning stage |
|  | • Source Health Department Funding to help provide subsidized Podiatry Services within the interim senior’s Centre and future seniors facilities. | 2009 | Included in role of Seniors Centre Coordinator | Manager Human Services and Seniors Centre Coordinator | Seniors Coordinator appointed Dec 2008 will progress once Seniors Centre is operational in July 2009. |
| To provide a Seniors Officer to coordinate and facilitate services and information across the organization | Provide a central contact person, a Seniors Centre Coordinator responsible for : | Senior’s Centre Coordinator July 2008 | Senior’s centre coordinator employed - ( I FTE) December 2008 | Manager Human Services | Seniors Coordinator appointed Dec 2008 |
|  |  informing/advising seniors on current services, regular events and senior issue |  |  |  | commenced |
|  |  promoting Council services for seniors |  |  |  | commenced |
|  |  facilitating and overseeing learning opportunities |  |  |  | commenced |
|  |  coordinating resources |  |  |  | commenced |
|  |  facilitating ongoing consultation with seniors |  |  |  | commenced |
|  |  overseeing Senior Advisory Group |  |  |  | commenced |
|  |  providing information and feedback on senior issues |  |  |  | commenced |