## Housing
Priority Domain: HOUSING
Goal Promote and expand programs that support affordable property maintenance and home repair | [7 empty] | Metrics: Tracking and Monitoring Progress
Collaborating Organizations Bergen Volunteer Center (Chore Service); Rebuilding Together; Habitat for Humanity; Jewish Home/Safely@Home; Habitat for Humanity; AARP (passive); Bergen County Community Action; Center for Food Action; PSEG; Women's Rights Information Center; Englewood Construction Code Compliance; Planning Board; City Council; Mayor; Englewood Tax Office | [8 empty] | Older Adult residents are involved in the Housing Work Group and in planing the mini-conference on May 25. Many were involved in focus groups and continue to particpate in monthly meetings and via one-on-one conversations with coalition partners.
Activities (what needs to be done) | By Whom (who will supervise this activity and serve on the team?) | Timeframe | Resources and Support (financial, human, political, larger community-wide systems) |  | Potential Barriers or Resistance (and approaches to address these) | Communication Plan for Implementation (how to distribute info and who should receive) | Metrics: Tracking & Monitoring Progress (who, what, when, and how will data be collected?) | Progress as of 2/1/2017 | Progress as of 4/30/2017 | Progress as of 9/30/2017 | Progress as of 3/25/18 | Progress as of 7/27/2018 | Plan for Year 3
|  |  | Available | Needed
Offer programs on simple modifications for safer homes | Coordinator will supervise; Chore, Karen Topjian CAPS*, Fall Prevention specialist | 3rd Quarter | Human resources; small honoraria for presenters | none | Attracting participants; will be addressed through broad-based PR and outreach through Coalition. | PR to precede each presentation in newspapers and social media; publicize through Coalition partners and specific locations (library, senior residence, churches, synagogues) | Numbers of media impressions; numbers of attendees at each. Coordinator, Partners, Support staff | 2 programs planned- 1 on fire safety in the home and another on downsizing/resizing | Fire safety program in Jan. Planning "Housing Options" mini-conference on May 25 to address needs of low-income homeowners | "Housing Options" mini-conference presented on May 25. 140 registered; 110 attended (bad weather). Very successful per evaluations | Info included in Senior Directory published in March 2018 |  | Plan to do "fall prevention" and "home repair" workshops in Yr 3
Provide checklist to encourage preventative home maintenance | Coordinator & support staff; Chore director; K. Topjian | ongoing | AARP HomeFit Guide and smaller pamphlet are readily available | Printed copies of Guide and pamphlet | None | PR to announce availability; Distribute through coalition partners; downloadable on website | Track media impressions and click through to order guide online. Numbers distributed through Library and Coalition Partners. Coordinator, Partners, Support staff | Checklist is being distributed electronically via partners, website and e-newsletter | Link provided in e-newsletlter in Jan, Feb, March | Link distributed at 5/25 conference and provided in follow-up e-newsletter | Included in Senior Directory published in March 2018 |  | Publicize in Media/Social Media in Yr 3
Promote low-cost services that provide home repairs | Coordinator & support Staff; Chore; Rebuilding Together; Habitat; Jewish Home/Safely@Home | ongoing | Chore volunteers; Rebuilding Together; Habitat for Humanity; Safely@Home | Cooperation of listed service providers | Scheduling constraints of service providers | PR to announce availability of services through newspapers and social media; outreach through Coalition Partners | Numbers of service requests from and/or service calls provided for Englewood residents. Service providers | CHORE gave presentation on Feb.1 - 25 attendees; we will attempt to track requests for services from Englewood | Chore is part of 5/25 conference | Chore ppresented at 5/25 conference and promoted in follow-up e-newsletter | Promoted in Senior Directory |  | Publicize in Media/Social Media in Yr 3
Promote Alternative Housing / Shared Housing | Coalition Workgroup on Housing | ongoing | WRIC has existing program; info about/models of alternative forms is available | More homes; more clients for referral | Clarification of zoning laws and compliance with construction code | Inform community of options: shared housing, tiny houses, granny flats, etc | Additional homes available for sharing. Perceived interest in alternative housing via survey.Women's Rights Info Center and HousingWorkgroup;Coordinator | Exploring this actively; have discussed with Construction Code official and City's attorney (Michael Kates) | Shared Housing is part of 5/25 conference | Presented at 5/25 conference and promoted in follow-up e-newsletter | Attended meeting convened by Taub about this service. Working with Women's Rights Info Center to promote more shared housing |  | Promoting housing alternatives - co-housing, shared housing, etc.
Advocate for low-income senior housing | Housing Workgroup, Coalition Coordinator, Coalition partners; interested and engaged older adults | ongoing | Additional senior housing is mentioned in City's Master Plan 2014 | Build interest among City Council and Planning Board | Properties are available; City is planning conversion; little interest in low-market-ratables. | Continual interaction at Council and Planning Board meetings; work with City Planner & NJ Futures | # older adults engaged in advocacy on this topic. Track activities of advocates. Track meetings where topic is discussed with City officials and advocates. Coordinator and Workgroup representative | Am advocating for this with Mayor and City Council. There is a big divide on this; the mayor is in favor but a very vocal council member is not.l | Attending City Council meetings to advocate for inclusion of senior housing in Liberty School redevelopment. Unlikely low-income will be included but we will advocate. | Attended 5 City Council & Planning Board meetings to advocate for senior housing | Attended several council meetings and private gatherings to discuss future of Liberty School | Continuing to advocate re senior housing an services in a refurbished Liberty School. Attended 2 City Council meetings since March | Continuing to advocate re Liberty School
Educate older adults about property tax freeze and tax relief & reverse mortgage | Coalition Coordinator & support staff | 3rd Quarter | Information is available | Information needs to be distributed broadly and persistently | Reaching those eligible for relief (address through outreach & PR) | PR through local media and Coalition Partners | May be difficult to track through City Tax Office, but we will try. Coordinator | Have reached out to tax collector to set up a means to inform residents of tax freeze & relief for older residents | Tax rebate, freeze & reductions are included in the 5/25 conference | Tax official presented at 5/25 conference; information distributed at conference and in follow-up e-newsletltelr | Info included in Senior Directory published in March 2018 |  | Continue to promote in Yr. 3
Promote social benefit programs that provide assistance for housing costs and utilities for older adults unable to meet their basic needs | Coalition partners; Coordinator & support staff | ongoing | Consult with providers of reduced cost services (CFA; PSEG; BCCA) | Research additional reduced cost services | None | PR through Coalition partners and local/online media | Numbers of click-through on social media. Hard to track through PSEG but BCCA and CFA can track referrals from Englewood seniors. Coordinator, Service providers, Support staff | Sent info about PSEG programs to Coalition partners. Will post on Facebook and Website and track clicks. | Information to be presented and/or distributed at 5/25 conference | Information distributed in packet at 5/25 conference. | Info included in Senior Directory published in March 2018 |  | Continue to promote in Yr. 3
Create resource list for homeowners | Coordinator & support staff | Third Quarter | Consult with contractors & Construction Code Manager | Cooperation of contractors & references | Resistance of references to refer contractors | PR to announce availability of checklist through newspaper and social media | Numbers of requests for checklist; brochures distributed through Coalition partners; click through on social media. Coordinator, Partners, Support staff | This was not started in Year 1 but may be attempted in year 2 |  | Home Safety checklist distributed at meetings and in e-newsletter twice. | Home Safety checklist included in Senior Directory. | Researching promoting Angie's List or HomeAdvisor.com | May/May not promote vetted online home repair services, depending on research
Research online resource reviwers (Angie's List and others) for relevlance to our program. | Support staff & Coordinator | Ongoing | Online plaltforms that review home repair services & contractors | Research | Don't want to endorse any particular vendors due to liability | PR through coalition partners and local/online media | We will disseminate information; difficult to track. |  |  |  | Research to be done this grant year. | Not done | Not Continuing in yr 3

## Outdoor Spaces & BUildings
Priority Domain: OUTDOOR SPACES & BUILDING
Goal: Advocate for improved public amenities
Collaborating Organizations: Mayor; Englewood Department of Public Works; City Engineer; Volunteer sidewalk & street assessors; Coalition Partners | [8 empty] | Older Adult residents are involved in the Coalition and provide input through focus groups and ongoing conversations.
Activities (what needs to be done) | By Whom (who will supervise this activity and serve on the team?) | Timeframe (important dates for completion of steps) | Resources and Support (financial, human, political, larger community-wide systems) |  | Potential Barriers or Resistance (and approaches to address these) | Communication Plan for Implementation (how to distribute info and who should receive) | Metrics: Tracking & Monitoring Progress (who, what, when, and how will data be collected?) | Progress as of 2/1/2017 | Progress as of 4/30/2017 | Progress as of 9/30/2017 | Progress as of 3/25/18 | Progress as of 7/27/2018 | Plan for Year 3
|  |  | Available | Needed
Advocate for audit of existing parks for benches, restrooms, cleanliness, maintenance and identify "quick fixes" | Coordinator; City Engineer; DPW; volunteers | 1st qtr - ongoing | City planning materials | Grant funding for audit | City may not recognize need.(Share data from surveys & focus groups plus input from Coalition partners; be persistent.) | Interaction with city officials; recruit & train volunteers through schools and media | Track # of improvements needed, # of improvements completed. Coordinator, volunteers, DPW staff |  | City claims to be doing this; we will keep in contact with the DPW and City Engineer to find out. | City has included this in Master Plan. We remind them regularly and send links to grants for which municipalities are eligible. | Continue to remind City Engineer and Council of elements in Master Plan | Continue to remind City Engineer and Council of elements in Master Plan | Follow up with reminders Yr3
Advocate for audit of sidewalks and crossings to recommend needed improvements, especially in residential areas | Coordinator; City Engineer; DPW; volunteers | 1st qtr - ongoing | City planning materials | Grant funding for audit |  | Recruit volunteers through schools and media; manage volunteer assignments | Track assessments completed; volunteers, coordinator (if needed) | Have forwarded info about available grant to City Engineer and City manager |  | City has included this in Master Plan. We remind them regularly and send links to grants for which municipalities are eligible. Will work with Civic Eye to conduct walkability study in next grant year. | Preliminairy meeting re Walkability Study set for April 4. Study to be conducted with community members in May. | Walkability study conducted May 24; awaiting report from WEB consulting. | Distribute report to appropriate City leaders and agencies. Follow up recommendations in report
Advocate for benches for resting to promote walkability | Coordinator, City Engineer, older adults, coalition partners, Rotary |  | Residents walk around neighborhoods to identify locations for benches | City and Special Improvement District have funds to install benches | This project depends on City to install benches. We can't foresee how this will fall in their DPW/construction priorities | Residents specify locations for benches. Information passed along to SID and City Engineer. Project promoted in local press and social media. | Track number of new benches installed in Englewood |  |  |  |  | Assessing for City Englneer and Special Improvement District Board where benches are needed for resting; will pass along to him | Will track progress and prod City to follow up and install benches
Coordinate a Walking Tour of Central Business District to promote walkability | Coordinator, Historical Society, Chamber of Commerce, SID |  | Historical Society and older residents have relevant information | Maps will be provided for "walkers" | None foreseen | Promote via blast emails and newspaper publicity | Number of residents who participate |  |  |  |  | Laying the groundwork for a walking tour with the Historical Society and Chamber as well as local residents who did this years ago. | Will conduct Walking Tour in Fall 2018
Encourage Complete Streets with separate bike/Pedestrian walkways | Coordinator advocate with City Engineer;Mayor; City Manager, City Council | 3rd qtr ongoing | Info about Complete Streets; City planning materials |  |  | Interaction with Mayor, Council, City Engineer | Number of direct interactions on this topic | City is in the process of re-developing major intersections with curb bumpouts and countdown stoplights. I've talked with Police Chief, City Engineer, City Manager and Mayor about this project and some issues residents have | City is continuing to develop curb bumpouts, timed crossing lights and better marked pedestrial crosswalks on major thoroughfares in Englewood. We are advocating publicly for approval of Light Rail expansion. | City is continuing to develop curb bumpouts, timed crossing lights and better marked pedestrian crosswalks on major thoroughfares in Englewood. We continue to advocate publicly for approval of Light Rail expansion. Streeets advocacy for now. | City continues to improve crossings. We continue to monitor. Attempting to consult with newly-appointed Business Development Special Improvement District (SID) on aspects that will improve livability. | Provided City Engineer with Complete Streets Manual from State of NJ. Consulting with newly-appointed Business Development Special Improvement District (SID) on age-friendly elements in 2014 Master Plan | Continue in Yr 3
New Ideas
Explore development of an Older Adult Playground | County Parks Dept., Corporate sponsors & volunteers, Coalition Partners, KaBOOM (builds playgrounds) | ongoing | Space available in Overpeck or other County Park; interest of Freeholder Tracey Zur; Coalition partners and other Age-Friendly Communities in Bergen County. | Funding, support of utilities (heavy equipment), corporate and community volunteers | Politics may be involved with County parks; funding tight at County level; will work all angles since older adults are a fast growing segment of the County population | Broad PR to generate interest, raise funds and recruit volunteers; also progress on building project and building day | Funds raised; volunteers involved; corporate and funding partners involved. |  | April 2017 - idea presented to Freeholder Chair Tracey Zur, who is very interested (depending on cost and logistics). | Met with Freeholder Chair Tracey Zur on 6/12/17 to present idea of Senior Playground. This idea fits in with County's Master Plan for Parks which is currently under development. G. Viggiano of Rebuilding Together joined me at meeting. Follow up in Sept. | We are continuing to advocate and follow up with Freeholder Zur. Master Plan for County Parks is still in development. | We are continuing to advocate and follow up with Freeholder Zur. Master Plan for County Parks is still in development. | Continuing to follow development of B.C. Parks Master Plan and advocate for "Granny Playground"
Explore and impement civic arts projects in downtown Englewood | Mayor/Council, Chamber, Special Improvement District (SID), artists, project manager, | Summer-Fall 2018 | Local & NYC artists, certified Project Manager, Mayor & Council, City Engineer, Building Owners | Permissions from building owners, artists' desigins, matching funds from SID | Denial of permission, lack of funding to complete | Local and Social Media | Artists enlisted; project plan developed and implemented, arts projects completed on time and in budget |  |  |  |  | Exploring concepts; interviewing artists; seeking funding apart from Taub grant. Have approval from Council to proceed in painting Utiity Boxes. Exploring possiblity of painting large murals, too. | Idea grew out of AARP Community Challenge grant (not received); All players are keen to proceed.

## Transportation
PRIORITY DOMAIN: TRANSPORTATION
GOAL Improve/Enhance network of transportation options to increase mobility of older adults and provide access to a broad range of activities
Collaborating Organizations NJ Transit, B.C. Community Transportation; EZ-Ride; Independent Travel Network (ITN), Englewood Economic Development Corp.; Mayor/Council/City Manager; Uber/Lyft; GoGoGrantparent; SESCIL, JCC, Flat Rock Brook; Actors' Fund Home, Board of Education (buses), Dwight-Englewood School, Houses of Worship (buses); AAA, Jewish Home at Home, AARP | [7 empty] | ITEMS in GRAY box will not be continued either because they are unfeasiible or have morphed into something else. | Older adult residents are involved in focus groups and ongoing discussions about Transportation, especially regarding Light Rail and transportation to-and-from transit "hubs" in Englewood.
Activities (what needs to be done) | By Whom (who will supervise this activity and serve on the team?) | Timeframe (important dates for completion of steps) | Resources and Support (financial, human, political, larger community-wide systems) |  | Potential Barriers or Resistance (and approaches to address these) | Communication Plan for Implementation (how to distribute info and who should receive) | Metrics: Tracking & Monitoring Progress (who, what, when, and how will data be collected?) | Progress as of Feb 1, 2017 | Progress as of 4/30/2017 | Progress as of 9/30/2017 | Progress as of 3/25/18 | Progress as of 7/27/2018 | Plan for Year 3
|  |  | Available | Needed
Provide education about available public transportation
Promote information about transportaton options: NJ Transit/AccessLink/EZ-Ride/Community Transportation/ NJ Find a ride/GoGo Grandparent/ITN | Transportation providers; Coordinator, Support staff | ongoing | All services have materials available | none | none | Provide info about various transporation options via e-Newsletter, website and press releases as necessary. | Try to assess with providers uptick in service from Englewood residents. Coodinator, Support Staff | Support staff member attended NJTIPS workshop, but she left for another job. Talked to Nieves about this on 2/1/17 | Providing links and boxes of info on our website and Facebook ads to promote transportation services | Hosted Transportation Options mini-conference on 9/28/17 with presenters on these topics | Information and Transportation Chart included in Directory published in March 2018 | Referred numerous individuals and agencies to Chart included in Directory published in March 2018 | Continue to add to and promote Transportation Chart
Promote availability of vouchers for ITN and GoGoGrandparent, using model from TriTown55Plus. | ITN, GoGoGrandparent, Coordinator | 1st qtr ongoing | Idea to be presented at Transportation Options conference in Sept. 2017 | Interest in plan;mechanism for distribution and tracking | Lack of interest in transportation vouchers; glitch in setting up mechanism with ITN and/or GoGoGrandparent | Provide information about availability of vouchers to broad-based media: City communications, AF website, e-news, press releases, direct email. | Track vouchers through GoGoGrandparent & ITN. Survey riders for satisfaction. Coordinator, Support Staff. |  |  | Will explore provision of vouchers for ITN and/or GoGoGrandparent in the next grant year. | Continuing to explore vouchers for ITN and/or GoGoGrandparent this Spring
Promote & Expand volunteer driver program - ITN | ITN and Transportation Workgroup | 1st qtr ongoing | ITN program is in place | more volunteers; more clients in Englewood | Difficulty in recruiting volunteers due to resistance to driving others (ITN will ramp up its recruitment efforts) | Extensive local publicity in newspapers, houses of worship and on social media to recruit volunteers. | Number of volunteer drivers recruited and trained; number of clients in Englewood registered for ITN. ITN will gather data. | Have consulted with Mary Lions Kim about reaching out to Englewood area through specific media. Am including promo in Feb. '17 e-news | Promoting iTN on our Website | Promoted ITN in July e-newsletter. Included as presentation and handout at 9/30 Conference. | Included in Senior Directory in listings and in Transportation Chart. Helped promote volunteer recruitment efforts. | Sent 2 blast emails and included 2 promotions for Volunteer Center's "Redefining Retirement" since April 1 | Continue to promote need for volunteer drivers
Explore alternative transportation Services
Explore provision of vouchers for taxi/Uber/Lyft | Englewood Economic Development Corp.; Mayor; Coordinator; Transportation Workgroup | 1st qtr-ongoing | Models of this program exist in other towns (Ridgewood) | Interest in program and funding to support it | Lack of funding and/or interest in providing this program (We will advocate strongly with city and/or seek alternative grant funding) | Outreach to Economic Development and Mayor. If program is established, broad communication to older adult residents of Englewood | Track enrollment in voucher program, number of vouchers distributed & rides provided. Economic Development (if agreeable) | Have had initial conversation with CofC and City Manager. Might consider if AFE provides funding for pilot program. | No interest at this time due to City budget. Also, City Manager resigned to take another position so that post is empty right now. | Looking into adopting TriTown55+'s model of providing vouchers for GoGoGrandparent | Continuing to explore vouchers for ITN and/or GoGoGrandparent this Spring | Not considering vouchers
Explore GoGoGrandparent | Coordinator; Transportation Workgroup; Coalition Partners | 1st qtr | Program is available | Information | Resistance to technology on the part of some older adults | Promote availability of program through houses of worship, senior residence, local papers and social media. Demonstration workshops and video. | Number of individuals signed up for program (if able to get from GoGoGrandparent) | To be explored at AFCI meeting on Feb. 2. Will include info in Feb 3-news. | Promting GoGoGrandparent on our Website | See above - may adopt TriTown55+ model in Englewood |  | Have referred 10 older adult residents to GoGo Grandparent and Ryde4Life. | Continue to prmote GoGoGrandparent and Ryde4Life.
Explore using buses from organization in town during off-peak hours | Actors' Fund Home; Board of Education; Dwight-Englewood School; Houses of worship; Coordinator, Support staff | 1st qtr | Buses are available at organizations in town | Willingness to let their drivers & buses be used to help seniors in town | Scheduling, lack of drivers or drivers assigned to other tasks when not bussing. | Develop schedule of rides with specific organizations: houses of worship, senior residences, apartment complexes, etc. | Number of rides provided/clients served. Organizations recruiting clients for rides. | Haved talked to Actors Fund home about this; need to finalize and plan for who would coordinate rides. | Actors Fund Home in major re-construction; no action on this at this time. | Still looking into this. Actors Fund Home in major construction now; implementation of bus-sharing on hold. | Waiting for Actors Fund Home major construction project to finish. Concept still on hold. | Actors Fund construction complete; now exploring this again | Hope to institute this in Year 3
NEW Explore provision of "senior bus" in Englewood to get residents to programs, events and doctors. | Coordinator, Bergen Family Center, other providers, City Manager |  | Research other towns use, costs, funding | Interest among seniors and agencies that need to get clients to programs | Difficulty in securing sustainable funding for a senior bus service | Publicize campaign to secure funds; publicize opportunity for transportation if/when operation begins. | Track number of riders and rides. | [5 empty] | Work with City to explore possiblity of senior bus.
Explore ride matching and/or ride-sharing to transport older adults to activities | Coordinator and Support staff reaching out to SESCIL, JCC, Flat Rock Brook, etc. | 3rd qtr | Organizations exist; will need to be reached out to. | Interest in concept and willingness to match those who drive with those who need rides | Organizations may be resistant to adding to their work by matching their clients for rides to their programs. | Personal interaction with providers of programs to which transportation is needed; outreach to prospective clients through local papers and direct interaction. | Number of rides arranged/clients provided rides to activity programs. Program Providers; Coordinator; Support staff. |  |  | According to contacts at local nonprofits, most clients to not share rides. The only place where this occurs is 111 West street. This research will not be continued. | Not feasible.
Improve the safety of older adult drivers
Promote availability of driver safety education and competency programs | AARP’s driver transition course; AAA; Jewish Home at Home program | 3rd qtr | Programs are available | Funding needed for those unable to pay | Recognition by driver that it may be time to assess competence | Outreach through local newspapers and social media | Track through provider of education course (if possible); Coordinator, Support staff | SESCIL does this; so does AARP - we will promote their programs in Spring. | Promoting AARP and AAA driver safety programs on our website | Promoting AARP and AAA driver safety programs on our website; also discounts from AARP. Handouts provided at 9/30 conference and links sent to e-mail list | Promoted in Senior Directory published in March 2018 | Promoted 1x in e-newsletter and 2x in Facebook posts | Continue to promote AARP and AAA Driver Safety courses
Future topic:
Explore possibility of insurance companies funding driver certification program | Large auto insurance companies, Coordinator, Support staff | 3rd qtr | Nothing known about such a program to date | Information and funding | No information about feasibility of such a program | Outreach to large auto insurance companies in Northern NJ | Coordinator; Support staff. |  |  | This will not be pursued in Year 2

## Community Sup&Health Services
Priority Domain : COMMUNITY SUPPORT FOR HEALTH SERVICES Goal: Promote & provide access to available health & social services Collaborating Organizations: Department of Health, Englewood Hospital,"Disease" organizations, Coalition Partner organizations providing Health-related and/or fitness activities; Police/Fire/EMS; Houses of Worship. | [7 empty] | ITEMS in GRAY box will not be continued either because they are unfeasiible or have morphed into something else. | Older adults are involved in meetings and conversations about planning all aspects related to health-related resources.
Activities (what needs to be done) | By Whom (who will supervise this activity and serve on the team?) | Timeframe (important dates for completion of steps) | Resources and Support (financial, human, political, larger community-wide systems) |  | Potential Barriers or Resistance (and approaches to address these) | Communication Plan for Implementation (how to distribute info and who should receive) | Metrics: Tracking & Monitoring Progress (who, what, when, and how will data be collected?) | Progress as of Feb 1, 2017 | Progress as of 4/30/2017 | Progress as of 9/30/2017 | Progress as of 3/25/18 | Progress as of 7/27/2018 | Plan for Year 3
|  |  | Available | Needed
Provide health-related informational and vaccination programs | Health Care providers; Coordinator, Support staff | 1st qtr Ongoing | Programs and locations | Scheduling and promotion | Scheduling and attracting participants for each presentation/activity. (Addressed through coordination and broad PR) | Coordinate with service provider to present educational program or vaccinations. Coordinate with locations to host program. Communications plan is outlined in goal area of Communications & Information | Number of participants in each program. Service providers; Coalition Partners hosting programs; Coordinator, Support Staff. | Working with Health Department on this | Helping to promote "Walk With A Doc" at City parks weekly through the Spring. PR and website as well as Facebook ad | Promoted "Walk with a Doc" through May; Yoga and Pilates "in the park" every Wed. and Thurs. throughout the summer | Continuing to promote Dept. of Health programs, especially those targeted for Spring and Summer | Promoted 10 Dept. of Health or Chamber programs re health & fitness in e-newsletter, Facebook posts and blast emails. | Continue to promote Dept. of Health and fitness programs promoted by the Chamber
Topic areas: Flu vaccinations, diabetes testing, rabies vaccination, Hepatitis C testing, info about Alzheimer's/dementia, Heart disease, etc. | [8 empty] | Helping to promote health fair at Englewood Hospital in the fall. | Helping Dept. of Health to promote its programs. | Helping Dept. of Health to promote its programs.
Promote the broad range of accessible and affordable fitness activities | Coordinator; SESCIL, Senior Source, Parks & Recreation, YWCA (Yoga, Senior Splash at Crowne Plaza), Englewood Hospital (Walk with a Doc), Dept. of Health (Walk with a Leader) | 1st qtr Ongoing | Programs and locations | Scheduling and promotion | Scheduling and attracting participants in activities (Addressed through cooperation and broad PR) | Communications plan is outlined in goal area of Communications & Information | Numbers of participants in programs; numbers of media impressions and click-through for registration (when possible). Service providers, Coordinator, Support staff. | Information is posted in monthly e-newsletter | We include calendars of organizations as link on website; include calendar of specific activities in monthly e-newsletter | We include calendars of organizations on our website and in monthely e-newsletter. Specifically promote Yoga in the Park and Pilates in the Park programs throughout the summer. | Promoting in monthly e-newsletter as well as blast emails inbetween. Information about many venues for activities included in Senior Directory published in March 2018 | Promoted fitness activities in monthly e-newsletter, blast emails and Facebook posts. | Continue to promote
Distribute refrigerator magnet with pocket to contain critical personal information to 1,000 older adult residents of Englewood | Police, Fire, EMS; Coalition Partners; houses of worship | 3rd qtr-Ongoing | Interest in providing magnet | Funding to purchase magnets | Lack of funding to start, but we think we can raise funds easily for this. Distribution will be a challenge. (Addressed through cooperation of Coalition partners and City agencies.) | Distribute through Coalition partners, EMS, houses of worship | Numbers of magnets distributed. Coordinator working with distribution point-organizations. | Have distributed 225 File of Life packets to date; have 475 more to distribute with informational card about AFE. | Have distributed an additional 300 File of Life packets with informational card about AFE | Distributed File of Life packets and magnets to attendees of 5/25 Housing Options mini-conference. Have distributed 700 File of Life Magnets & info cards to date. Will not continue in Year 2 unless there is big demand. | Continue to fulfill requests for File of Life. Provided packets to Police and Fire Departments. Will continue to order and distribute as requested by older adult residents of Englewood. | Provided File of Life to 10 residents of Towne Centre apartment complex | Will assess and distribute if needed
Promote existing health-related programs | Health Care providers; "disease" organizations; Coordinator, Support staff | Ongoing | Dept. of Health, Englewood Hospital and disease-related programs and locations | Promotion of existing programs | Being notified so we can promote each presentation/activity. (Addressed through coordination and broad PR) | Keep contact with program providers so we can help promote them. Communications plan is outlined in goal area of Communications & Information | Number of participants in each program. Service providers; Coalition Partners hosting programs; Coordinator, Support Staff. | Promoted programs at at Englewood organizations and JCC through e-newsletter | Continued to promote in e-newsletter | Continue to promote in e-newsletter | Continue to promote in e-newsletter and blast emails. Also included in Senior Directory published in March 2018. | Promoted health-related programs in monthly e-newsletter, Facebook posts and blast emails. Also included in Senior Directory published in March 2018. | Continue to promote existing programs; focus on Medicare/Medicaid enrollment
Topic areas: Flu vaccinations, diabetes testing, rabies vaccination, Hepatitis C testing, info about Alzheimer's/dementia, Heart disease, etc.
Work with Englewood Hospital & Medical Center (EHMC) to help them reach the goals of their Community Health Needs Assessment | Coordinator working with appropriate staff at EMHC | 1st qtr Ongoing | EMHC offers many programs to the community | information about programs so we can help promote and drive up numbers | Lack of response from appropriate staff at EHMC (they have been hard to reach) | Find out about programs and help to promote through AFE communications channels: Website, e-mail, e-News, press releases, etc. | Number of attendees at EHMC community programs. EHMC staff, coordinator. | Contact is on medical leave | Contact on medical leave | This will be pursued vigorously with EHMC in Year 2 | Englewood Hospital has been engaged in intensive internal introspection and informed us that they will be ready to do more community outreach later in 2018. | Hospital's introspection nearly complete; working more closely to assess how we can work together for benefit of community | Work more closely with Englewood Hospital on community programs
New for Year 3
Promote home-care and caregiver support groups | Caregiver support coordinators | ongoing | Existing caregiver support groups at the County, JCC and other organizations | Need to be promoted | Lack of attendance; do more promotion including benefits | Promote in monthly newsletter and through e-mail blasts | Increased participating (track through coordinators) |  |  |  |  | Promoted 6 meetings of caregiver groups through newsletter, Facebook posts and blast e-mails | Continue to promote
Encourage Englewood Hospital to open Urgent Care center in Central Business District | Coordinator; EHMC Planning Dept. | ongoing | EHMC | Plan and funding from EHMC | Lack of plan and funding | We will promote like crazy if/when EHMC opens an Urgent Care center in the Central Business District | If/when Urgent Care center opens |  |  | This idea came from an 83-year-old resident who saw many empty storefronts near her building in the Central Business District and thought at least one should be made into an Urgent Care center. We passed this along to Englewood Hospital for consideration. |  | Talked to Strategic Planning officer at EHMC; interested in idea | Continue to pursue

## Civic Particip & Employment
Priority Domain: CIVIC PARTICIPATION & EMPLOYMENT Goal: Successfully integrate older adult residents of Englewood into the life of the community Collaborating Organizations: Chamber of Commerce, EEDC (Englewood Economic Development Corp.); Mayor/Council/City Manager; Volunteer Center, nonprofit organizations, agencies of City government, Coalition partners, Houses of worship | [7 empty] | ITEMS in GRAY box will not be continued either because they are unfeasiible or have morphed into something else. | Older adults are involved in all aspects of planing for engagement in civic particpation in Englewood.
Activities (what needs to be done) | By Whom (who will supervise this activity and serve on the team?) | Timeframe (important dates for completion of steps) | Resources and Support (financial, human, political, larger community-wide systems) |  | Potential Barriers or Resistance (and approaches to address these) | Communication Plan for Implementation (how to distribute info and who should receive) | Metrics: Tracking & Monitoring Progress (who, what, when, and how will data be collected?) | Progress as of Feb. 2 | Progress as of 4/30/2017 | Progress as of 9/30/2017 | Progress as of 3/25/18 | Progress as of 7/27/2018 | Plan for Year 3
|  |  | Available | Needed
Encourage businesses to adopt age-friendly practices that attract and retain older adults as customers and potential employees
Work with Chamber of Commerce & EEDC (Special Improvement District-SID-as of early 2018)to encourage businesses to adopt AARPs age-friendly practices to help them attract and retain older adults as customers and potential employees | Coordinator, Chamber of Commerce, EEDC | 1st qtr - ongoing | NYC Checklist for businesses | Willingness of CofC and EEDC to help in this effort. Copies of printed checklist. | Reluctance of Chamber and EEDC to promote Age-Friendly Englewood. (we will educate them and enlist their support) | Personal outreach by Coordinator to Chamber of Commerce and EEDC to educate about the value of older adult participation in commerce. Article in business section of paper(s). | # Checklist for Business distributed to businesses in town. C of C, Coordinator, Support staff | Gave presentation to CofC on 1/27 & distributed Checklist for Businesses to 60 attendees | Include Checklist for Businesses on website and Facebook ad | Include Checklist on Website. Paid Facebook ad for Age-Friendly Business Checklist. | Checklist included on Website. Chamber promoted in Senior Directory published in March 2018. Info about Age-Friendly Businesses to be distributed again through Chamber. | Checklist distributed to 50 businesses at Chamber meeting on March 28, 2018 | Work with new SID to continue to promote age-friendly business practices.
Certify Englewood businesses as "age friendly" | Enlist businesses through CofC and EEDC | ongoing | NYC Checklist for businesses; sticker for window | Printed checklist; stickers for windows | Resistance to being designated "age-friendly" (We will educate them through CofC) | Outreach through CofC and EEDC; PR in local newspapers and through social media | # Checklist for Business and Window Stickers distributed to businesses in town. C of C, Coordinator, Support staff |  |  |  |  | New Assistant Coordinator will initiate this late in Yr 2 | Visit businesses and enlist as "age-friendly"
Engage older adults in civic life of the community
Advocate for creation of Advisory Board to evaluate and provide guidance on policies, operations, programs, events and services impacting older adults | Mayor/City Council, City Manager, Coordinator, Coalition Steering Committee | 1st qtr - ongoing | Interest expressed by Mayor | Commitment by Mayor and City Manager to have an Advisory Board | Advisory Board does not exist. (Develop "value proposition" that will entice City Fathers to have an Advisory Board) | Personal outreach to Mayor/Council and City Manager. Then develop plan to appoint Advisory Board members | # of advisory Board members appointed. Coordinator, Support Staff |  | Have approached Mayor on this; City Manager post currently vacant. Consulting with Borough of Tenafly's Senior Citizens Advisory Committee about Age-Friendly initiatives there. | Have continued to present idea of Mayor and Acting City Manager. Continue to consult with Tenafly and with Oradell on age-friendly initiatives in those towns. | Have continued to advocate for Senior Advisory Council with Mayour and City Manager. Continuing to consult with Tenafly and Oradell. Recognized by Tenafly Mayor for assistance to that town. | Continue to advocate with Mayor, City Council and City Manager for Senior Advisory Council. Continuing to consult with Tenafly & Oradell. Recognized on May 23 at Tenafly Senior Center. | Continue to advocate for Senior Advisory Council
Engage older adults in decision-making bodies in public and private sectors | Nonprofit organizations, agencies of city government, houses of worship; Coordinator | 1st qtr - ongoing | Orgs and City agencies exist; many have Boards; Coordinator is experienced in Board development and training. | Willingness of organizations and city agencies to enlist new members of their boards/committees | Some may not have a process in place to engage others. (We will encourage agencies to engage older adults on their Boards and committees) | Outreach through Coalition Partners. Work with City Manager/City agencies to develop advisory boards/committees. Reach out through media to older adults who may wish to participate | # of positions available. # of positions created. #of older adults who indicate interest. # older adults engaged in decision-making bodies. Participating agencies, Coordinator, Support Staff |  | Reaching out to nonprofits to encourage more older adults on Boards (many already have several on their Boards) | Continue to advocate with nonprofit partners to place older adults on their boards. | Continue to advocate with nonprofit partners to place older adults on boards. |  | Continue to advocate with nonprofit partners to place older adults on boards.
Promote volunteer opportunities for older adults to remain engaged in the community | Volunteer Center; Coalition Partner organizations; agencies of City government | 1st qtr-ongoing | Volunteer Center listings | Listings of volunteer opportunities at other organizations; training of volunteers; matching volunteers with vol jobs | Lack of knowledge about volunteer opportunities. Lack of volunteer jobs due to lack of volunteer job creation and supervision. (Volunteer Center to be enlisted to provide training for organizations and prospective volunteers.) | Outreach to organizations and houses of worship to think creatively about volunteers/volunteer jobs. PR to recruit volunteers in newspapers and social media; publicize through Coalition partners and at specific locations (library, senior residence, churches, synagogues) | #volunteer jobs identified; # volunteer jobs created; # volunteers recruited. Organizations that engage volunteers; Coordinator, Support staff | Working with Community Chest & Volunteer Center to develop Volunteer Fair in the Spring | Helping to promote Volunteer Center's "ambassador" program to recruit community-based expert on volunteer opportunities. | Continue to promote Volunteer Center's "ambassador" program. One volunteer from Englewood enlisted to date. | Continue to promote Volunteer Center's "ambassador" program. One volunteer from Englewood enlisted to date. | Promoted Volunteer Center's "Redefining Retirement" Matchmakers in monthly newsletter and e-mail blasts | Continue to promote volunteerism & Volunteer Center
Develop list of volunteer opportunities a) for older adults and b) for those serving older adults in Englewood | Volunteer Center; Coalition Partner organizations; agencies of City government, Coordinator | 3rd qtr ongoing | Some listings available now | Research/develop additional volunteer opportunities | Difficulty in developing volunteer jobs in city government and in organizations that do not yet engage volunteers. (Volunteer Center to be enlisted to provide training for organizations and prospective volunteers.) | Promote volunteering through local newspapers and online resources. Publicize and distribute listings through Coalition Partners and other locations in town. | # volunteer jobs created. # listings distributed. Coalition Partners, Coordinator, Support Staff | Promoting existing volunteer jobs on VC website | Promoting Volunteer Center's website and database as resources to find volunteer positions | Continue to promote actively the Volunteer Center's website and database as resources to find volunteer positions. Will defer to Volunteer Center in Years 2 and 3.
Assure sustainability of Age-Friendly Englewood
Enlist Coalition Partners in ongoing commitment through Memorandum of Understanding (MOU) | Coordinator; Coalition Partners; additional organizations in or serving Englewood | 3rd qtr ongoing | Knowledge of original partners | Ongoing commitment to Age-Friendly Englewood | Resistance to or ambivalence about making a commitment. (Hopefully, success will breed success. Early partners will enlist others to sign MOU) | Personal contact by email and in person | # of MOUs received. # attendance at meetings. # actively participating Partners. Coordinator and support staff | Have drafted MOU & received feedback/approval from Steering Committee, but not distributed yet | Started to brainstorm at Coalition meeting on April 26 about what success will look like. | Continuing to look at "success"; workshop with AFCs in June was helpful. Will continue to pursue in Year 2. | Coalition meetings are used to assess success on an ongoing basis. | We continue to discuss "sustainability" at 6 Coalition meetings in grant year - every-other-month. | Continue in Year 3
New Activity
Continue to consult (as requested) with communities exploring "Age-Friendly" initiatives | Coordinator, representatives of interested communities | ongoing | Interested communities | Time to consult with them | none. If community decides it is not interested, consultation will stop | That is up to the town with whom we are consulting | only name of community and # people participating |  | Consulting frequently with the Senior Citizens Advisory Board in Tenafly since Fall, 2016 | Am now consulting with borough clerk in Oradell on age-friendly matters | Participated in of Age-Friendly presentation to Bergen County Div. of Senior Services in November. |  | Will continue to support/advise other communities in B.C. as opportunities arise.
Promote employment opportunities for older adults | Coordinator, Asst. Coord., SID | ongoing | local businesses; online resources | Willing particpatioin of local businesses and availability of appropriate online resources | Local businesses not hiring | Publicize concept of hiring older adults through SID and Chamber as well as in local & social media | Track through Chamber/SID if possible | [5 empty] | Will launch efforts to a) promote hiring of older adults and b) promote training of older adults for jobs in Year 3.
Apply to join AARP/WHO Age-Friendly Network | Coordinator, Asst. Coord, Mayor, City Council President | 4th qtr-yr 2 | Baseline assesment, work plan, etc | Time to complete application; buy-in from Mayor & Council | Lack of interest among city leaders (but I don't think this will be the case). | Publicize through local & social media | Acceptance by WHO/AARP into the Age-Friendly Network |  |  |  |  | Application to be begun in 4th qtr of Year 2 | Application process may continue into Yr 3.

## Social Participation&Inclusion
Priority Domain: SOCIAL PARTICIPATION & INCLUSION Goal: Promote and ensure access to a range of activities that integrate older adults into the life of the community Collaborating Organizations: Numerous Coalition Partners offering activities, Dept. of Health, DPW, Bergen PAC, Recreation, CofC, EEDC, Houses of Worship; Housing complexes; Providers of Meals on Wheels; High Schools/students; Mayor, City Manager; Police/Fire/EMS; Village to Village Network | [8 empty] | Older adults are involved in all aspects of increasing engagement and communicating about social activites in Englewood.
Activities (what needs to be done) | By Whom (who will supervise this activity and serve on the team?) | Timeframe (important dates for completion of steps) | Resources and Support (financial, human, political, larger community-wide systems) |  | Potential Barriers or Resistance (and approaches to address these) | Communication Plan for Implementation (how to distribute info and who should receive) | Metrics: Tracking & Monitoring Progress (who, what, when, and how will data be collected?) | Progress as of Feb. 2 | Progress as of 4/30/2017 | Progress as of 9/30/2017 | Progress as of 3/25/18 | Progress as of 7/27/2018 | Plan for Year 3
|  |  | Available | Needed
Increase Number of Older Adults participating in existing activities
Promote existing activities | Arts for Life, SESCIL, Senior Source, Flat Rock Brook, JCC on the Palisades, Library | 1st qtr-ongoing | Many already exist at low- or no-cost. | Promotion of what's available | Lack of transportation or funding; see TRANSPORTATION work plan; funding may be provided to some organizations to support client fees. | See COMMUNICATIONS workplan | See COMMUNICATIONS workplan | extensive list published in e-News in Dec. & Jan; Feb nearly ready | Continue to promote activities in e-newsletter, Facebook and website. Working to develop community arts project in vacant storefront. | Continuing to promote activities through e-newsletter, Facebook and website. Continuing to develop storefront arts project. | Continuing to promote activities through e-newsletter, Facebook and website. Storefront arts project on hold. Info about activities included in Senior Directory published in March 2018. | Presented 4 programs this quarter: Community Baptist Church of Englewood, Senior Source, Rebuilding Together, Care Fair. | Continue to seek and provide programs in Yr 3
Develop/enhance knowledge of technology | Classes offered at Library, 111 West Street, Parks & Recreation Dept., High School students | 1st qtr-ongoing | Programs exist | Promotion of what is available | Lack of transportation. Overcoming sense that "I'm too old to learn" through education and outreach through Coalition Partners. | Recruit students through Coalition Partners' personal outreach. PR through local newspapers and online social media | # older adults who take classes. Coalition Partners, Coordinator, Support Staff |  | Low income senior building (111 West St.) has obtained new computer equipment but not yet installed it. We wil help coordinate lessons when computer lab is set up. | Donated computers turned out to be very low quality; setup not yet completed at 111 West. Plan to continue to develop program to link students and older adults for technology lessons. | Working with local tech store to develop lessons for seniors. Helping low-income housing building acquire computers and refurbish their community room. | Attempting to help the low-income senior buiding refurbish computer room and lounge. Met with Housing Authority Diector and interested local well-known architect eager to help. | Continue in Yr 3
Expand access to activities through personal invitation | Social clubs (Rotary, Woman's Club, Elks, etc.), Houses of Worship, Bergen Family Center/Mentoring Anyone; Coalition Partners, Housing complexes, neighborhood associations. | 1st qtr-ongoing | Many activities and clubs exist | Personal invitation to encourage attendance; transportation to activities | Transportation-some may not drive (Encourage sponsoring organizations to arrange car-pooling or ride-sharing to activities.) Membership requirements/fees (Some may not be able to afford Rotary or other clubs.) | Communicate importance of personal outreach through Coalition Partners, Clubs and Houses of Worship. Broad based PR to inform about range of clubs open to new members. | # people reached through personal contact; Coalition partners; Clubs; Houses of worship; Coordinator, Support staff | Planting the idea of personal outreach with Coalitioin partners and hopeful that they will do so. | Promoting activities of partner organizations vigorously and broadly through Website, Facebook and monthly e-newsletter. | Continuing to promote activities through e-newsletter, Facebook and website. Continuing to develop storefront arts project. | Continuing to promote activities through e-newsletter, e-mail blastsl, Facebook and website. Included a good deal of info about available activities in Senior Directory published in March 2018. | Continuing to promote activities through e-newsletter, e-mail blastsl, Facebook and website. Included a good deal of info about available activities in Senior Directory published in March 2018. | Continue in Yr 3
Host Celebration of milestone birthdays (5 year intervals) | Mayor, City agencies, Providers of service to seniors in Englewood, Coordinator; Support Staff | May, 2018 | People and agencies exist in town; host at Liberty School | Refreshments and give-always | Adequate promotion to get people there; adequate participants in "Senior Fair" to make it busy an fun. Raffle/gift cards as incentives. Extensive outreach to make this happen! | Reach milestone birthdays through tax records. Outreach to agencies for Senior Fair. Extensive PR in newspapers and social media. | #birthdays to be celebrated; # older adults who attend; # agencies participating. Coordinator, support staff, Coalition partners | Holding off on this as County and other towns are holding fairs in Spring. | Have asked County and City leaders to approach Bergen PAC to host celebration during Older Americans Month May 2018. |  | Held "Launch Party" to introduce new Senior Directory on March 15, 2018. Attended by about 40 people. | See below | Develop Celebration in Yr 3, perhaps in concert with Arts project to paint murals and utility boxes in Central Business District.
Coordinate and promote Celebration of Older Americans Month (May) with performance at Bergen PAC | BergenPAC, Coordinator, Coalition committee, support staff | 1st-3rd qtrs leading up to May event | Bergen PAC's contacts with entertainers/agents; Coalition partners to help publicize & sell tickets | Artists to perform; adequate sponsorships and publicity | Inability of BergenPAC to book appropriate entertainment | Broad promotion through Coalition partners, Facebook, Website, e-mail, paid ads | # attending performance; Bergen PAC, Coordinator, support staff |  |  | Met with CEO of Bergen PAC on5/23/17 to discuss idea of hosting special show during Older Americans Month next May. | Co-sponsoring with AARP-NJ a Doo-Wop show at BergenPAC on May 20. Sponsored ad in BergenPAC program for 6 months preomoting Age-Friendly Englewood and the 5/20 Doo-Wop show. | Sponsored Doo-Wop show at BergenPAC on May 20; hosted reception before "Doo-Wop" show at BergenPAC. 25 at reception; show was a complete sell-out. | Will look to sponsor another show at BergenPAC during Older Americans Month
Reach out to Isolated Older Adults
Reach out to isolated homebound individuals through providers of service and neighbors | Good Morning Englewood program of Police/Fire/EMS; Visiting Homemakers, Meals on Wheels, Kosher Meals on Wheels, Houses of worship, Volunteers to go door-to-door. | 1st qtr-ongoing | Some individuals are known Will work with local clergy to ID isolated individuals in Year 2 | To identify those who are isolated and not known | Difficult to reach those who are completely isolated. (We will aggressivley try various means of outreach) | Reach out through Coalition partner organizations, houses of worship, politicians, Post office(?) to identify those isolated. Make concerted effort to reach by personal visits and media outreach. | Numbers of isolated older adults identified. Service providers, houses of worship, politicians, Coordinator, Support staff | Working with Police Dept. which runs "Good Morning Englewood," callinegshut-ins daily. Have also reached out thorugh MealsOnWheels to deliver File of Life to clients. | April 2017 - Have proposed meeting with Police, Fire, EMS, Postmaster, Dept. of Health, OEM, Pharmacies, etc. to brainstorm how best to reach those isolated at home. | Met with Acting Fire Chief about expanding outreach to those who are isolated. Still trying to arrange meeting with Postmaster, Dept of Health, Pharmacies, etc. | Still intend to meet with Postmaster, Dept. of Health, Pharmacies, Police, Fire, EMS about reaching those who are isolated | Have not yet done this | Will plan for Yr 3
Host breakfast/Focus Group for local clergy of all faiths; purpose is to share ideas on how they support agingi-in-place, how to reach those who are isolated, etc. | Clergy of all faiths (already have list); Consultant/facilitator; Coordinator; Support staff | 1st qtr | List of clergy. Consultant who is expert facilitator | Participation by clergy | Reluctance of clergy to participate | Personal invitation by letter from Coordinator. Follow up by email and phone calls to encourage attendance. Consultant/Facilitator to provide report of session afterwards to make follow-up easier. | # clergy attending, ideas developed; Consultant/facilitator, Coordinator, Support Staff |  |  | Planning clergy breakfast for Year 2. | Planning clergy breakfast for late Spring | Hosted breakfast for leaders of 13 houses of worship on July 10: Protestant, Jewish & Muslim faiths represented. | Follow up on ideas to alleviate social isolation at Clergy breakfast
Mail postcard to Voter lists through politicians | Research utilization of voter registration and/or tax records to reach those isolated | 2nd qtr | Lists exist | Not sure if we can use lists | Not able to use voter or tax lists to reach out. Alternative will be more aggressive PR and personal contact through neighborhoods and houses of worship. We may also enlist volunteers to go door-to-door in their neighborhood to identify those who are isolated. | Develop and mail postcard alerting those who may be isolated of available services, such as "Good Morning Englewood,"Meals on Wheels and other services. | # of postcards sent. # of individuals who respond to postcard. # isolated older adults identified by outreach. Coordinator, support staff | Trying to find out how to get lists; County Clerk's office does not answer phone. Will stop in soon. | No luck with this yet. | According to Election Commission, voter list can only be provided for political campaigns. Am seeking to do so through candidate for City Council in Englewood.
Connect residents who respond to postcard mailing to existing facilities, programs and resources | Coordinator; Coalition Partners; additional organizations in or serving Englewood | 3rd qtr ongoing | many activities exist already | Contact info of those who respond to postcard | Moot point if we are not able to mail postcard. (If this is the case, we will utilize strategies listed herein.) May not be done in Year 2 | Ongoing outreach through media (see Communications & Information goal area) | # older adults connected with programs (for first time?); Service provider, Coordinator, Support staff
Connect those identified as needing services with service provider | Coordinator, Bergen Family Center, B.C. Div. of Social Services; Police/Fire/EMS, others who have knowledge of isolated older adults | 3rd qtr ongoing | Case management system already in place | Need to identify isolated older adults who need case management | Difficulty in identifying those completely isolated who may need services. (We will utilize professional services to protect client confidentiality.) | Work directly with Police/Fire/EMS and professional providers of case management | # older adults connected with case management system; Service provider, Coordinator, Support staff | Have fielded several calls from Coalition partners to link residents with services (City Manager, Dir. Of Health Dept., individual residents have contacted me directly for referrals.) About 10 calls to date with issues resolved. | Continue to provide linkage for those needing services. | Continue to provide linkage for those needing services, especially housing (which is tough). | Continue to provide linkage for those needing services, especially housing (which is tough). Respond by phone or email to requests for information. | Continue to provide linkage for those needing services, especially housing (which is tough). Responded by phone or email to 15 requests for information. | Continue in Yr 3
Reach out to Hispanic Populations
Conduct focus groups with Hispanic residents to engage them in Age-Friendly Englewood | Consultant, Coordoinator, Spanish-speaking staff of Coalition partner agencies | 1st-2nd qtr | Spanish-speaking facilitators & translators; consultant to devise process; format of earlier focus groups | Spanish-speaking resideints to attend focus groups | Lack of understanding of why their involvelment is important to them and to Englewood. Incentives of gift cards to Shoprite will be provided | Outreach through houses of worship, nonprofit partners, press releases and ads in Spanish-language media | # Hispanic residents attending focus groups; facilitator, coordinator, consultant, support staff |  |  | To continue in Year 2 | Planning Spanish-speaking focus group for late Spring 2018 | Held focus group in Spanish on June 13. Attended by 17 women and 1 man, all older adult residents of Englewood. Very good meeting. Will develop goals based on input at this meeting, such as more communication about activities to Spanish-language press. | Continue follow-up into Yr. 3
Develop Multi-Generational Activities that engage students with older adults
Provide training for students about the aging process | Jeanne Martin-Meals on Wheels Pascack Valley | 2nd qtr | High school advisors, presenter of topic | Students to participate | Lack of time by school advisors and/or students due to school schedules. (Will try to fit in /work around schedules.) | Outreach to students through schools. | # students trained; School advisors, Coordinator, Support staff |  | On hold for now - see below. | Same | Same | SAME -new Assistant Coordinator is reaching out to Jeanne Martin and to teacher/coordinator at Dwight Morrow High School | Continue in Yr 3
Students help/engage with seniors to rake, shovel snow, place/return garbage & recycling bins | High School students; 111 West Street, Houses of worship | 2nd qtr | Students and school advisors exist; older adults need help | Outreach to recruit students and older adults | Identifying older adults who need help; enlisting students to help them; keeping students engaged. Ongoing supervision of students is necessary. | Outreach to school advisors to help coordinate this activity. PR in local newspapers and social media. | # of students enlisted; # of older adults assisted. Schools track kids; Coordinator & Support staff track older adults assisted. | Posted the idea for able-bodied to shovel for less-able-bodied during recent snowstorm.Have reached out to Director of "The Zone" at Dwight-Morrow High School to get started. | Dwight-Morrow High School (and all public schools in town) currently in crisis mode; will approach these topics in the fall. Also cooperating with Volunteer Center and The Links to hopefully link volunteers to help isolated older adults with specific tasks. | Have hired a recently-retired Englewood Reference librarian to help with this in Year 2; she's done many projects with students over the years. | Recently retired librarian decided she didn't want to work. Am starting with a new person in April who will work on this. | Hired new Assistant Coordinator who will be working on this over the summer and Fall. Finally reached leaders of Boy Scout Troops in Englewood. | Continue in Yr 3
Help older adults understand options in retirement
Present workshops to provide information about Retirement and Benefits through established programs | Greater Bergen; NJ Foundation on Aging, Merrill Lynch Age Wave program, County Surrogate; Coordinator, Support staff | 2nd qtr-ongoing | Programs and information are available about benefits, wills, etc. | Programs for Age Wave | Recruit participants for programs | PR to precede each presentation in newspapers and social media; publicize through Coalition partners and specific locations (library, senior residence, churches, synagogues) | # participants in programs. Providers/hosts of programs, Coordinator, Support staff | Arranged meeting with Age Wave reps for Feb. 7 | Continuing to consult with Merrill Lynch (Age Wave) about modifying the program for low-income older adults. Very slow moving | Continuing to consult with Merrill Lynch/Age Wave/Bank of America about doing special programs about retiring, geared to lower-income individuals. | Project with Merrill Lynch/Age Wave on hold due to change in personnel at those organizations. | Continiue to promote Economic Security Index of Nat'l Council on Aging. Will not contnue Merrill Lynch/AgeWave project. | Will continue to promote Economic Security Index and other benefit assessment programs in Yr. 3
Explore development of a "Village" | Village to Village Network of Northern NJ working with Age-Friendly Englewood Coalition | 1st qtr-ongoing | Volunteer leader (Kathy Kuzma) |  | Interest in such a project needs to be cultivated (Mrs. Kuzma is developing a committee to work on this) | VtoV Network is communicating directly with interested individuals and Coalition Partners | # interested individuals; # volunteers recruited to work with the Village; Go-NoGo date of November 2017. VtoV coordinator | Kathy Kuzma is doing this | Kathy Kuzma continuing to do this. | Kathy Kuzma continuing to do this. | We hosted 2 meetings in 2018 to date to pursue interest in Englewood. The "village" project has little traction in Englewood. | No interest in Englewood | Will not pursue in Yr 3
Work plan developing a "Village" in Englewood is attached with this proposal. Those interested in working on this project are invited to do so at Coalition meetings and other gatherings coordinated by Age Friendly Englewood. Age-Friendly Englewood funds will only be used for minimal refreshments for meetings. | [10 empty] | At this point, Age-Friendly Englewood is not pursuing development of a "village". One kind of such entity is under development at Ahavath Torah, a synagogue with a very large Orthodox congregation.
Later ideas
Arrange a trip to a local place of interest | ?? | ?? | Ideas of where to go | Funding & transportation | This was suggested in brainstorming and got a lot of energy. Details to be worked out! | ?? | Coordinator |  |  | Some older adults want this to happen. Coordination is needed. | Looking in to and promoting opportunities for Englewood older adults to join trips sponsored by other towns (Leonia and Tenafly) | Senior Source is looking into putting together a few trips for older adults. We will promote such trips to Englewood residents. | Continue in Yr 3
Encouraging older adult women to speak out about harrassment | Coordinator | Ongoing starting early 2018 | YWCA is taking lead |  |  | Communicating through YWCA | Coordinator |  |  |  | Coordinator is participating in "Time is Now" coalition of the YWCA in response to the "MeToo" movement with the thought that many older women have been harrassed and had no way to express how they were impacted. | Partnering with the YWCA to promote their programs on this issue. | Will continue in Yr 3 as appropriate and as opportunities are presented

## Communications & Information
Priority Domain: COMMUNICATIONS & INFORMATION
Goal: Improve access to information about services and programs for older adults and caregivers
Collaborating Organizations: Coalition Partners, Local Media, 2-1-1, City Communications manager;
Activities | By Whom | Timeframe | Resources and Support |  | Potential Barriers or Resistance | Communication Plan for Implementation | Metrics: Tracking & Monitoring Progress (who, what, when, and how will data be collected?)
(what needs to be done) | (who will supervise this activity and serve on the team?) | (important dates for completion of steps) | (financial, human, political, larger community-wide systems) |  | (and approaches to address these) | (how to distribute info and who should receive) | (who, what, when, and how will data be collected?) |  | Englewood older adults are involved in planning all aspects of communications. They participated (and continue to participate) in focus groups and in monthly meetings. Additional input is received through one-on-one communications with the Coordinator and Coalition partners.
|  |  | Available | Needed
Communications Strategies to be utilized across all activities as needed | [8 empty] | Progress as of 4/30/2017 | Progress as of 9/30/2017 | Progress as of 3/25/18 | Progress as of 7/27/2018 | Plan for Year 3
Explore various avenues for sustaining age-friendly initiativs long term | Coordinator, Asst. Coord., Elected officials, city agencies, nonprofits, civic leaders | ongoing | Reservoir of activities and resources on which to draw | Commitment and funding to sustain age-friendly principles throughout Englewood | Lack of interest and/or funding to sustain | Assertive outreach to potential partners; keep public informed via social and traditional media. | Number of programs that find new homes |  |  |  |  | Exploring possiblities with elected officials, City Manager and select nonprofits. | Explore as stated
Promote Age-Friendly Englewood-related activities via print and social media | Coalition partners, Commuications Workgroup, Coordinator | ongoing | Info about programs and activities | email addresses of older adults, caregivers, family members | Capturing email addresses and importing into Constant Contact. (We will seek email adresses via Website sign-up, Coalition Partners, City offices, etc.) | Develop newsletter format; import email addresses; prepare and distribute quarterly newsletter utilizing Constant Contact. Also generate broad publicity through Coalition partner and local newspapers, driving readers to sign up on website for e-newsletter | # email addresses captured; # e-newsletters produced and distributed. Coordinator, Intern, Support staff, Communications Chair | Launched e-News in December with 183 addresses; now up to 242 | Enews mailing list now over 350 local organizations and individuals. Newsletter sent every month. Press releases sent to promote time-specific programs. Purchased ad space to be printed on 65,000 prescription bags delivered to customers of Buckleys Drugs. Began running ads on Facebook to promote specific events and/or links; these are proving successful in increasing our reach and engagment (clicks). | Enews mailing list now over 600 local organizations and individuals. Newsletter sent every month. Press releases sent to promote time-specific programs. Ad printed on 65,000 prescription bags delivered to customers of Buckleys Drugs. Continuing to run ads on Facebook to promote specific events and/or links; these are proving successful in increasing our reach and engagment (clicks). We did an online survey about our eNewsletter and got very positive feedback. 353 "likes" on Facebook as of 9/30/17 | E-news mailing is now over 800 local orgs, individuals and businesses. Newslettersent every month. Press releases sent to promote Launch of directory in March and Doo-Wop show in May. Continuing to run ads on Facebook to promote specific activities, events and items of interest. 381 "likes" on Facebook as of 3/25/18 | Monthly e-news sent to more than 900 email addresses; average 36% open rate. Nearly 1,000 Website visitors since 10/1/17. FACEBOOK: 450 "like" our Facebook page. Since 10/1/17, we've had 1103 visits, reached 41,157, and engaged 3,903 people. Press releases sent to local media to promote Doo-Wop show/Older Americans Month in May. E-mail blasts: Sent 35 blasts to 319 older adults and 45 coalition partner organizations since Oct 1, 2017 | Produce 12 e-newsletters-1 each month; post items at least weekly on Facebook; run paid ads to draw attention to important topics; send a press release to local media to promote each program we sponsor.
Create database as basis for creation of print and online directory of common referrals for older adult services; distribute print directory and publicize availability of both. | Coordinator, Intern, Communications Committee; Coalition partners | ongoing | Skills and some info available; Some funds budgeted through Taub grant; | Comprehensive info about available services; additional funds from local businesses. | Possibility that a printed directory will be out of date as soon as printed; online directory will need to be updated continually. Distribution | Broad publicity through Coalition partners, local newspapers and social media. Distribution through Coalition partners and other entities that serve older adults. | # of directories distributed; # visits to online directory. Coordinator, Intern, Support staff |  | Starting to compile information for directory to be distributed at Senior Conference at Community Baptist Church on September 9. | Assembling Directory information is continuing. Date of Conference at Community Baptist is now uncertain. | Directory was finished and 2,000 copies printed free of charge by SUEZ (water company). Distribution is in progress. Directory is well received. | Distributed all 2,000 copies at locations in Englewood; are going to reprint this summer. Will create database from information in Directory. | Continue to promote & distribute Directory in Yr 3. Develop database in Yr 3.
Promote NJ2-1-1 as source of information about services and activities | City Manager (City marquee); Coalition partners, Coordinator | 2nd qtr ongoing | NJ2-1-1 exists | Info about services input into 2-1-1 | Lack of info about NJ2-1-1 (We will promote NJ2-1-1 to partners and city agencies to enhance/enrich available information and promote 2-1-1 to public via outreach) | Promote NJ2-1-1 via City's electronic marquee, online media and e-newsletter as well as through Coalition Partners | # of hits on NJ2-1-1 from Englewood residents; # Englewood agencies listed in NJ2-1-1. NJ2-1-1 staff, Coordinator, Support Staff |  | Wrote news item about 2-1-1 for "My Englewood" newsletter distributed to Englewood residents with The Suburbanite (North Jersey Media Group) in March. | Items submitted to every edition of "My Englewood" about Age-Friendly Englewood. |  | Promoted NJ 2-1-1 in one monthly e-newsletter, in "My Englewood" City newsletter, and in Directory | Continue to promote in Yr 3
Survey residents about Age-Friendly Englewood activities, communications, programs, etc | Coordinator, support staff | ongoing | use Constant Contact survey tool | questions for survey based on current activities or need for info | lack of responses | direct distribution of survey to email lists; publication of results via e-News and press releases, as warranted by results of surveys | # surveys sent for each topic; # responses; Plan development or modification in reponse to survey results. Coordinator, Support Staff |  |  | Will do this in Year 2 to assess progress to date. | Survey will be done later in Spring. | Survey to be conducted Summer of 2018. | Analysis of survey and updated action based on results will be completed in Yr 3
Prepare materials in Spanish and/or other languages as needed | Coalition partners | 1st qtr ongoing | translators | translation of myriad materials | Securing translations in a timely manner | Request translation services from Coalition Partners as an ongoing activity of Age-Friendly Englewood | # documents (print and online) translated into Spanish and other languages as needed. Coalition partners; Coordinator, Intern, Support staff | Working on setting up brainstorming session for Spanish-speakers. This was in last-year's plan. | Still working on this. | Still working on this. Trying to get Spanish-language facilitators for focus group. | Still working on this. | Still working on this. Will reach out more to existing Spanish-language newspapers, as that's where members of our Spanish focus group get their information. | Continue in Yr 3
Utilize existing resources to promote Age-Friendly programs and services
Revised for Year 2 Encourage City to include more info for older adults (in addition to links to Age-Friendly Englewood) | City communications staff, Coordinator | 1st qtr ongoing | City website | Update w/ "age-friendly" info | Keeping website updated in a timely manner | Work closely with communications staff of City Manager/Mayor's Office | Monitor city website; # visits to Age-Friendly page(s). Coordinator, Intern, Support staff; City communications manager | City has posted a link to our website | Have been contacted by 11 residents who saw info about AFE in City communications. Added them to our email list. | Continuing to add to our email list. Now up to 600 + about 10 on snail-mail list. | Email list now over 800 with addition of Chamber of Commerce mailing list. | Constant Contact E-mail list is now expanded to over 900, including Chamber members and members of Englewood Rotary, elected officials, older adults and coalition partners. | Continue in Yr 3
Include generic "age-friendly" blurbs in annual DPW calendar | Coordinator, Intern, DPW staff | 1st qtr | To be completed before January 1 | DPW staff to initiate process for calendar | None | DPW distributes calendar to all Englewood residents | # calendars distributed; increased visits to agencies highlighted in the blurbs; DPW staff; coordinator, Intern, Support staff | Coordinated with DPW; calendar was printed in December & distributed to all residents in January. Finding out how many. | Working on 2018 calendar with DWP staff | Working on 2018 calendar with DPW staff; calendar to be distributed in Jan 2018 to all residents of Englewood. | 2018 Calendar completed & distributed to all reaideints. Age-Friendly Englewood and Age-Friendly practices included in every Sunday box throughout the year. | DPW will again include Age-Friendly Englewood information in their annual calendar distributed to 10,000 households. | Continue in Yr 3
Distribute Division of Senior Services pamphlets and Monthly calendar of events/programs | Coordinator, Intern, Coalition Partners, City agonies, nonprofits, businesses | 1st qtr ongoing | DSS materials are available | Distribution to Coalition partners and select locations | Managing distribution effectively across Englewood | Distribute DSS materials to City offices, beauty salons, barber shops, nonprofits, houses of worship, library, pharmacies, Shoprite, shops, civic groups | # of distribution points; # of brochures disbursed. Coordinator, Intern, Support staff |  | Distributing Div. of Sr. Services brochures at meetings and around town. Approximately 4,000 placed in venues and agencies in Englewood and handed out at Care Fair on 4/23/17 | Brochures distributed at Housing Conference in May and Transportation Conference in September. | Items promoted by the Div of Senior Services are includled in our e-newsletter and/or e-blasted | Items promoted by the Div of Senior Services are includled in our monthly e-newsletter and/or e-mail blasts | Continue in Yr 3
Include info about Age-Friendly Englewood in "My Englewood" newsletter produced by City | City communications staff, Coordinator | 1st qtr ongoing | Newsletter is already produced on regular schedule | Info about Age-Friendly program | Developing articles in timely manner (We will do this!) | Work with City staff to submit articles. City handles distribution | # links from City newsletter to AFE website. # inquiries from City Newsletter. City communications staff, Coordinator, Intern, Support staff | Article due Feb. 10 - will focus on Work Plan and e-mail sign-ups for e-news. | Article provided for "My Englewood" in March. | Article provided for "My Englewood" in June and September. | Included 2 articles in March 2018 edition of "My Englewood" - about the new directory and the 5/20 DooWop show. | Included 2 articles in June 2018 edition of "My Englewood"
Increase access to information
Expand/enhance use of technology (computers and/or smart phones) by older adults | SESCIL, Housing Authority, Library, Dept. of Parks & Recreation | 1st qtr ongoing | Local programs already exist | recruit and train students as teachers | Transportation to existing classes; reluctance to let student of other teacher into private home of older adult | Broad publicity through Coalition partners, local newspapers and social media. | # older adults given tech support; # students/other volunteers recruited, trained and matched with an older adult. Coordinator, Intern, Support Staff, Coalition partners | Working with low-income senior housing complex. They are getting new computers and already have an instructor. | Low income senior housing complex has new computers and is fixing up the basement to make a nice computer lab and recreation area. Not done yet. | Computer room has not yet been set up. When it is, we will help promote programs to learn technology. | Same | Same. Plan to coordinate series of tech sessions at local Apple vendor to provide lessons free of charge to older adults in Englewood. | Continue in Yr 3
Create desktop Plexiglas information “kiosks” for distribution of brochures in select community locations | Support staff, Coordinator, Coalition Partners; select locations in Englewood | 3rd qtr | Brochures from service providers | Funds to purchase 10 Plexiglas kiosks | Maintaining brochures provided in kiosks as they are depleted | Broad publicity through Coalition partners, local newspapers and social media. | # kiosks distributed; # kiosks re-filled. Intern, Support staff |  | On hold for now. | On hold for now. | On hold | Not doing - too difficult to keep materials up to date.
Reach out to caregivers and family members of older adults in Englewood | Coordinator, Intern, Coalition partners | 1st qtr ongoing | Information relevant to care-givers | Who/where are caregivers | Seek caregivers through Caregiver Coalition of Bergen County; provide programs relevant to caregivers | Invite caregivers to visit websites and attend programs via broad publicity through Coalition partners, local newspapers and social media. | # caregivers who self-identify via website visits and attendance at programs targeted to them. Coordinator, Intern, Support staff, Coalition partners, program providers |  | Working with Community Chest on "SUMMIT" to be held on June 19 and focus on needs, including those of older adults, in Eastern Bergen County. Beginning to reach out to identify caregivers and refer them to the Care Giver Coalition of Bergen County; may do program on this next year. | Facilitated session on Older Adults at June 19 Community Issues Summit of the Community Chest. Am regularly provided information to/for Caregivers through the Bergen County Caregiver Coalition which we distribute out to our lists. | Attend monthly Caregivers Luncheons at Bergen Family Center. Promote Caregiver meetings of the JCC and the Caregiver Coaltion of Bergen County through our e-news and email blaslts. | Continuing to promote caregiver groups | Continue in Yr 3
Explore additional communications vehicles | Coalition Partners, Friends, Coordinator, Intern | 1st qtr ongoing | Look into feasibility of: Public access Cable TV channel; Bulletin board at Shoprite; Opt-in/sign up for robo-calls from City about Age-Friendly activities; Information phone line staffed by senior volunteers |  |  |  | Will need to figure out how to track this. Communications Work Group; Coalition Partners; Coordinator, Intern, Support staff | Have developed branded website, newsletter, letterhead, ads, business cards, hand-outs, etc. Also ordered stand-up banner and table cover with our brand. | Continue to expand communications effectively and efficientlly | Working on this regularly. | Continuing full range of communications. | Continuing full range of communications. Expand use of Twitter | Continue in yr 3