## Action Plan
TORBAY ASSEMBLY |  |  |  |  | Planning | [14 empty] | Year 1 | [11 empty] | Year 2 | [11 empty] | Year 3
Age Friendly Torbay Action Plan |  | Based on Age Friendly Environments Cycle of Continuous Improvement | 2021-04-01 |  | 2020/2021 |  |  | 2021/2022 | [11 empty] | 2022/2023 | [11 empty] | 2023/2024 | [11 empty] | 2024/2025
Objective | Action | Who | Outputs | Milestone | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M
1. Engage and understand |  |  |  |  | 2020/2021 J: 1. Engage and understand
Form active steering group | 1.0 Set up an Assembly partnership, committee/working group/steering group. | Recruit voluntary and lay community representatives and representatives from Council, TCDT, Age UK, NHS, business and employer representative. | Monthly meetings | 2021-02-01 | bar: 2020/2021 F
Form active steering group | 1.1. Perform a participatory assessment. | Include Council, TCDT and NHS – add Torbay Assembly sign-up to Charter. | Report | 2021-03-01 | bar: 2020/2021 F to 2020/2021 M
Form active steering group | 1.2 Recruiting an active Chairperson and Vice Chair | Assembly Action Group - define role. Consider leadership team. | Recruited | 2022-02-01 | bar: 2021/2022 J to 2021/2022 F
Form active steering group | 1.3 Paid coordinator three years | Assembly Action Group | Funding and recruited | 2022-04-01 | bar: 2022/2023 A to 2024/2025 M
Assess Torbay's Profile | 2.0 Create a baseline profile. | Review AWT Ageing Better Baseline Profile Report Torbay | Add review to update existing report | 2021-07-01 | bar: 2020/2021 F to 2021/2022 J
Feedback on plans | 3.0 Disseminate findings. | To Council, TCDT, NHS, Assembly, Age UK, UK Network of Age-friendly Communities. Ageing Better, Community Partnerships, Healthwatch, Good Neighbours Network | Report and quarterly newsletter to members | 2021-08-01 | bar: 2020/2021 M to 2021/2022 A
Recognition of Age-friendly values | 4.0 Gain political commitment. | Leader of the Council, Steve Darling, ward Councillors and local politicians. | Letter and WHO application submitted | 2021-09-01 | bar: 2020/2021 M to 2021/2022 S
Good Communications | 5.0 Research comms for all members where they can participate in decision making. | TCDT Comms, Assembly, NetFriends | Systems of Communications and Media | 2021-10-01 | bar: 2021/2022 A to 2021/2022 O
2. Plan |  |  |  |  | 2020/2021 J: 2. Plan
Form active and committed steering group | 1.0 Unite stakeholders behind a common vision. | Assembly Action Group | Charter agreed | 2021-06-01 | bar: 2020/2021 M to 2021/2022 J
Assess Torbay's Profile | 2.0 Analyse strengths and weaknesses of action plan. | Assembly Action Group | Report | 2021-06-01 | bar: 2020/2021 M to 2021/2022 J
Effective strategy and action plan | 3.0 Strategy formulated into an accessible charter | Assembly Action Group | Report. Update action plan. | 2021-08-01 | bar: 2021/2022 A to 2021/2022 A
Recognition of the value to the community of Age-friendly processes | 4.0 Get approved. | Council, TCDT, NHS, Assembly and Age UK, Healthwatch | Approval - signed charters | 2021-09-01 | bar: 2021/2022 J to 2021/2022 S
Effective strategy and action plan | 5.0 Define responsibilities. | Assembly Action Group | Action Plan | 2021-09-01 | bar: 2021/2022 J to 2021/2022 S
3. Act |  |  |  |  | 2020/2021 J: 3. Act
Achieve WHO membership | 1.0 Make a three year action plan to submit to WHO | Assembly Action Group | Action Plan | 2021-06-01 | bar: 2021/2022 A to 2021/2022 A
Achieve WHO membership | 1.1 Achieve WHO membership | Assembly, Age-friendly Partners | Member status | 2021-09-01 | bar: 2021/2022 J to 2021/2022 S
Achieve WHO membership | 1.2 Announce and launch at AWT Festival | AWT Programme, Assembly, Age-friendly Partners | Festival | October 2021 | bar: 2021/2022 O
Effective strategy and action plan | 2.0 Consult on plan. | Community Builders, Assembly etc | Review and update | 2021-10-01 | bar: 2021/2022 A to 2021/2022 O
Source resources | 3.0 Secure support and resources. | Action Group | Funding, meeting place, resources. | Annual review
Implementing action plan | 4.0 Implement action plan. | Action Group | Community engagement | Annual review
Recognition of the value to the community of Age-friendly processes | 5.0 Scale up successful action. | Action Group | Community engagement | From Nov-21 | bar: 2021/2022 N to 2024/2025 M
Engagement | 6.0 Grow membership | Action Group | 3% annually | Review annually | bar: 2021/2022 N to 2024/2025 M
Engagement | 6.1 Increase our partnership networks | Action Group | Working Collaborative Partnerships | Review annually | bar: 2021/2022 N to 2024/2025 M
4. Measure |  |  |  |  | 2020/2021 J: 4. Measure
Review action plan | 1.0 Monitor progress | Assembly Action Group | Report, Research Ripple Effect Mapping | From Sept 2021
Learn from implementation | 2.0 Carry out outcome and impact evaluation. | Assembly Action Group | Report and updated action plan | 6 monthly from Dec 2021 | bar: 2021/2022 N to 2021/2022 D; 2022/2023 J; 2022/2023 D; 2023/2024 J; 2023/2024 D; 2024/2025 J; 2024/2025 M
Maintain active and committed steering group and partnerships | 3.0 Continue and expand partnerships. | Assembly Action Group | Community engagement | From May-2021
Review action plan | 4.0 Sustain and continually improve action. | Assembly Action Group | Report and updated action plan | From Sep-2021 | bar: 2021/2022 S to 2024/2025 M
Share learnings/experience | 5.0 Exchange internationally. | Assembly Action Group report progress to WHO and UK at least one age-friendly practice per year. | Photos/Media and report | End of each year | bar: 2021/2022 D; 2022/2023 D; 2023/2024 D; 2024/2025 M
Influence Policy | 6.0 Representatives on planning groups | Assembly representatives (themes) | Health and Wellbeing Board, Council Planning, Adult Social Care, Children, Youth and Families. | From Jan-21 | bar: 2021/2022 J to 2024/2025 M
5. Share and celebrate |  |  |  |  | 2020/2021 J: 5. Share and celebrate
Share learning | 1.0 With Torbay Community, UK Network and WHO Global Network | Assembly Action Group | Learning publications and guidelines | 6 monthly | bar: 2022/2023 J to 2022/2023 O; 2023/2024 J to 2023/2024 O; 2024/2025 J to 2024/2025 O
Celebrate | 2.0 With Torbay Community | Assembly, Age-friendly Partners | Festival and events | 6 monthly | bar: 2022/2023 S to 2022/2023 O; 2023/2024 S to 2023/2024 O; 2024/2025 S to 2024/2025 O
6. Theme related actions |  |  |  |  | 2020/2021 J: 6. Theme related actions
1. Community Support and Health Services | 1.0 Health and Wellbeing Board members Age Friendly Audit | HWBB Assembly representative | Audit linked to charter | One partner every 6 months | bar: 2022/2023 A to 2022/2023 J; 2022/2023 O to 2022/2023 D; 2023/2024 A to 2023/2024 J; 2023/2024 O to 2023/2024 D; 2024/2025 A to 2024/2025 J; 2024/2025 O to 2024/2025 D
| 1.1 Representation on Mental Health Alliance | Assembly Mental Health representative | Collaboration in Mental health voluntary and statutory sector | Quarterly meetings | bar: 2022/2023 A; 2022/2023 J; 2022/2023 O; 2022/2023 J; 2023/2024 A; 2023/2024 J; 2023/2024 O; 2023/2024 J; 2024/2025 A; 2024/2025 J; 2024/2025 O; 2024/2025 J
| 1.2 Frailty and Healthy Ageing and Living Longer Better resources and activities in the community | Assembly coordinator | Resources and engagement | Review 6 monthly | bar: 2022/2023 J; 2022/2023 D; 2023/2024 J; 2023/2024 D; 2024/2025 J; 2024/2025 D
2. Civic Participation and Employment | 2.0 Employment path ways and opportunities for local people developed - from volunteering to employment | Assembly Employment representatives | Pilot | Review yearly | bar: 2022/2023 O to 2023/2024 A; 2024/2025 A
| 2.1 Wealth Building representative/advocate | Assembly coordinator and representatives | Wealth Building plan | Review yearly | bar: 2023/2024 M to 2023/2024 N; 2024/2025 N
| 2.2 Awards and acknowledgments for local contributions | Assembly coordinator, representative and partners | Event | Annual | bar: 2021/2022 O; 2022/2023 O; 2023/2024 O; 2024/2025 O
3. Social Participation | 3.0 Annual Festival | Assembly and partners | Event | Annual | bar: 2021/2022 O; 2022/2023 O; 2023/2024 O; 2024/2025 O
| 3.1 Age Friendly Events and activity listings | Assembly representatives and coordinator | Web listing | Seasonally updated | bar: 2021/2022 N; 2021/2022 F; 2022/2023 M; 2022/2023 A; 2022/2023 N; 2022/2023 F; 2023/2024 M; 2023/2024 A; 2023/2024 N; 2023/2024 F; 2024/2025 M; 2024/2025 A; 2024/2025 N; 2024/2025 F
| 3.2 Support places of welcome in Brixham, Paignton and Torquay | Coordinator | Partners providing spaces | Review annually | bar: 2021/2022 M; 2022/2023 M; 2023/2024 M; 2024/2025 M
4. Communication and Information | 4.0 Clear and accessible information is provided about the health and social services for older people. | Assembly and partners | Guidelines | Update yearly | bar: 2021/2022 D; 2022/2023 D; 2023/2024 D; 2024/2025 D
| 4.1 Charter signed | Assembly representatives | Four each year | Review yearly | bar: 2021/2022 F; 2022/2023 F; 2023/2024 F; 2024/2025 F
| 4.2 Promoting blended including digital approaches to communications | Assembly and partners | Phone, digital, media, personal and groups. | Update 6 monthly | bar: 2021/2022 M; 2022/2023 S; 2022/2023 M; 2023/2024 S; 2023/2024 M; 2024/2025 S; 2024/2025 M
| 4.3 Quarterly Partner Forum | Coordinator and Action Group | Meetings and reports | Quarterly meetings | bar: 2021/2022 M; 2022/2023 S; 2022/2023 M; 2023/2024 S; 2023/2024 M; 2024/2025 S; 2024/2025 M
5. Respect and Social Inclusion | 5.0 Guidelines for businesses and organisations | Coordinator | Guidelines | Review yearly | bar: 2022/2023 S to 2022/2023 J; 2023/2024 J; 2024/2025 J
| 5.1 Intergenerational work with schools - piloted | Coordinator, assembly members, partners and Imagine This | Pilot | Review in first year | bar: 2024/2025 S to 2024/2025 M
| 5.2 Research loyalty card/voucher scheme for local people supporting local businesses | Assembly representatives | Scoping and pilot | Review in first year | bar: 2023/2024 A to 2023/2024 S; 2023/2024 M; 2024/2025 M
| 5.3 Reengage people with community post COVID. | Membership | Isolated and shielding people supported | Quarterly review | bar: 2021/2022 A to 2021/2022 M
6. Housing | 6.0 Age Friendly housing design and planning guidelines | Coordinator and Assembly representatives and partners | Guidelines | Review yearly | bar: 2021/2022 A; 2021/2022 J; 2021/2022 O; 2021/2022 J; 2022/2023 A; 2022/2023 J; 2022/2023 O; 2022/2023 J; 2023/2024 A; 2023/2024 J; 2023/2024 O; 2023/2024 J; 2024/2025 A; 2024/2025 J; 2024/2025 O; 2024/2025 J
| 6.1 Contribute to a housing alliance that advocates for affordable living communities. | Assembly representatives | New and updated plans and policies | Quarterly meetings | bar: 2021/2022 J to 2022/2023 J; 2022/2023 J; 2023/2024 J; 2024/2025 J
| 6.2 Advocate for blended and integrated approaches between community and care living facilities. | Coordinator and Assembly representatives and partners | Pilot | Review yearly | bar: 2022/2023 S to 2022/2023 F; 2023/2024 F; 2024/2025 F
7. Outdoor Spaces and Buildings | 7.0 Natural Healthy Forum and Torbay on the Move - join | Assembly representatives | Local green space initiatives | Quarterly meetings | bar: 2020/2021 J; 2021/2022 A; 2021/2022 J; 2021/2022 O; 2021/2022 J; 2022/2023 A; 2022/2023 J; 2022/2023 O; 2022/2023 J; 2023/2024 A; 2023/2024 J; 2023/2024 O; 2023/2024 J; 2024/2025 A; 2024/2025 J; 2024/2025 O; 2024/2025 J
| 7.1 Representation on environmental planning | Assembly representatives | New and updated plans and policies | Quarterly meetings | bar: 2020/2021 M; 2021/2022 J; 2021/2022 S; 2021/2022 D; 2021/2022 M; 2022/2023 J; 2022/2023 S; 2022/2023 D; 2022/2023 M; 2023/2024 J; 2023/2024 S; 2023/2024 D; 2023/2024 M; 2024/2025 J; 2024/2025 S; 2024/2025 D; 2024/2025 M
| 7,2 Local Age Friendly guidelines | Coordinator | Guidelines | Review yearly | bar: 2022/2023 M to 2022/2023 J; 2022/2023 J; 2023/2024 J; 2024/2025 J
8.Transport: | 8.0 Representation on transport planning committee | Assembly representatives | New and updated plans and policies | Quarterly meetings | bar: 2020/2021 F; 2021/2022 M; 2021/2022 A; 2021/2022 N; 2021/2022 F; 2022/2023 M; 2022/2023 A; 2022/2023 N; 2022/2023 F; 2023/2024 M; 2023/2024 A; 2023/2024 N; 2023/2024 F; 2024/2025 M; 2024/2025 A; 2024/2025 N; 2024/2025 F
| 8.1 Advocating for improved public transport for underserved routes | Coordinator and Assembly representatives and partners | Community Transport initiatives | Review yearly | bar: 2022/2023 S; 2023/2024 S; 2024/2025 S
| 8.2 Advocating for affordable, clean and efficient public transport services | Coordinator and Assembly representatives and partners | Monitor standards | Review yearly | bar: 2022/2023 J; 2023/2024 J; 2024/2025 J
9. Integrate the themes | 9.0 Joined up and integrated approaches that link the themes - ie healthy, active in nature with efficient transport options. | Membership | Partnership working and person centred approaches | Review yearly | bar: 2022/2023 A; 2023/2024 A; 2024/2025 A
| 9.1 Legacy - Enjoying and celebrating growing older | Assembly Action Group and membership | Monitor through engagement | Annually | bar: 2022/2023 A; 2023/2024 A; 2024/2025 A
Support functions
Recognition of the value to the community of Age-friendly processes | 1. Building an understanding of the age-friendly concept and age-friendly cities and communities | Action Group
Form active and committed steering group | 2. Identifying key stakeholders and partners | Action Group
Form active and committed steering group | 3. Building a team | Action Group
Form active and committed steering group | 4. Identifying and developing leadership | Action Group
Form active and committed steering group and partners | 5. Establishing governance, management and advisory infrastructure | Action Group
Form active and committed steering group and partners | 6. Facilitating community meetings | Action Group
Form active and committed steering group and partners | 7. Using co-design, co-creation and other collaborative processes | Action Group
Form active and committed steering group and partners | 8. Ensuring older people’s participation | Action Group
Recognition of the value to the community of Age-friendly processes | 9. Securing political support | Action Group
Recognition of the value to the community of Age-friendly processes | 10. Providing technical assistance and support (e.g. translating or adapting WHO documents) Providing training or ongoing education | Action Group
Achieve WHO membership | 11. Applying for membership with the GNAFCC Council | Action Group
Effective strategy and action plan | 12. Undertaking community assessments and determining priorities for change | Action Group
Effective strategy and action plan | 13. Developing an action plan | Action Group
Implementing action plan | 14. Implementing the plan | Action Group
Implementing action plan | 15. Providing project management or project coordination | Action Group
Source resources | 16. Securing funding | Action Group
Managing Age-friendly Torbay | 17. Managing finances and information, and/or providing legal advice | Action Group
Review action plan | 18. Measuring impact and building a system of continuous improvement (e.g. collecting data, feedback, monitoring, researching, evaluating progress) | Action Group
Recognition of the value to the community of Age-friendly processes | 19. Communicating the age-friendly work to the wider community | Action Group
Recognition of the value to the community of Age-friendly processes | 20. Sharing successes and lessons learned through, for example, the Age-friendly World website | Action Group
Share learnings/experience | 21. Connecting directly with other cities and communities | Action Group