## Yate Ageing Better 2021 Actions
Yate Town Council
Yate Ageing Better Action Plan 2021-2022
Objective | Action | Target Date | Status December 2021 | Review Date
1. Raise the profile of older people in Yate |  |  |  | 2022-12-01
1.0 Create an identifiable Yate Ageing Better ‘brand’ to position Yate as an age-friendly community and use this to bring together the diverse initiatives that exist in the town, and to raise awareness of new ones. | Engage community in a competition to design a brand logo for Yate Ageing Better | 2020-04-01 | Completed and logo is now in use for Yate Ageing Better.
1.1. Organise an official community launch event for Yate Ageing Better to showcase local services and things to do for those over 50 in Yate | Decide the date, gather interested Members and staff to coordinate vision and plan for the event in 2021. | 2020-05-01 | Completed Yate Ageing Better Festival took place October 2021
1.2 Join the UK Network of Age-Friendly Communities, hosted by the national Centre for Ageing Better |  | 2020-09-01 | Completed
1.3 Join the WHO Global Ageing Friendly Communities | Create a baseline profile, letter of commitment from Yate Town Council Mayor, | 2021-04-01 | Completed attached to Global WHO age friendly communities application profile
1.4 Involve and empower older people in the community | Start by setting up a team of 10-12 Champions who will meet regularly with Council members to plan policy and promote the age-friendly agenda. | 2021-10-01 | Ongoing- Unsuccessful at Yate Ageing Better Festival but continue to explore with Councillors
1.5 Designate a member of the Council’s Staff as the key contact for issues affecting older people. | Consideration could be given to co-opting older people onto the Sub-Committee or bring under existing community group Yate Community Plan | Sept 202 | Completed- Community Projects Manager and Chair of the Yate Ageing Better, Health and wellbeing Working Group
1.6 Establish Yate Ageing Better Awards for organisations and older individuals that make a positive contribution to the lives of older people or who inspire and help others. | Decide the date, gather interested Members and staff to coordinate vision and plan for the event in 2021. | 2021-10-01 | Ongoing- look to encorporate this into the next Yate Ageing Better Festival in June 2022
2. Tackle social isolation and loneliness
2.1 Ensure older people moving to and living in the Town can access information on 'what's on' for the over 50s | Produce an information directory and ensure there are welcome packs available to those moving to the area | 2021-01-01 | Completed April 2021 available online
2.2 Signpost older people to existing services to reduce social isolation and loneliness such as the befriending scheme delivered by 'Age Uk South Gloucestershire' |  | 6 Monthly | Ongoing
2.3 Make greater use of the Pop Inn Café (over 50's café) for encouraging socialising | Create a welcoming 'Happy to Chat' table/space within the café for those visiting the café alone | 2021-09-01 | Completed
2.4 Implement a 'Dementia Friendly Friday' session at the Pop Inn Café | Organise a new session on a Friday welcoming those living with Dementia, their carers and family members | 2021-01-01 | Ongoing COVID19 and volunteer capacity currently an issue, revisit in early 2022
2.5 Engaging local community transport Services at the Pop Inn Café | Inviting organisations to attend the Pop Inn Café and ensure promotions of their service are readily available throughout | Ongoing | COVID19 dependent, revisit early 2022
2.6 Promote the Town Council ageing initiatives and services | Utilising social media, press releases and community noticeboards/properties to promote local groups and 'happy to chat' facilities |  | Ongoing COVID19 dependent revisit early 2022
3. Encourage more opportunities for physical exercise
3.1 Support and promote gentle exercise sessions in venues such as Yate Active Living Centre, Shire Way Community Centre, the Pop Inn and Armadillo and in care homes. | Promote what is currently available on Town Council notice boards and social media. |  | Ongoing via the Yate Ageing Better Facebook Page
3.2 Explore introducing gentle exercise for the over 50s at our community venues such as YOSC (Yate Outdoor Sports Complex), Playing fields and bowling club. | Discuss with YOSC potential development of activities for older people | 2022-01-01 | Awaiting partnership documents to be agreed, revisit early 2022
3.3 Liaise with Yate Active Leisure Centre – to promote times when older people can use the pool, and to make people aware of ‘quiet’ times. | Promote what is currently available at the lifestyle centre to our visitors to over 50s provision locally |  | Ongoing via our Yate Ageing Better Facebook Page
3.4 Support and promote the range of physical activities offered by Yate and Sodbury U3A so that older residents can benefit. | Make use of Town Council notice boards to rotate promoting community activity groups such as U3A and Towns Woman’s Guild. Liaise with groups to promote their activities. Eg.weekly social media post and round up newsletter article on rotating community groups. |  | Ongoing
4. Extend the range of intergenerational activities
4.1 Examine ways of working with local Schools around supporting ageing in our community | Contact the secondary schools to explore ways of working with them within the sport or cookery department in context of Yate Ageing Better, Health and Wellbeing projects | 2021-09-01 | Completed- 2 main secondary schools contacted but confirmed they already have in house provision and are not looking to expand
5. Opportunities for older people to eat and cook together
5.1 A ‘relaunch’ of the Pop Inn, with a focus on healthy eating. (Include rebranding of age range to fit with customer base) | A starting point could be the addition of new items, such as homemade soup, to the menu. It could be followed by phased introduction of an extended, nutritionally sound, lunchtime menu, initially for a trial period and only on specific days of the week. This could be an opportunity for recently recruited volunteers to be inducted into the Pop Inn team. | 2020-04-01 | Completed- no further plans to extend food offer at the Over 50s Café at this time
5.2 Explore ways of promoting more shared meals across the town, including cooking and eating together. | Try to identify a suitable venue to host such activities and also explore ways of delivering or supporting the delivery of such activities. | 2022-01-01 | Ongoing- YMCA will be ready early 2022 and will run a community open day to gauge interest from local services
6. Encourage and support volunteers
6.1 There is no central point for older people to find out about volunteering opportunities in the area. | Use launch of the Yate Ageing Better Health and Wellbeing initiative to promote volunteering | 2021-10-01 | Completed and continue to promote opportunities to volunteer for the over 50s at our venues
6.2 The achievements and contribution of volunteers should also be recognised and celebrated, and the Council could play a part in this. | Celebrate and thank volunteers at Civic Christmas event. | Covid Dependent | Ongoing
7. Make full use of the town’s assets and facilities
7.1 Assess and review our properties to consider how ageing friendly they are | consider findings from assessments and consider improvements/additions where possible |  | Ongoing- to be undertaken as part of a wider organisation review of accessibility on our properties
7.2 Consider implementing more 'happy to chat' social 'resting spaces' out in our parks and open spaces | Roll out of happy to chat benches, subject to successful trial at Kingsgate Park, St Mary's green and Abbotswood | 2021-01-01 | Ongoing- COVID19 dependent revisit early 2022
7.3 Ensure the Town Council URBIE (Urban Vehicle for Information and Education) is used at more activitiesand events aimed at the over 50s | Utilise the URBIE at the Yate Ageing Better Event and explore using it at other annual events the Town Council organise. | 2021-10-01 | Completed- The Urbie was on site for the Yate Ageing Better Festival and will be used at future events aimed at the over 50s