## Slide 1: Rapid Response Teams Managers Workshop
Venue, country, dates
Welcome!
Country logo/flag
Speaker name

## Slide 2
This module includes basic information about RRT Training Programme Monitoring and Evaluation. A comprehensive version of this module, including detailed Key Performance Indicators, will be published once the WHO RRT Monitoring and Evaluation Framework is finalized, in the course of 2024.
2
Warning!

## Slide 3
The content of this presentation is to be adapted to your final RRT MTP agenda and specifics of your country. Areas to be reviewed/completed by RRT MTP organizers/facilitators are highlighted in yellow.
2
Note to facilitators

## Slide 4
Module 5
Introduction to RRT programme monitoring and evaluation in country
3

## Slide 5
At the end of this module, you will be able to:
Define monitoring and evaluation
Define indicators and recall their types
Recall the objectives of monitoring and evaluation of RRT programme during preparedness and response phases
Identify tools for monitoring and evaluation of RRT programme during preparedness and response phases
Identify RRT programme M&E challenges and how to mitigate them
Module objectives
4

## Slide 6
5.1 Monitoring and evaluation: definitions and
concepts
5.2 RRT M&E in preparedness and response phases
Outline
5

## Slide 7
5.1 Monitoring and evaluation: Definitions and concepts
6
Notes: Paula

## Slide 8
At the end of this session, you will be able to:
Define monitoring and evaluation
Define indicators and recall their types
Session objectives
4

## Slide 9
  In an active emergency, processes in the two phases may intersect, especially in countries that do not have a functional RRT prior to emergency onset.
Reminder: RRT preparedness and response phase operations
5.1 Monitoring and evaluation: definitions and concepts

## Slide 10: M&E is an important tool to:
Support evidence-based decision making at programmatic & policy levels
Allow for the comparison between what was planned to occur & what is actually occurring
Ensure the most effective & efficient use of resources
Determine the extent to which the program/project is on track & to make any needed corrections accordingly
Evaluate the extent to which the program/project is having or has had the desired outcomes & impacts
Produce & share information with stakeholders
Report to development partners
M&E promotes organizational learning & encourages adaptive management
Notes: Utility of the data for stakeholders: need for a feedback mechanism (CQI process)

## Slide 11: Definition of monitoring
Monitoring is a continuous process that involves the regular collection and analysis of data to facilitate timely decision-making, verify that activities are being carried out according to plan, ensure accountability, and provide the basis for evaluation and learning.
With regards to the RRT programme, monitoring is a continuous process to inform the RRT managers, members, and stakeholders of what the programme achieved against planned results. It tracks changes in RRT programme performance over time and the achievement of specified results.
5.1 Monitoring and evaluation: definitions and concepts
8
Notes: Monitoring
Continuous process; routine data collection​
Data used to inform day-to-day management​
Track what is happening with a program: ​
-What resources have been used? (inputs)​
-What activities have been completed? (outputs)​
-Are the activities resulting in the intended changes? (outcomes)​
Results used to make real-time decisions​
When to Monitor:
Understand what is happening to your program regularly
Data is easier to collect
Early warning measure of risk that may disrupt progra
Make real-time decisions

## Slide 12: Definition of evaluation
Evaluation assesses the degree of success achieved and determines to what extent the anticipated outcomes are produced. It measures whether objectives have been achieved through specific intervention activities. Evaluation also provides insights into lessons learned and promising practices.
With regards to the RRT programme, evaluation is the systematic and targeted examination of the extent to which the programme has achieved or is achieving its predetermined objectives over its life. Evaluation assesses the effectiveness, efficiency, impact, and relevance of the Rapid Response Teams programme.
Learning is the process through which information generated from M&E is reflected upon and intentionally used to continuously improve the RRT's ability to achieve results.
5.1 Monitoring and evaluation: definitions and concepts
9
Notes: Evaluation:
Collect data at discrete time points
Answer specific questions related to design, implementation & results
Assess causal contribution of activities to outcomes & impact
Results used to improve future operations, inform policy, etc.
When to Evaluate
Assess questions to inform future policies and programs
Requires more resources for data collection
Outcomes that are difficult to measure frequently
Not likely to change during short time frame

## Slide 13: Monitoring vs. evaluating
What do we mean by Monitoring & Evaluation?
MONITORING |  | EVALUATION
Continuous process; routine data collection |  | Collect data at discrete time points
Data used to inform day-to-day management |  | Answer specific questions related to design, implementation & results
Track what is happening with a program: -What resources have been used? (inputs) -What activities have been completed? (outputs) -Are the activities resulting in the intended changes? (outcomes) |  | Assess causal contribution of activities to outcomes & impact
Results used to make real-time decisions |  | Results used to improve future operations, inform policy, etc.

## Slide 14: Monitoring vs. evaluating
When to Monitor vs. Evaluate?
MONITORING |  | EVALUATION
Understand what is happening to your program regularly |  | Assess questions to inform future policies and programs
Data is easier to collect |  | Requires more resources for data collection
Early warning measure of risk that may disrupt program |  | Outcomes that are difficult to measure frequently
Make real-time decisions |  | Not likely to change during short time frame
Monitoring & evaluation are complementary
Monitoring & evaluation should always be conducted for every program/project

## Slide 15: M&E (ideal) timeline
During program implementation
After program implemented
for some time
Before program is implemented
Why is the program being implemented in this way for these people?
What does the organization plan to do?
What are the risk they face?
Analyze data & draw conclusions about impact of program (evaluation)
Disseminate findings
Collect & analyze data (monitoring & evaluation)
Identify opportunities for improvement (monitoring)

## Slide 16: Data-driven decision making
Monitoring
What resources have been used? (inputs)
What activities have been completed? (outputs)
Are the activities resulting in the intended changes? (outcomes)
Questions
Actions
Adjust inputs (funding, staffing, resources)
Adjust program activities
Evaluation
Provision: are the services accessible? Is their quality adequate?
Utilization: are services being used?
Coverage: is the target population being reached?
Impact: was their improvements to behavior change or health?
Adjust location of services
Improve quality of services
Change outreach strategy
Inform program strategy

## Slide 17: Key questions for monitoring and evaluation
For whom are the data collected (stakeholders)?
What data are collected (questions and indicators)?
How is data collected (methodology)?
Who collects the data (personnel)?
When is data collected (frequency)?
Who reports the data and when/how often?
Who does what based on the information?

## Slide 18: Definition of indicators (1)
Indicators represent summary of qualitative or quantitative measures that capture relevant information on different attributes and dimensions, and the performance of programmes, health system, …
With regards to the RRT programme, an indicator is a quantitative or a qualitative factor that provides a simple and reliable means to measure achievement or reflect changes connected to or affecting the RRT work.
The construction of an indicator is a process with various degrees of complexity, ranging from a direct count (numbers) to the calculation of proportions, rates, ratios, and more sophisticated indices.
5.1 Monitoring and evaluation: definitions and concepts
10

## Slide 19: Definition of indicators (2)
Indicators should be SMART (Specific, Measurable, Attainable, Relevant, and Time-Bound).
Specific : Able to be translated into operational terms, focusing on the ‘who’ and the ‘what’ of the intervention. It is also important to include the ‘how’, ‘where’ and ‘who’ is doing the ‘what’.
Measurable : Has the capacity to be counted, observed, analyzed, tested, or challenged.
Attainable : Can achieve the performance target accurately and specifies the amount or level of what is to be measured in order to meet the result.
Relevant : An indicator is relevant to the extent that it captures or measures a facet of the outcome it is intended to measure.
Time-bound : Should state when it should be measured.
Whenever applicable, indicators should be able to provide disaggregation for different pieces of data
(by sex, age, region, or other relevant variables).
5.1 Monitoring and evaluation: definitions and concepts
11
Notes: Specific : Able to be translated into operational terms, focusing on the ‘who’ and the ‘what’ of the intervention. It is also important to include the ‘how’, ‘where’ and ‘who’ is doing the ‘what’ as it provides the action for the intervention.
Measurable – The indicator must have the capacity to be counted, observed, analyzed, tested, or challenged. If one cannot measure an indicator, then progress cannot be determined.
Attainable – The indicator can achieve the performance target accurately and specifies the amount or level of what is to be measured in order to meet the result.
Relevant – An indicator should be a valid measure of the result or outcome. The indicator should be meaningful and important to the outcome to certify that the results are showing a related impact. An indicator is relevant to the extent that it captures or measures a facet of the outcome it is intended to measure.
Time-bound – The indicator is attached to a timeframe. The indicator should state when it should be measured.
Indicators also whenever applicable should be able to provide disaggregation for different pieces of data (by sex, age, region, or other relevant variables).

## Slide 20: What are indicators?
Indicators are measured at:
  Start of intervention
  After the intervention has had time to produce impact
Indicators measure change over time & are used for decision making
Indicators can be:
    Number
    Ratio
    Percentage
    Average
    Rate
    Index (composite of indicators)

## Slide 21: Types of indicators
Type of the indicator | Definition
Input | Human and financial resources, physical facilities, equipment, and operational policies that enable services to be delivered. Example: Epidemiologist working in the Rapid Response Team.
Process | Multiple activities that are carried out to achieve the objectives of the program. It includes both what is done and how well it is done. Example: Number of trainings conducted to improve the overall knowledge scores of RRT.
Output | The results of these efforts at the programme level. Example: Percentage of the RRT that are trained on M&E.
Outcome | Higher level indicators that measure the change that happened at the target population level. Example: Survival rate in the affected communities.
Impact | The systemic changes achieved that can be attributed to the programme. These reflect long-term outcomes. Example: Average death rate by outbreak in the affected communities
5.1 Monitoring and evaluation: definitions and concepts
12

## Slide 22: Why are indicators important?
Indicators enable us to reduce a large amount of data to its simplest form
Indicators are used for decision making
            Are corrective measures needed?
            Do we need to change program activities?
            Are we reaching the target population?

## Slide 23: Indicators are critical for decision making
Relevant
Related to a specific question or issue or concern
Sensitive to changes of the conditions
Give an early warning of pending changes
Scientifically sound
Unbiased, representative of the conditions in question
Scientifically credible & reliable
Based on the best available data
Robust & unaffected by minor changes in the method/scale
Consistent & comparable over time & space
Applicable to users
Relevant to policy-makers & management needs
Easily understood & applied by potential users

## Slide 24: No indicator is perfect!
Qualities of good indicators:
Action focused – know what you will do with the data
Important – a key component of the theory of change
Quantifiable – measurable
Specific – not vague
Standardized – allow for comparisons over time
Simple

## Slide 25: How many indicators?
The minimum number to know if the outcome has been achieved
At least one or two indicators per result
At least one indicator for every core activity
No more than 8-10 indicators per area of significant program focus
Use a mix of data collection strategies/sources to triangulate
Must balance between too many indicators & enough information

## Slide 26
5.2 RRT M&E in preparedness and response phases
16
Notes: Paula

## Slide 27
At the end of this session, you will be able to:
Recall the objectives of monitoring and evaluation of RRT programme during preparedness and response phases.
Describe key features of RRT monitoring and evaluation of RRT programme during preparedness and response phases
Identify tools for RRT monitoring and evaluation of RRT programme during preparedness and response phases
Identify RRT programme M&E challenges and how to mitigate them
Session objectives
4

## Slide 28: Goals of RRT programme M&E
The main goals of monitoring and evaluation are to:
Identify successes as well as issues that occurred during all phases of a response.
Track internal programme activities as well as the RRT’s impact related to emergency response readiness, deployment activities, and the outbreak itself.
Help leadership understand the value of RRT capacity, its impact, and the cost-benefit of continuous funding/support.
Maximize response efficiency and effectiveness by improving response plans, processes, and training for future responses.
5.2 RRT M&E in preparedness and response phases
14

## Slide 29: Objectives of RRT programme M&E
The M&E of RRT programme aims to :
Identify problems early
Ensure resources are used efficiently
Help the team learn from their mistakes
Improve decision-making
Help the team replicate the best practices
Use the data for decision making, such as determining if an activity should be continued, stopped, or modified to achieve better results
Create opportunities for learning, such as during the quarterly data analysis process where best practices, success stories, and successful approaches can be documented
Report to the donor/leadership to ensure accountability and sustainability
Inform the communities to gain their trust and help engage them
5.2 RRT M&E in preparedness and response phases
15

## Slide 30: Preparedness phase monitoring and evaluation
Note that:
Tracking preparedness phase operations documents the true capacity of the RRT programme to respond.
Databases to capture this information include: the roster, training tracking database (can also be included in the roster), and a database of the application data for future reference.
Dashboards that display the status of members’ readiness requirements and availability will allow for a more efficient and effective way to identify the most appropriate responders for a deployment.
5.2 RRT M&E in preparedness and response phases
17

## Slide 31
The monitoring and evaluation system should enable to collect the information needed for:
Reporting requirements for the programme/leadership.
Reporting requirements for funding the programme.
Example of dashboard to track RRTs activities
Preparedness phase monitoring and evaluation
5.2 RRT M&E in preparedness and response phases
18

## Slide 32: Potential M&E data to track for Response phase
Elements to track can include:
Imminent, current, completed deployments
Location, duration, types of outbreaks/public health events, who responded, re- deployments
Timeliness of RRT response
Activity specific indicators (i.e., number of healthcare workers trained).
Consider reporting for partners that highlight their agency’s contribution to the national emergency response.
5.2 RRT M&E in preparedness and response phases
19

## Slide 33
Potential M&E data to track for Response phase
5.2 RRT M&E key performance indicators

## Slide 34: Potential M&E databases
Potential M&E databases include:
Request tracker (e.g., emergency assistance, emergency type, request status, etc.)
Deployment tracker (e.g., who deployed, for what emergency, etc.), and;
Post-response database (response issues and the corresponding updates/changes to the SOP(s), processes and operations, etc.).
5.2 RRT M&E in preparedness and response phases
20

## Slide 35: RRT operations and performance monitoring and evaluation (1)
Develop Key Performance Indicators (KPI) to evaluate RRTs capacity in country, including:
      Workforce, including RRT organization, roster system, number of teams/ members at national and subnational, retention, skill status (trainings and deployments)​
      Availability of SOPs and protocols
      Financial support of RRTs
      Logistic support of RRT operations
      Timeliness of verification, deployment and initiating response​
      Completeness of emergency response (documentation and reporting)​
      Interventional response such as Risk Communication and Community Engagement
      Monitoring and evaluation: mechanism, post deployment assessment meeting​.
5.2 RRT M&E in preparedness and response phases
21

## Slide 36: RRT operations and performance monitoring and evaluation (2)
Ensure monitoring and evaluation to :
      Provide information about current emergency response capacity for decision-makers.
      Identify gaps, address challenges, and plan for improving the capacity to respond.
5.2 RRT M&E in preparedness and response phases
22
      M&E for continuous programme improvement!

## Slide 37: Common M&E challenges
M&E Challenges
Lack of capacity
Educate stakeholders & decision makers on value of M&E
Conduct M&E trainings; Identify SMEs
Identify alternative data sources; Digitalize data collection
Lack of quality data
Stakeholders don’t want to know the true impact
Prioritization of other activities
Lack of funding
Mitigation Strategies

## Slide 38: Common M&E challenges
M&E Challenges in Emergencies
Mitigation Strategies
Need data fast
Prioritize groups, locations, variables
Data from other similar contexts; retrospective approach
Interagency meetings & clear division of responsibilities
Planning; Assess historical data; Use standard data collection tools (when appropriate)
Lack of baseline data
Balance precision & accuracy
Lack of coordination across agencies
Difficult to identify key groups & variables before information collected
Prioritize accuracy over precision

## Slide 39: Common M&E challenges
M&E Challenges in Emergencies
Mitigation Strategies
Collecting data that is informative and timely
Link M&E data to planning
Develop a continuous quality improvement process
Develop a data reporting plan and key dissemination outlets
Refine current metrics to only include those that answer the program’s evaluation questions
Convert data/findings to action
Need for sharing of lessons learned and best practices
Burdensome data collection and reporting processes

## Slide 40: Challenges of RRT programme M&E
Challenges encountered for the monitoring and evaluation of the RRT programme may include:
Complexity determining which indicators and measures are most appropriate to effectively assess RRT programme performance, as this M&E covers multidimensional aspects (response effectiveness, coordination, training, etc.).
Difficulty to attribute outcomes and impact of the RRT programme solely to the performance of RRTs, other external factors can influence them ( e.g.: the nature of the public health event itself, the health infrastructure, etc.).
Limited resources including staff, time and funding, which may result in limited data collection and analysis.
Difficulty in ensuring the quality and availability of relevant data for M&E.
Evaluating the sustainability and long-term impact of RRT programmes can be challenging, as it may take time to observe and measure changes in response capacity.
Building a culture of data-driven decision-making and ensuring stakeholder buy-in can be challenging.
5.2 RRT M&E in preparedness and response phases
15

## Slide 41: Mitigation of RRT programme M&E challenges
Mitigating these challenges requires in particular:
Careful planning.
Resource allocation.
Collaboration among involved stakeholders, training and effective communication.
Accurate choice of evaluation methods and key performance indicators.
5.2 RRT M&E in preparedness and response phases
15

## Slide 42
5.3 RRT M&E key performance indicators
16
Notes: Paula

## Slide 43
At the end of this session, you will be able to:
Understand the link between RRT programme and JEE/SPAR indicators and 7-1-7 metrics
Describe the RRT programme KPIs
Session objectives
4

## Slide 44
The KPIs developed as part of the M&E of the RRT Programme are consistent with:
5.3 RRT M&E key performance indicators
7-1-7 timlieness metrics ​
and milestones
Global Indicators
(JEE and SPAR)

## Slide 45
P.1.2 Gender Equality in Health Emergencies
P.2.2 Financial Resources for Public Health Emergency Response
P.3.2 Multisectoral Coordination Mechanisms
P.3.3 Strategic Planning for IHR, Preparedness, or Health Security
P.5.2 Response to Zoonotic Diseases
P.6.1 Surveillance of foodborne diseases and contamination
5.3 RRT M&E key performance indicators
RRT KPI & Global Indicators ​(JEE and SPAR)​
PREVENT
DETECT
RESPOND
PoE
The establishment of an RRT programme helps to improve the indicators used in SPAR and the JEE:
D2.2. Event verification and investigation
D2.3. Analysis and information sharing
D.3.1 Multisectoral Workforce Strategy
D.3.2 Human Resources for Implementation of IHR
D.3.3 Workforce Training
D.3.4 Workforce Surge during a Public Health Event
R.1.1 Emergency Risk Assessment and Readiness
R.1.4 Activation and Coordination of Health Personnel and Teams in Public Health Emergency
R.1.6 Research, Development and Innovation
R.2.1 Public health and security authorities are linked during a suspect or confirmed biological, chemical or radiological event
R.5.1 Risk Communication and Community Engagement System for Emergencies
PoE2. Public health response at PoEs
Notes: RRTs are involved directly or indirectly on these indicators

## Slide 46
The 7-1-7 approach includes three timeliness metrics and targets that RRTs should achieve:
  Time to Detect: 7 days to identify a suspected public health threat (time between emergence of a public health threat and detection)
  Time to Notify: 1 day to inform the appropriate public health authorities (time between detection and notification)
  Time to Complete Early Response: 7 days to initiate an effective response (time between notification and early response completion)
RRT KPI & 7-1-7 timlieness metrics and milestones
5.3 RRT M&E key performance indicators

## Slide 47
RRT KPI & 7-1-7 timlieness metrics and milestones
Source: https://717alliance.org/app/uploads/2023/04/High-level-stakeholder-presentation-v3-04-April-2023.pptx
5.3 RRT M&E key performance indicators

## Slide 48
A systematic monitoring and evaluation system of the RRT programme should be put in place to identify successes as well as issues that occurred during all steps of a response, with the ultimate goal of maximazing response efficiency and effectiveness.
Key Performance Indicators (KPI) should be developed and adapted to country context to monitor RRT activities and performance.
Good RRT programme M&E planning, resources allocation and involvement of key stakeholders could reduce the main challenges.

## Slide 49
Health Indicators: Building Blocks for Health Analysis, PAHO, Epidemiological Bulletin, Vol. 22 No. 4, December 2001
https://www3.paho.org/english/dd/ais/eb_v22n4.pdf
Social and Behavior Change Communication for Emergency Preparedness Implementation Kit, Johns Hopkins University, 2020
https://sbccimplementationkits.org/sbcc-in-emergencies/lessons/unit-9-monitoring-and-evaluation/
Guidance for U.S. Centers for Disease Control and Prevention Staff for the Establishment and Management of Public Health Rapid Response Teams for Disease Outbreaks, CDC, 2020
https://www.cdc.gov/coronavirus/2019-ncov/downloads/global-covid-19/RRTManagementGuidance-508.pdf
7-1-7 Implementation Toolkit, Resolve To Save Lives, 2021
https://717alliance.org/digital-toolkit/
Fundamentals for the Rapid Response Team Monitoring & Evaluation Guideline, WHO EMRO
Under development

## Slide 50
​Management and Facilitation of an After-Action Review (AAR), WHO HSLP​
https://extranet.who.int/hslp/training/enrol/index.php?id=131 ​
​
WHO After Action Reviews (AAR) VIDEO​
https://www.youtube.com/watch?v=l61dcs45HDI&t=59s

## Slide 51
U.S. CDC disclaimer
This training package was made possible by grant/cooperative agreement number GH0002225-03 from the U.S. Centers for Disease Control and Prevention. Its contents do not necessarily reflect the official policies of the Department of Health and Human Services nor does mention of trade names, commercial practices, or organizations imply endorsement by the U.S. Government.

## Slide 52
WHO Health Security Learning Platform - Training Materials
These WHO Training Materials are © World Health Organization (WHO) 2022. All rights reserved.
Your use of these materials is subject to the “WHO Health Security Learning Platform, Training Materials – Terms of Use”, which you accepted when downloading them and which are available on the Health Security Learning Platform at: https://extranet.who.int/hslp
Should you adapt, modify, translate, or in any other way revise the contents of these materials, you shall not imply that WHO is any way affiliated with such modifications and shall not use the WHO name or emblem in such modified materials.
Should you adapt, modify, translate, or in any other way revise the contents of these materials, you shall acknowledge the source of the material providing the following attribution: “These training materials are a modified version of the Rapid Response Teams Manager Face-to-Face package (available at: https://extranet.who.int/hslp/, which is © the World Health Organization (WHO), 2022, and used with permission from WHO. WHO disclaims any responsibility for any modifications to, or revisions of, the WHO copyrighted materials.”
Further, please inform WHO of any modifications of these materials that you use publicly, for record-keeping purposes and continued development, by emailing ihrhrt@who.int