## Slide 1: Rapid Response Teams Managers Workshop
Venue, country, dates
Welcome!
Country logo/flag
Speaker name

## Slide 2
The content of this module is to be adapted to your final RRT Managers Workshop agenda and specific needs in the country where the workshop is held.
Areas to be reviewed/completed by RRT MW organizers/facilitators are highlighted in yellow.
Note to facilitators

## Slide 3
Module 4
SOPs for RRT management
in response phase

## Slide 4
At the end of this module, you should be able to:
Develop/adapt SOP for RRT activation and pre-deployment
Develop/adapt SOP for deployment of RRTs
Develop/adapt SOP for post-deployment of RRTs
Module objectives

## Slide 5
4.1 RRT activation and pre-deployment
4.2 Group activity: RRT activation and pre-deployment SOP
4.3 RRT deployment
4.4 Group activity: RRT deployment SOP
4.5 RRT post-deployment
4.6 Group activity: RRT post-deployment SOP
Outline

## Slide 6
4.1 RRT activation and pre-deployment

## Slide 7
Session objectives
At the end of this session, you should be able to:
List RRT activation criteria and describe its process
Describe the pre-deployment process

## Slide 8: RRT management cycle
Communication & Reporting Monitoring & Evaluation Team Evolution & Demobilization
h
Reminder
The main activities during preparedness and response phases are as follows:

## Slide 9: Welcome to Makati!
With your technical guidance, the Ministry of Health in Makati has established their new national rapid response team programme – woohoo!

## Slide 10: But wait…
Days of consistent heavy rain have caused flooding along the coast and in parts of the capital, Mondo City. Many along the coast have fled rising floodwaters and damaged housing to seek shelter in Mondo City.
Mondo City hospital has reported 6 patients with vomiting, diarrhea, and dehydration. Three ought initial treatment from a local healer. One patient, a 25-year-old man, has died.
How will you activate your RRT?
Hurricane Dorin!

## Slide 11: RRT management cycle
Communication & Reporting
Monitoring & Evaluation
Team Evolution & Demobilization
h
4.1 RRT activation and pre-deployment

## Slide 12: Reflection
What alerts have the RRT responded to?
What led to the activation of the RRT?
What was the decision-making process/mechanism by which the RRT was activated?
Plenary discussion
Country
logo/flag
Notes: Identify a rapporteur/note taker and time keeper
1: Which PHE
2: Severity od the disease/event; Size of an outbreak; Media attention; Political will...
3: Activation process

## Slide 13: Goals of RRT activation
Maximize response efficiency by reducing time needed for activation processes.
Maximize response efficiency by identifying appropriate team composition, minimizing the human resources used by strategically selecting staff.
Maximize response effectiveness by selecting staff with
the skills to effectively address the response needs.
RRT activation enables to:
4.1 RRT activation and pre-deployment

## Slide 14: RRT activation process
An RRT can be activated:
Upon receipt of an alert and its verification
Or
After Emergency Operations Center* activation
* Or equivalent
4.1 RRT activation and pre-deployment
Notes: Key Point: The RRT may be activated with OR without an EOC activation, i.e. it is NOT required to have an EOC activation to activate the RRT (many countries may not even have a fully-functioning EOC yet). The RRT Roster is then used to select deployers depending on the need and pre-deployment processes are completed to prepare deployers for the field. The RRT is then deployed – and it can be team of people or just 1 individual to investigate an event and/or provide technical assistance.

## Slide 15: Decision-making criteria for activation
What decision-making criteria (factors or data) should be considered in the decision to activate the RRT?
Decision-making criteria for RRT activation depends on:
Severity of disease/public health impact
Size of outbreak
Risk of transmission
Location or geography
Local capacity to respond
National capacity to respond
Funds
Media attention/public concern and political will
Leadership decisions.
4.1 RRT activation and pre-deployment
Notes: Facilitator guide:
Ask participants to propose decision-making criteria for RRT activation before showing the slide content.

## Slide 16: Decision-making criteria for activation
Alert Verification
Is the information accurate and from a trusted source?
Emergency Triggers
Is the RRT deployment aligned with national guidelines and/or pre-determined activation triggers?
Public Health Authority or Jurisdiction
Is an invitation or formal request necessary for RRT deployment?
Funding
Are necessary funds and resources avaialble to support the response?
Risk Posed
Disease severity; risk of transmission; scale of the oubreak; local response capacity; national RRT capacity?
The decision-making criteria for RRT activation would ideally be delineated in the RRT activation SOP. Considerations include:
Remember: the RRT activation SOP has to define who is responsible and has the authority to activate the RRT.
4.1 RRT activation and pre-deployment
Notes: when thinking through the different decision making criteria 5 main areas can be considered:
The first is related to the verification of the alert or whether the information we received is accurate and from a trusted source
The second is related to whether or not the RRT deployment is aligned with national (or pre-determined) emergency activation triggers (ex: IDSR)
The third is related to PH authority or jurisdiction meaning that is there an invitation or formal request that is necessary to obtain for an RRT to deploy?
The fourth is related to funding – is there enough $ and resources to support this deployment
Finally, the fifth is related to the risk posed – or the consequences of not deploying

## Slide 17: Team composition
Recommend the RRT composition according to:
What roles should be included?
How many responders in each role?
Does there need to be a team lead?
4.1 RRT activation and pre-deployment

## Slide 18: RRT structures
SINGLE-DISCIPLINE TEAM
MULTI-DISCIPLINE TEAM
Or the RRT structure can be tailored…
Depending on the response needs, the mobilized RRT can be:
4.1 RRT activation and pre-deployment
Notes: Key Points:
•Single-discipline team: all responders have the same role or are focused in the same sector (e.g. case management).
•Multi-discipline team: responders have different areas of expertise. This is useful during initial phases of the outbreak when it may not be clear what the response needs are.

## Slide 19: RRT structure: Tailored to existing capacity
Remember: consider creating a standard template that can be adapted to different contexts.
To compose an RRT:
  Identify response needs and appropriate roles
  Assess local capacity
  Select RRT members to fill gaps
4.1 RRT activation and pre-deployment
Notes: Key Points: 1) Response needs initially identified as requiring the four roles listed. 2) Local capacity can only fully fill the needs for one role, case management. 3) RRT members are selected to fill the gaps in the remaining roles. Thus, RRTs do not lead a response, but rather insert themselves into the ongoing local response that has already begun.

## Slide 20: RRT structure: tailored to need
Roles:
Example
structures:
4.1 RRT activation and pre-deployment
Notes: Here we have additional tailored RRT structures of the 7 roles listed based on different scenarios:
First, on the left, If the request is skill and role specific as this first example asks for support in staffing a mobile lab, then a small, single discipline team can be deployed
Second, If there is not much known about the event in question, such as the example in the middle with a suspected outbreak in a health facility, we can deploy a multi-disciplinary team to investigate
Finally, If the need is specific to a response challenge, such as the example on the right where rumors in a community are hindering contact tracing efforts, we can deploy a tailored team, in this case, a rumor management team

## Slide 21: RRT structure: tailored to need
  An alternative approach is to :
  Pre-select a multidisciplinary team to deploy to emergencies regardless of the disease or response context : “Go teams”
  Once in the field, the pre-determined RRT members can assess the response needs: other RRT members can join the team and others who are not needed can be rapidly demobilized.
If safety and/or security are an issue, consider the inclusion of a safety/security officer on the RRT.
4.1 RRT activation and pre-deployment

## Slide 22: RRT management cycle
4.1 RRT activation and pre-deployment
Communication & Reporting Monitoring & Evaluation Team Evolution & Demobilization
h

## Slide 23: Goals of pre-deployment
The pre-deployment enables to:
Maximize response efficiency by standardizing processes in preparation for RRT member deployment.
Maximize response effectiveness by providing RRT members with information, equipment, and supplies necessary to respond appropriately to the specific emergency.
4.1 RRT activation and pre-deployment

## Slide 24: Pre-deployment processes
  Pre-deployment processes include:
  Equipment
  Travel and lodging arrangements
  Funds/advances
  Administrative paperwork
  Others?
4.1 RRT activation and pre-deployment
Notes: Pre-deployment processes are the technical and operational activities an RRT needs to get done before deployment

## Slide 25: Other pre-deployment activities
Pre-deployment activities also include:
Pre-deployment briefing
  Provide situational awareness before going to the field
Just-in-time training
  Mission-specific technical training
  Can also be role-specific
4.1 RRT activation and pre-deployment
Notes: In addition to the processes listed in the last slide, we should also consider providing a
pre-deployment briefing: The purpose of the pre-deployment briefing is to provide situational awareness to the deploying RRT members including the latest information on the current outbreak.
JIT: Just-in-time training provides technical information and content, such as biological and epidemiologic characteristics of the disease of concern as well as role-specific pertinent information for the particular disease.
Both the pre-deployment briefing and just-in-time training can be provided in person, over the phone, or as reference materials to be reviewed while en route to the field

## Slide 26: Pre-deployment briefing: operational considerations
A pre-deployment briefing enables to:
Provide situational awareness on evolving response
Provide latest information available regarding particular health emergency
Address concerns RRT members may have about the present emergency
Maximize RRT responder effectiveness and safety in the field.
4.1 RRT activation and pre-deployment
Notes: Key Points:
The purpose of the pre-deployment briefing is to provide situational awareness including the latest information on the outbreak and response to deploying RRT members so that they can be effective and safe in the field.
Logistics:
•Often occurs in person as an opportunity to provide equipment to RRT members
•May be done remotely
•Include skills lab for donning and doffing personal protective equipment

## Slide 27: Pre-deployment briefing: content
Latest surveillance data/situation report
Handover notes/reports from returning responders
Clear, well-defined objectives for response activities
Reporting mechanisms, format, and frequency
Relevant indicators/metrics
Current safety and security situation, including emergency evacuation plans.
Arrival logistics and lodging details
Field points of contact or other responders
A pre-deployment briefing should touch on the following:
4.1 RRT activation and pre-deployment
Notes: Challenges to consider:
•At the beginning of a response, reliable information can be scarce. How should RRT members be prepared in this situation?

## Slide 28: Just-in-time training: operational considerations
To be considered for just-in-time training:
Relevant training content tailored to context
Facilitators
Subject matter experts
Training location
Required equipment for RRT members
Available local, national, and international guidelines
4.1 RRT activation and pre-deployment
Notes: •Recall: JIT training is one component of a larger RRT training paradigm
Just-in-time training provides technical information and content, such as biological and epidemiologic characteristics of the disease of concern as well as role-specific pertinent information for the particular disease.
Like the pre-deployment briefing, just-in-time training can be provided as reference materials to be reviewed while en route to the field.

## Slide 29: Just-in-time training: content
Content that may be considered for just-in-time training:
Disease/event specific epidemiologic characteristics
Use of standardized tools, such as:
    National response guidelines
    Case investigation forms
    Rapid diagnostic tests
    Environmental testing kits
    Specimen collection, packaging and transport
Other relevant training to function effectively
4.1 RRT activation and pre-deployment

## Slide 30: RRT equipment
RRT members may need certain supplies and equipment to safely meet their objectives while in the field:
Appropriate supplies, specific to the public health event, should be identified and provided before deployment.
Equipment should cover communication, safety (e.g., personal protective equipment) and technical/scientific supplies.
The RRT deployment coordinator can delineate where and how the resources will be available to the team, with a supply distribution plan.
Checklists are useful tools to track supplies and equipment
Supply needs may arise during deployment.
4.1 RRT activation and pre-deployment
Notes: RRT members may need certain supplies and equipment to safely meet their objectives while in the field so appropriate supplies, specific to the disease outbreak, should be identified and provided before deployment.
Checklists are useful tools to track supplies and equipment for both logisticians and deploying RRT members.
Supply needs may arise during deployment so a funding mechanism to cover field costs, such as cash advances to team members and/or credit accounts with local vendors in the field should be considered when possible

## Slide 31
Key messages
    Activation criteria are specific to each RRT, but consider many of the same factors
    RRT activation SOP has to define who is responsible and has the authority to activate the RRT
    RRT pre-deployment processes should be standardized as much as possible and include a pre-deployment briefing and any necessary just-in-time training.

## Slide 32
4.2 Group activity:
RRT activation and pre-deployment SOP

## Slide 33
Instruction to facilitator: Please insert here the summary of the brainstorming session related to the station 6. RRT activation and pre-deployment in Group activity 1.2:
Brainstorming session: the country RRT experience
62
Brainstorming session summary

## Slide 34: Instructions for group work
  Draft a SOP for RRT activation and pre-deployment using :
          The SOP template,
          The summary of brainstorming station 6. RRT activation and pre-deployment
          The summary of plenary discussion on RRT activation and pre-deployment
          Questions on annex 8
  Groups 1, 2, 3 Activation SOP
          Criteria for activation of the RRT
          Authorization process for activating the RRT
          Process for expedition of decision making
          Team composition and structure / Criteria for inclusion of security officer
4.2 Group activity: RRT activation and pre-deployment SOP ​

## Slide 35: Instructions for group work
        Groups 4, 5, 6 Pre-deployment SOP
          Pre-deployment processes – team, finance, logistics, admin
          Identified content, format, responsibility for pre-deployment briefings
          Just-in-time training facilitation, repository, and distribution assigned
          Availability, distribution and funding for RRT equipment and supplies
    Each group will assign a rapporteur to present in plenary the outcomes of the group discussion.
    Duration: 45’ group work; 15’ presentations
    Output: SOP for RRT activation and pre-deployment adapted to your country context
4.2 Group activity: RRT activation and pre-deployment SOP ​

## Slide 36: Additional optional activity: Activate or not the RRT?
    You will be given scenarios.
    Using decision-making criteria for RRT activation, determine whether or not to activate the RRT
    You can also create a flow chart showing how you reached your decision.
    Each group will assign a rapporteur to present in plenary the outcomes of the group work/discussion.
    Duration: 45’ group work; 15’ presentations
    Output: Decision made as to whether or not to activate the RRT
4.2 Group activity: RRT activation and pre-deployment SOP ​
Instructions for group work

## Slide 37: Additional optional activity: Activate or not the RRT? (1)
It’s flu season and a newspaper has published that there are more cases of seasonal flu and deaths than usual, and that the occupancy rate of intensive care beds exceeds 95%. You contact the head of epidemiological surveillance who confirms that the number of cases and deaths are even below the thresholds recorded during each season and sends you the surveillance report which confirms that the type B influenza virus circulates practically alone during this season. You contact the provincial hospital manager who confirms that only 8% of intensive care beds are occupied by patients, only one of whom is 98 years old in respiratory distress due to lung metastases.
Will you activate the RRT?
4.2 Group activity: RRT activation and pre-deployment SOP ​
Mini scenario 1

## Slide 38: Additional optional activity: Activate or not the RRT? (2)
The information has been verified.
What was reported by the newspaper is a rumor!
You will not activate the RRT!
4.2 Group activity: RRT activation and pre-deployment SOP ​
Mini scenario 1 - debriefing

## Slide 39: Additional optional activity: Activate or not the RRT? (3)
Nine participants in a religious ceremony presented with headache, fever, photophobia, vomiting and 3 others were admitted to hospital for a disorder of consciousness and purpura, one of whom died.
Will you activate the RRT?
4.2 Group activity: RRT activation and pre-deployment SOP ​
Mini scenario 2

## Slide 40: Additional optional activity: Activate or not the RRT? (4)
12 cases
3 admitted to the hospital for a disorder of consciousness and purpura
1 death
4.2 Group activity: RRT activation and pre-deployment SOP ​
Mini scenario 2-debriefing
Severe disease
Risk of transmission/ exposure to the same source
You should activate the RRT!
Notes: Decision-making criteria for RRT activation depends on:
Severity of disease/public health impact
Size of outbreak
Risk of transmission
Location or geography
Local capacity to respond
National capacity to respond
Funds
Media attention/public concern and political will
Leadership decisions.

## Slide 41: Additional optional activity: Activate or not the RRT? (5)
Matulidji country is about to declare the end of the Ebola virus disease outbreak on its national territory. You receive a notification from CAPITAL Hospital in your country concerning a health professional coming from Matulidji who presented two days after his return bloody vomiting and diarrhea, with epistaxis and fever without other similar cases in his entourage. The information quickly circulated in social networks and the media, which are starting to exert pressure!
Will you activate the RRT?
4.2 Group activity: RRT activation and pre-deployment SOP ​
Mini scenario 3

## Slide 42: Additional optional activity: Activate or not the RRT? (6)
Suspected case of Ebola virus disease
Severe disease+++
Transmission+++
Pressure social networks and the media
        You should activate the RRT!
4.2 Group activity: RRT activation and pre-deployment SOP ​
Mini scenario 3-debriefing
Notes: Decision-making criteria for RRT activation depends on:
Severity of disease/public health impact
Size of outbreak
Risk of transmission
Location or geography
Local capacity to respond
National capacity to respond
Funds
Media attention/public concern and political will
Leadership decisions.
Decision-making criteria for RRT activation depends on:
Severity of disease/public health impact
Size of outbreak
Risk of transmission
Location or geography
Local capacity to respond
National capacity to respond
Funds
Media attention/public concern and political will
Leadership decisions.

## Slide 43
You’ve successfully deployed your RRT!
Woohoo!
But wait… there is more to do!

## Slide 44
4.3 RRT deployment

## Slide 45
Session objectives
At the end of this session, you should be able to:
Describe RRT coordination in the field and with headquarters during a response
Discuss reporting requirements and monitoring of RRT activities during deployment

## Slide 46: RRT management cycle
4.3 RRT deployment
Communication & Reporting Monitoring & Evaluation Team Evolution & Demobilization
h

## Slide 47: Goals of deployment
Maximize response efficiency by reducing duplication of response efforts through coordination with the EOC and response partners.
Maximize response effectiveness by monitoring the emergency status and response activities to ensure response efforts are making an impact.
Maximize response effectiveness by modifying team composition and structure to effectively address evolving response needs.
4.3 RRT deployment

## Slide 48: RRT coordination and reporting
Contributing to coordination; and
Clear reporting mechanisms and expectations
Facilitate effective communication:
  Within the team
  With RRT management and the emergency coordination unit.
4.3 RRT deployment
Notes: Key Point: Coordination is a common problem during emergencies. Many types of coordination may need to occur for an effective response.

## Slide 49: Coordination in the field
To be considered:
Jurisdiction and public health laws
Partners and key stakeholders
  Local/subnational
  National
  International
Cross-border
Information sharing
4.3 RRT deployment
Notes: Key Point: This figure is meant to show the breadth and complexity of coordination that is often required in a response (especially larger ones with international partners). In terms of the RRT, consider:
•Who is responsible for communicating and coordinating with responders across the border? People in the field? EOC?
•What other modules or organizations must become involved?

## Slide 50: Reporting from the field
You’ve Got mail!
4.3 RRT deployment

## Slide 51: Reporting from the field
What information does the RRT manager and ECU/EOC need to get?
4.3 RRT deployment
Notes: Key Points:
•Status of the emergency – what is happening? Where? Who is affected? Etc.
•RRT activities – are the RRT members meeting their objectives?
•RRT needs – do the RRT members need anything else to meet their objectives? E.g. supplies, additional manpower, subject matter expertise, etc.

## Slide 52: Reporting from the field
Should be reported from the field to the RRT team leader:
Outbreak Data
Activities/interventions
Challenges
Stakeholder coordination
RRT Needs
  Transportation
  Equipment
  Staffing
RRT safety and security
4.3 RRT deployment
The RRT team leader compiles the data and writes a report for the RRT manager
Notes: Key Points:
Consider these things as topics that need to be conveyed to the next level of leadership within the hierarchy.
Can vary from multiple times per day to once per week or less; depends on the situation and the communication and coordination needs for the response
Discuss the balance between time spent developing reports (compiling data, writing summaries, etc.) and time spent doing other response activities (case investigations, IPC evaluations of healthcare facilities, data analysis, etc.)
How can the format of the reporting address this balance? What are the advantages and disadvantages of different reporting formats? E.g.: Text messaging (SMS) very brief bulleted updates: takes little time for responders; however, limits the amount of information sent to EOC/RRT Manager; Situation reports or other comprehensive reports: may take a great amount of time from response work (depends on the RRT responsibilities and amount of information they must compile), but provides EOC/RRT Manager with much more information
Key Point: It can take a lot of time to pull together a report, depending on the amount of information and processing. A balance must be achieved between the amount of time available to focus on response activities vs. the amount of time spent writing reports.
Consider what information is “nice to know” vs. “need to know” to ensure the necessary information is being
reported without overburdening the responder and taking time away from his/her other response activities. Consider also variety in the report frequency and formats: E.g. report 3-5 bulleted updates for the team every day, and a 2-3 page detailed report once per week.

## Slide 53: Reporting from the field
Remember, RRT reporting protocols should outline :
Who provides the information
For example, RRT members to RRT team leader to RRT management.
What's content to include in the report
Daily activities, accomplishments, challenges, next steps, Staffing /resource needs, and response/ disease-specific indicators
When to report (time of day) and frequency
Early in a response may require multiple briefings per day, whereas weekly reporting may be sufficient in later stages of response.
How or methods of reporting
Common methods include telephone, short message service (SMS), email and writing reports. Contingency plans are useful when the usual means of communication may be disrupted.
4.3 RRT deployment
Notes: Clear reporting mechanisms and expectations can facilitate effective communication within the team as well as with RRT management and the emergency coordination unit.
RRT reporting protocols should outline who on the RRT will provide the information, what critical information elements are included in the report, when to report, and how to report
key components of an RRT reporting protocol is delineating who, what, when, and how.

## Slide 54
Unique Deployment ID (auto generated) | Responder Name | Responder ID | Response Event Name | EOC Activated | Deployment City | Deployment State/ Country | Emergency Type | Trip Description | Deployment Role | Role Title | Leadership Role_yn | Deployment Start Date | Proposed Deployment End Date | Actual Deployment End Date | On-Call | #DaysDeployed | Cost
XXXXXX | XXXXX YYYYY | abc1 | COVID-19 | Yes | EOC | NA | Disease Related | To provide operations support to the current COVID-19 response in the CDC EOC. | Logistics | Operations Lead | Yes | 10/6/2020 | 10/20/2020 | 11/1/2020 | No | 25 | $$$
XXXXXX | VVVV ZZZZZZ | def8 | EVD | Yes | City1 | Country1 | Disease Related | To support the 2018 Ebola Response in the role of Health Communications. | Health Communications | Health Communications | No | 1/27/2020 | 2/27/2020 | 2/27/2020 | Yes | 31 | $$$
XXXXXX | AAAAA BBBB | xyz2 | Cholera | No | City4 | Country4 | Disease Related | To deploy as a Laboratorian in support of the Cholera outbreak. | Laboratorian | Laboratorian | No | 1/3/2018 | 1/28/2018 | 1/29/2018 | No | 26 | $$$
XXXXXX | CCCC DDDD | qrs1 | Cholera | No | City5 | Country5 | Disease Related | Providing emergency support to ministry of health to plan for cholera outbreaks in the upcoming religious mass gatherings. | Epidemiologist | Epidemiologist | No | 7/31/2017 | 8/18/2017 | 8/18/2017 | Yes | 18 | $$$
4.3 RRT deployment
Note: a tracker for RRT deployment must be set up if the country roster does not collect this information!

## Slide 55: Extra, extra!
4.3 RRT deployment

## Slide 56: RRT evolution and demobilization
Generalist demobilized
RRT members deployed
initially
Response needs identified and expertise requested
Additional expertise requested
Additional expertise available by phone/email
Expert deployed
As the response progresses, the technical support required from the RRT will evolve.
4.3 RRT deployment
Notes: Key Point: It’s likely that the composition of the RRT will evolve throughout the response from the initial deployment, due to a variety of potential factors, including the changing needs of the response.
The flexible, modular design of the RRT is intended to allow for rapid adjustments to these changes.
Individual responders can be deployed (added) and demobilized (removed), from the field as dictated by the response needs.
Shown is one example of how the RRT composition may change due to specific expertise required.
Additional consideration of RRT evolution is needed to balance the negative consequences of rapid turnover while ensuring team members are still performing and maintaining their mental health and wellbeing.

## Slide 57: Potential criteria to be considered for RRT members deployment or demobilization are:
Response Evolution
Established Criteria
Duration
Funding
Skills
Effectiveness
Conduct
RRT evolution and demobilization
4.3 RRT deployment
Notes: Potential criteria for Demobilization:
•Response evolution: Use monitoring data from the field to determine when changes to the RRT composition are needed
•Established Activation criteria: Consider whether any of the activation criteria can be used
•Length of time in the field: What is a reasonable length of time?
•Funds: Are there sufficient funds to pay for the mobilization?
•Need for the RRT member’s skills: Is there enough work/need to keep the RRT member busy?
•Effectiveness: How productive is the RRT member?
•Conduct: Are there any behavioral or ethical concerns with the RRT member?

## Slide 58
A handoff report, written by demobilizing RRT members for arriving teammates, can ease the maintain continuity of the response.
Handoff report should include (at minimum):
  Key stakeholders and their contact information
  Key meetings (with time and location)
  Overview of the response
  Completed, current, and ongoing response activities and interventions
  Specific gaps identified
  Accomplishments
  Challenges
  Next steps, future plans or arrangements
RRT evolution and demobilization
When possible, demobilizing RRT members should overlap with the arriving RRT members in the field
4.3 RRT deployment

## Slide 59
Key messages
    While in the field, RRTs coordinate with a different other response actors, in addition to headquarters
    RRTs should report regularly to the EOC/ECU on the status of the emergency, their activities, their challenges and their needs

## Slide 60
4.4 Group activity:
RRT deployment SOP

## Slide 61
Instruction to facilitator: please insert here the summary of the brainstorming session related to the station 7. RRT Deployment & 12. RRT communication in Group activity 1.2:
Brainstorming session: the country RRT experience
62
Brainstorming session summary

## Slide 62: Instructions for group work (1)
    Draft an RRT staffing and rostering SOP adapted to your country context using the provided template, key topics for discussion you will be given and taking into consideration the following key elements:
          Established leadership structure responsible for RRT coordination
          Determined frequency and modality of RRT communication and reporting (including standardized RRT deliverables, i.e., mission reports, sitreps)
          Process for monitoring and evaluation of the RRT in staffing and response needs
          Process for RRT travel logistics considering changes during deployment
          Process for team evolution (i.e., standardized handoff, sending RRT staff home, replacing staff)
          Established criteria and process for team demobilization
4.4 Group activity: RRT deployment SOP ​

## Slide 63
    Please fill out the SOP template provided including the following sections:
          Coordination
          Monitoring & Evaluation
          Team Evolution & Demobilization
    Prompts for content are provided in Annex 9 as key topics for discussion
    Each group will assign a rapporteur to present in plenary the outcomes of the group work/discussion
    Duration: 45’ group work; 15’ presentations
    Output: RRT deployment SOP adapted to your country
4.4 Group activity: RRT deployment SOP
Instructions for group work (2)

## Slide 64: Instructions for group work
    X teams will act as RRT members and x teams will act as RRT management teams
    The teams acting as RRT management teams will provide the RRT members with a pre-deployment briefing that includes the necessary situational awareness information
    The RRT members will then need to use this information to create an action plan and report back to the RRT management.
    Each group will assign a rapporteur to present in plenary the outcomes of the group work/discussion
    Duration: 45’ group work; 15’ presentations
    Output: Content of pre-deployment briefing and RRT action plan developed
4.4 Group activity: RRT deployment SOP ​
Additional optional activity: Briefing before deployment

## Slide 65: The RRT has returned from the field…

## Slide 66
4.5 RRT post-deployment

## Slide 67: RRT management cycle
4.5 RRT post deployment
Communication & Reporting Monitoring & Evaluation Team Evolution & Demobilization
h

## Slide 68
Session objectives
At the end of this session, you should be able to:
Recall the post-deployment goal and key activities

## Slide 69: Goals of post-deployment
Post-deployment aims to:
Maximize the health and well-being of returning responders
Maximize response efficiency and effectiveness by identifying:
  What activities functioned well, so they can be continued
  What activities did not function well, so they can be improved
  What gaps exist, so they can be filled.
4.5 RRT post deployment

## Slide 70: Post-deployment key activities
Three key types of activities are strongly recommended in post deployment:
Finalization of residual response activities
Provision of resources for returning responders (i.e., healthcare,
psychosocial support, etc.)
Evaluation and improvement planning.
4.5 RRT post deployment
Notes: RRT management does not end when responders return home! There are still processes that need to take place.
In the post-deployment phase, three key types of activities are strongly recommended:
• The finalization residual or outstanding response activities
• The provision of resources such as healthcare, psycho-social support and others for returning responders
• And evaluation and improvement planning

## Slide 71: Post-deployment: evaluation
In order to make the necessary improvements, an evaluation is required through:
Debrief: held with responders soon after their return from the field, when the memories are fresh.
After Action Review (AAR): conducted after the mission ends with all major actors in the response.
4.5 RRT post deployment
Notes: Key Point: Debriefs should be conducted with each responder when he/she returns home (this can be done in groups or individually). Only one AAR should be done with all major response actors in attendance.

## Slide 72: Post-deployment: evaluation
The following questions should be addressed regarding evaluation:
Will there be a standardized approach?
How will sensitive information be handled?
Where will this be documented?
How will information inform improvements to the RRT programs?
Remember: consider how to formalize the process and store sensitive information over time and across responses.
4.5 RRT post deployment

## Slide 73: Post deployment: debriefs and After-Action Review
What information should be collected during the debriefs and After- Action Review?
Collect data that can be used to improve future response efforts:
    gaps and challenges in response activities
    action plans to address the gaps and challenges
    responsibility for implementing the action plans.
Methods for submitting anonymous feedback should be available for sensitive issues(e.g., an anonymous survey), especially or management and leadership issues.
It is important to identify in advance (i.e., in the SOP) who will compile and analyze data from debriefs and after-action reviews.
4.5 RRT post deployment
Notes: An operational debrief or meeting to discuss the RRT member’s experience should occur immediately or soon after the return of a responder to provide feedback on the RRT response highlighting what worked well and what did not work well before they forget the details of their experience.
The debriefing agenda may focus on gaps and challenges in response activities, action plans to address the gaps and challenges, and assigning responsibility for implementing the action plans.
As we can see in the image on the slide, if multiple RRT members or teams are deployed successively, each responder or group should be debriefed upon their return.
Whenever possible, the debrief for one individual or group should not be delayed while waiting for the return of other responders, which may result in conducting multiple debrief sessions
It’s important to note that methods for submitting anonymous feedback should be available for sensitive issues (for example, an anonymous survey), particularly around management and leadership issues that occurred in the field.
The goal of After Action Reviews is to improve the overall functionality of the RRT during any emergency response and as the image shows, are conducted after the mission ends with all major actors in the response
Overall, RRT management can consider several factors in their evaluation including:
  The timeliness of RRT deployment after surveillance alert was verified
  The quality of pre-deployment activities such as whether the pre-deployment brief was useful, the just-in-time training was appropriate, and the resource distribution matched what the RRT needed
  We can also consider evaluating the quality of response activities by looking at the completion of response indicators Mays talked about during her presentation, by the RRT
  Also, we can look at RRT support mechanisms such as communication and reporting, human resource support, the provision of supplies and equipment, and any support provided by subject matter experts back at HQ
  Finally, any and all RRT challenges should be documented as part of this activity

## Slide 74: Post deployment: debriefs and After-Action Review
What factors should RRT management consider in RRT evaluation? (1)
RRT management can consider several factors including:
Timeliness of RRT deployment after surveillance alert verified
Quality of pre-deployment activities
  Pre-deployment brief utility
  Just-in-time training appropriateness
  Resource distribution matched to RRT needs
Quality of response activities: RRT completion of indicators
4.5 RRT post deployment

## Slide 75: Post deployment: debriefs and After-Action Review
What factors should RRT management consider in RRT evaluation? (2)
RRT support mechanisms
  Communication and reporting
  Human resources
  Supplies and equipment
  Subject matter expertise
RRT challenges
Ideally, RRT management will use the findings (lessons learnt) to modify future trainings and response protocols as needed.
4.5 RRT post deployment

## Slide 76: Post deployment: responder resources
Medical and / or mental health resources should be available for responders upon demobilization.
Administrative support can be offered to returning RRT members :
  Rest days,
  Reducing workload,
  ….
4.5 RRT post deployment
Notes: During an emergency response, responders may encounter a variety of situations including exposure to a disease pathogen or toxin, other medical issues such as illness or injury, traumatic events, or general stressful circumstances due to the chaotic nature and gravity of an emergency.
Returning RRT members may benefit from medical care and/or psychosocial support if available.
Members should be encouraged to identify when they or others may need care or support and providing information on accessing available resources and encouraging team members to seek services as needed can facilitate their transition back to their regular duties and daily life.
Pre-deployment training can introduce some of this information ahead of time; however, these issues should be revisited and additional resources, such as psychosocial support and medical screening, should be provided after returning from a deployment

## Slide 77: Preventing responder attrition
Continuing education opportunities
    Refresher trainings
    Trainings on specific topics
    Trainings on specific emergencies
    Access to trainings/materials
    Mentorship opportunities
    Etc.
Leadership opportunities
Field and headquarters leadership
Leadership specific training:
    Coordinating team members and resources
    Delegating tasks matched to skill sets
    Conducting daily briefings
    Dealing with team conflict
    etc.…
Highlighting responders
    Awards
    Internal communication
    External communication
Responder attrition can be prevented through:
4.5 RRT post deployment

## Slide 78
Key messages
    RRT’s activities should always be evaluated after deployment through a debrief(s) and After-Action Review
    Medical and/or mental health resources should be available for responders upon demobilization
    Evaluation recommendations should be implemented in order to make any necessary improvements

## Slide 79
4.6 Group activity:
RRT post-deployment SOP

## Slide 80
Instruction to facilitator: please insert here the summary of the brainstorming session related to the stations 8. RRT Post-deployment et 10. RRT wellbeing in Group activity 1.2:
Brainstorming session: the country RRT experience
62
Brainstorming session summary

## Slide 81: Instructions for group work (1)
    Draft an RRT staffing and rostering SOP adapted to your country context using the provided template, key topics for discussion you will be given and taking into consideration the following key elements:
          Identified timing, modality and responsibility of post-deployment debriefs
          Responder resources considering physical and mental wellbeing and reintegration
          Process (including responsibility) for improvement planning and action
4.6 Group activity: RRT post-deployment SOP ​

## Slide 82
                Please fill out the SOP template provided including the following sections:
          Evaluation
          Resources for Responders
          Improvement Planning & Action
                Prompts for content are provided in Annex 10 as key topics for discussion
                Each group will assign a rapporteur to present in plenary the outcomes of the group work/discussion
    Duration: 45’ group work; 15’ presentations
    Output: RRT post-deployment SOP adapted to your country
4.6 Group activity: RRT post-deployment SOP
Instructions for group work (2)

## Slide 83
Key messages
    Activation criteria will be specific to each RRT but will consider many of the same factors.
    Pre-deployment processes to prepare and equip responders should be standardized as much as possible and include a pre-deployment briefing and any necessary just-in-time training.
    RRTs will likely need to coordinate with a variety of other response actors, in addition to headquarters, while in the field.
    RRTs should report regularly to the EOC/ECU on the status of the emergency, their activities, and their needs.

## Slide 84: The content of this module was adapted from the RRT management workshop organized by CDC US
Guidance for U.S. Centers for Disease Control and Prevention Staff for the Establishment and Management of Public Health Rapid Response Teams for Disease Outbreaks, U.S. CDC 2020
https://www.cdc.gov/coronavirus/2019-ncov/downloads/global-covid-19/RRTManagementGuidance-508.pdf
Standard Operating Procedures for Coordinating Public Health Prepardness and Response in the WHO African Region. World Health Organization Regional Office for Africa, 2014. https://apps.who.int/iris/bitstream/handle/10665/112855/SOP2014.pdf?sequence=1&isAllowed=y
Greiner, A., Stehling-Ariza, T., Bugli, D., Hoffman, A., Giese, C., Moorhouse, L., Neatherlin, J.C., Shahpar, C. (2020). Challenges in Public Health Rapid Response. Health Security, S8-S13. Retrieved from https://www.liebertpub.com/doi/10.1089/hs.2019.0060
GUIDANCE FOR CONDUCTING A COUNTRY COVID-19 INTRA-ACTION REVIEW (IAR), WHO 2020
https://www.who.int/publications/i/item/WHO-2019-nCoV-Country_IAR-2020.1
Guidance for conducting a country COVID-19 intra-action review (IAR): Addendum 1, Tool 4, WHO 2021
https://www.who.int/publications/i/item/WHO-2019-nCoV-Country-IAR-add.1-2021.1

## Slide 85
Rapid response teams training programme
https://extranet.who.int/hslp/package/rapid-response-teams-training-programme
Rapid response teams managers training package
https://extranet.who.int/hslp/package/block-2-rrt-managers-training-package
Management and Facilitation of a Country COVID-19 Intra-Action Review (IAR)
https://openwho.org/courses/covid-19-intra-action-review-en
Management and Facilitation of an After Action Review (AAR), OpenWHO
https://openwho.org/courses/AAR-en
WHO After Action Reviews (AAR) VIDEO
https://www.youtube.com/watch?v=l61dcs45HDI&t=59s

## Slide 87
U.S. CDC disclaimer
This training package was made possible by grant/cooperative agreement number GH0002225-03 from the U.S. Centers for Disease Control and Prevention. Its contents do not necessarily reflect the official policies of the Department of Health and Human Services nor does mention of trade names, commercial practices, or organizations imply endorsement by the U.S. Government.

## Slide 88
WHO Health Security Learning Platform - Training Materials​
These WHO Training Materials are © World Health Organization (WHO) 2022. All rights reserved.​
Your use of these materials is subject to the “WHO Health Security Learning Platform, Training Materials – Terms of Use”, which you accepted when downloading them and which are available on the Health Security Learning Platform at: https://extranet.who.int/hslp ​
​
Should you adapt, modify, translate, or in any other way revise the contents of these materials, you shall not imply that WHO is any way affiliated with such modifications and shall not use the WHO name or emblem in such modified materials. ​
​
Should you adapt, modify, translate, or in any other way revise the contents of these materials, you shall acknowledge the source of the material providing the following attribution: “These training materials are a modified version of the Rapid Response Teams Managers Training Package (available at: https://extranet.who.int/hslp/), which is © the World Health Organization (WHO), 2022, and used with permission from WHO. WHO disclaims any responsibility for any modifications to, or revisions of, the WHO copyrighted materials.” ​
Further, please inform WHO of any modifications of these materials that you use publicly, for record-keeping purposes and continued development, by emailing ihrhrt@who.int​