## Slide 1: Rapid Response Teams Managers Workshop
Venue, country, dates
Welcome!
Country logo/flag
Speaker name

## Slide 2
The content of this presentation is to be adapted to your final RRT MTP agenda and specifics of your country. Areas to be reviewed/completed by RRT MTP organizers/facilitators are highlighted in yellow.
Note to facilitators

## Slide 3
Module 9
RRT Programme Planning

## Slide 4
At the end of this module, you should be able to:
Define change management and describe pathways to change
Develop a workplan for RRT programme (including administrative aspects, supply and logistics, training, performance evaluation, funding, etc.)​
Review/develop a budget plan covering RRT activities during both preparedness and response phases
Identify next steps to finalize the RRT MW outputs
Module objectives

## Slide 5
Outline
9.1 Change Management
9.2 Planning for RRT programme
9.3 RRT programme workplan development
9.4 RRT programme budget plan development
9.5 Next steps

## Slide 6: 9.1 Change Management

## Slide 7
At the end of this session, you should be able to:
Define change management
Recall common challenges
Describe pathways to change
Session objectives

## Slide 8: Change Management Definition
  Change management is a systematic approach to manage change effectively for transition and transformation of organizational goals, processes or technologies.
Ensuring that the technical results of projects are implemented and used for the purpose they were intended.
Often brings about a new way of doing things.
Considers the effects on the organization.
9.1 Change management
Notes: The definition of change management is a systematic approach to manage change effectively for transition and transformation of organizational goals, processes or technologies. The management change ensure that the technical results of a projects are implemented and used for the purpose they were intended; often brings about a new way of doing things; and considers the effect on the organization

## Slide 9: Is the development of an RRT Programme a form of change? Is the development of a new roster a form of change? Is the identification of an RRT Manager a form of change?
9.1 Change management
Notes: Based on the definition and the background from the recent RRT Management Training, is the development of an RRT program a form of change? Is the development of a new roster a form of change? Is the identification of a RRT manager a form of change?

## Slide 10: Size of Change versus Size of Project
Size of Project | Size of Change
Big Project | Big Change
Big Project | Small Change
Small Project | Small Change
Small Project | Big Change
9.1 Change management
Notes: We could classify all of these items that was aforementioned as a type of project or program. Change occurs when there is a creation or enhancement of systems, replacing of existing solutions, or retiring of programs that require an update based on new technology, international guidelines, or structure. A change can be big or small regardless of the project size. The size of change will help dictate who is engaged, the planning efforts and the implementation pathways.

## Slide 11: Considerations of Change
Structure
Strategy
Operational method
Technology
Organizational culture
9.1 Change management
Notes: What are some areas that would require a change. This may be a new or enhanced structure, strategy, operational method, technology, or large scale such as organizational culture.

## Slide 12: Common Challenges
Funding
Leadership Buy-In
RRT managers retention
Program management and deployment equipment
Technological resources to support roster management
9.1 Change management
Notes: From returning PHEM Fellows- Common Challenges:
Funding​ 75%​
RRT managers retention​ 49%​
Program management and deployment equipment​ 43%​
Technological resources to support roster management​ 43%​

## Slide 13: RRT Programme: How will you implement or change your RRT programme?
9.1 Change management

## Slide 14: Pathways to Change
Identify the need for change
1
Plan for change
2
Implement the change
3
Manage the transition
4
Maintain the change over time
5
9.1 Change management
Notes: We will walk through these five steps when you think about implementing or introducing changes to an RRT programme.
Source: https://online.hbs.edu/blog/post/change-management-process

## Slide 15: Step one: identify the need for changeNeed for Change
Why is an RRT Programme needed in your Ministry of Health?
  What is the contribution it brings to your Ministry of Health
  How will it improve management of coordination of Emergency Response Activities
9.1 Change management
Notes: The first step in this process is to identify the need for change. In order to do this, think about why is the program needed, what is the added benefit and how will it improve existing emergency preparedness and response processes and procedures.

## Slide 16: RRT Programme Benefits
Timeliness
Effectiveness
Cost Savings
Health
9.1 Change management
Notes: Timelines – faster response times which in an outbreak or natural disaster is essential (7-1-7)
Effectiveness – finding the “right” staff with the “right” skills that is needed
Cost Savings – preparedness is cheaper than response – 25-88% ROI - ensures economic resiliency in public health events. And the cost of establishing a RRT is minimal. And this is the most important, the health of the population - with faster and more effective response ultimately mitigating the effects of a public health event on the population– the whole reason we are doing the work we are doing. 6. The World Bank People, pathogens and our planet: the economics of one health. Washington: The World Bank, 2012. http://documents.worldbank.org/curated/en/612341468147856529/People-pathogens-and-our-planet-the-economics-of-one-health [Google Scholar]

## Slide 17: Why is an RRT Programme needed in your Ministry of Health?
9.1 Change management
Notes: The facilitator asks the question: Why is an RRT Programme needed in your Ministry of Health?
In principle, participants will raise the gaps and challenges of the country's MOH which can be resolved by the establishment of an RRT programme.
The facilitator collects answers on a flipchart and moderates the discussion.
Finally, the facilitator provides a summary of the key elements of the discussion.

## Slide 18: What are the benefits that the RRT Programme is expected to generate?
9.1 Change management
Notes: The facilitator asks the question: What are the benefits that the RRT Programme is expected to generate? The facilitator collects the answers on a flipchart and moderates the discussion.
At the end of the discussions, the facilitator will provide a summary specifying that the establishment of an RRT programme will contribute to preparedness and response to health emergencies capacity building as required by the IHR. The RRT programme will allow the availability of multidisciplinary teams trained and equipped for emergency response, with capacity to deploy rapidly, efficiently and effectively to respond to public health emergencies and in coordination with other response efforts.

## Slide 19: Identify the need for change and communicate the need
Brainstorm on how you would communicate your need. And how to sell your RRT programme idea to your leadership in a 30 seconds to 1 minute elevator or sales pitch.
9.1 Change management

## Slide 20: Pathways to Change
Identify the need for change
1
Plan for change
2
Implement the change
3
Manage the transition
4
Maintain the change over time
5
9.1 Change management

## Slide 21: Step Two: Plan for Change
Who do you want to include?
When do you want to include them?
Are there special considerations for various groups?
Identify all your stakeholder both internal and external affected by or interested in the outcomes of the RRT
9.1 Change management
Notes: Once you have communicated the need, you will need to identify all of your stakeholders that are internally or externally affected by the RRT program development or change. Components of this communication strategy include who do you want to include, who do you want to exclude, when do you want to include them,

## Slide 22: Stakeholders Identification
Stakeholders
Identify all your stakeholder both internal and external affected by or interested in the outcomes of the RRT
9.1 Change management
Notes: Ensure those impacted by the RRT see the need for change
Do stakeholders understand that the RRT is necessary to solve a problem or benefit from the opportunity

## Slide 23: Pathways to Change
Identify the need for change
1
Plan for change
2
Implement the change
3
Manage the transition
4
Maintain the change over time
5
9.1 Change management

## Slide 24: Step Three: Implement the Change
Inform stakeholders of the objectives for the change
Understand the barriers and drivers to change, plan for issues, monitor for likely issues and correct for changes
9.1 Change management

## Slide 25: Pathways to Change
Identify the need for change
1
Plan for change
2
Implement the change
3
Manage the transition
4
Maintain the change over time
5
9.1 Change management

## Slide 26: Step Four: Manage the transition
Incorporate changes into the culture and practices of the structure that manages the RRT programme.
New organizational adaptation, controls, and reward systems should all be seen as tools to help changes.
9.1 Change management

## Slide 27: Pathways to Change
Identify the need for change
1
Plan for change
2
Implement the change
3
Manage the transition
4
Maintain the change over time
5
9.1 Change management

## Slide 28: Step Five: Maintain the Change over time
A change initiative put in place does not mean that it has been successful.
Conduct regular analysis and review to better understand results and sustain change based on lessons learned and to guide future change efforts.
9.1 Change management

## Slide 29
9.2 Planning for RRT programme

## Slide 30
At the end of this session, you should be able to:
Describe phases of RRT Programming
Describe the main factors favoring the implementation of a sustainable RRT programme
Describe the main challenges to implement a sustainable RRT programme
Session objectives

## Slide 31
Phased approach* to RRT Programming
Analysis
Design
Development
Implementation
Evaluation
Response Capacity Mapping
RRT Management Training
RRT SOP Development
RRT Training
RRT Programme Review
RRT Staffing and Rostering
RRT Just-in-Time Training
RRT Programme Simulation Exercise
RRT Roster Development
9.2 Introduction to planning for RRT programme
*This approach is the CDC model and has not yet been validated
Notes: Here you can see what the activities are re phased approach to RRT programing. Always begin by conducting a response capacity assessment. Based on what exists or does not exist in country – RRT-Management training and RRT SOP development workshop to equip newly appointed RRT Managers with program considerations and develop the blueprint of the program through the SOPs. Part of sustaining and monitoring the program involved RRT Database development – often this is through the use of open-source platforms like google forms or use of excel. This is then followed by staffing and rostering the program, training newly identified RRT members and after 6 months to a year we can then conduct a program review or simulation exercise to evaluate the efficiency and effectiveness of the program.

## Slide 32
Top factors that support RRT programme implementation
Co-Investigators : M Tejan, C Boutelle, C Corkish, A Hoffman, T Stehling-Ariza, H Lofgren, C Giese, D Bugli, JC Neatherlin, AL Greiner
56 participants
23 countries
9.2 Introduction to planning for RRT programme
Notes: CDC Survey shows that participants (56 participants from 23 countries) noted that the top factors that support RRT program implementation included leadership support and understanding of the importance of RRT programs, having RRT managers and surge staff, funding to support RRT program activities, and well developed SOPs.

## Slide 33
Main challenges for RRT programme implementation
Chart: 
| Funding | RRT managers retention | Program management and deployment equipment
 | 0.7451 | 0.4902 | 0.43137
Co-Investigators : M Tejan, C Boutelle, C Corkish, A Hoffman, T Stehling-Ariza, H Lofgren, C Giese, D Bugli, JC Neatherlin, AL Greiner
56 participants
23 countries
9.2 Introduction to planning for RRT programme
Notes: The top factors that challenge RRT program implementation were lack of funds, inability to retain RRT managers, and lack of equipment for program management and member deployment.

## Slide 34
Top factors that support RRT programme implementation
Staff, roster, and train technically skilled RRT members
Surge Staff
Ensure leadership understands and supports RRT program establishment and implementation
Leadership
Appoint and train RRT management staff on RRT management considerations
RRT Management Staff
Determine and secure funding mechanisms for RRT program establishment and implementation (including management and deployment equipment)
Funding
Develop RRT program preparedness and response phase SOPs
SOP Development
9.2 Introduction to planning for RRT programme
Notes: If we were to summarize this into the 5 factors that must be addressed when establishing and implementing a program they are –
1. Ensure leadership understands and supports RRT program establishment and implementation
2. Appoint and train RRT management staff on RRT management considerations
3. Determine and secure funding mechanisms for RRT program establishment and implementation (including management and deployment equipment)
4. Develop RRT program preparedness and response phase SOPs
5. Staff, roster, and train technically skilled RRT members

## Slide 35
    RRT programme plan is important to ensure efficient RRT management, should be:
    Based on needs assessments and priorities (risk mapping)
    Involve key stakeholders
    Consider available funding
    Regularly evaluated and reviewed
Plan for RRT programme
9.2 Introduction to planning for RRT programme
    To secure the necessary funds for the implementation of the RRT programme plan, the approval of decision makers is highly recommended.

## Slide 36: General Planning Advice
Value commitment, collaboration, and accuracy of information over speed
Strive towards inter-agency planning
Ensure the plan will be used by distributing and practicing it
Stick with what is realistic
Measurable objectives/activities
Revise often (annually, if possible, and/or post-exercise or emergency)
9.2 Introduction to planning for RRT programme

## Slide 37
9.3 Group activity:
RRT programme workplan development

## Slide 38
At the end of this session, you should be able to:
Develop a plan for establishment/consolidation of an RRT programme.
Session objectives

## Slide 39
9.3 Group activity: RRT programme workplan development
    Each group will:
          Define the main goal of the RRT programme workplan in your country
          Develop/adapt the main objectives for RRT programme using the template provided.
    Duration: 90’ group work; 30' presentations
    Each group will assign a rapporteur to present in plenary the outcomes of the group work/discussion.
    Output: A draft of RRT Programme workplan
Instructions for group work

## Slide 40
Standard template for workplan for RRT programme
9.3 Group activity: RRT programme workplan development
Actions | Output | Responsible | Needed resources | Indicator | Date of completion | Anticipated challenges
Objectives 1. ....... |  |  |  |  |  | 
Action 1.1 |  |  |  |  |  | 
Activity 1.1.1 |  |  |  |  |  | 
Activity 1.1.2 |  |  |  |  |  | 
Activity 1.1.3 |  |  |  |  |  | 
Action 1.2 |  |  |  |  |  | 
Activity 1.2.1 |  |  |  |  |  | 
Activity 1.2.2..... |  |  |  |  |  | 
Action 1.3 |  |  |  |  |  | 
Activity 1.3.1.... |  |  |  |  |  | 
Objectives 2. ....... |  |  |  |  |  | 
Action 2.1 |  |  |  |  |  | 
Activity 2.1.1 |  |  |  |  |  | 
Activity 2.1.2 |  |  |  |  |  | 
Activity 2.1.3 |  |  |  |  |  | 
Action 2.2 |  |  |  |  |  | 
A...... |  |  |  |  |  | 

## Slide 41
Goal of the RRT programme workplan
9.3 Group activity: RRT programme workplan development
The RRT programme workplan aims to ensure that RRTs are effectively established, run, tested, and maintained during preparedness phase, and that RRTs are operational according to set procedures during response phase.

## Slide 42
Workplan for RRT programme- Example
9.3 Group activity: RRT programme workplan development
Objective 1: Establish an RRT management team |  |  |  |  |  | 
Actions | Output | Responsible | Needed resources | Indicator | Date of completion | Challenges to be anticipated
Action 1.1 Nominate the RRT management team | RRT management team is nominated | General Secretary of MOH? EOC manager? | Financial resources? Legal resources? | Official nomination signed |  | 
Action 1.2 Train the RRT management team | RRT management team is trained | EOC manager? RRT management lead? |  | # of training completed |  | 
..... |  |  |  |  |  | 
Notes: Hypothesis: the factors that hinder the realization of this action (especially those external ones that do not depend on the RRT management team)
Actions: Strategic actions

## Slide 43
Workplan for RRT programme- Example
9.3 Group activity: RRT programme workplan development
Objective 2: Develop RRT standard operational procedures |  |  |  |  |  | 
Actions | Output | Responsible | Needed resources | Indicator | Date of completion | Challenges to be anticipated
Action 2.1 Make an inventory of available and missing SOPs | Available and missing RRT SOPs are identified | RRT management lead | Financial? Human resources? Legal resources?.... | # of available SOPs |  | 
Action 2.2 Develop priority missing SOPs | Priority missing SOPs are developed | RRT management lead |  | # of Priority SOPs developed |  | 
Action 2.3 Update priority SOPs | Priority SOPs are updated | RRT management lead |  | # of Priority SOPs updated |  | 
Action 2.4..... |  |  |  |  |  | 
….. |  |  |  |  |  | 
Notes: Hypothesis: the factors that hinder the realization of this action (especially those external ones that do not depend on the RRT management team)
Actions: Strategic actions

## Slide 44
9.3 Group activity: RRT programme workplan development
Objective 3: Ensure availability of qualified human resources/ RRT members |  |  |  |  |  | 
Actions | Output | Responsible | Needed resources | Indicator | Date of completion | Challenges to be anticipated
Action 3.1: recruit staff/RRT members according to the set SOP | RRT members are recruited | Deployment/Surge Coordinator | # of members recruited |  |  | 
Action 3.2 Develop/update a roster according to the set SOP | A roster is developed/updated | Roster Manager /Data Analyst | % of missing data in the roster |  |  | 
Action 3.3 Ensure adequate training according to the set SOP | RRT members are trained | Training Specialist/Coordinator | # of RRT members trained |  |  | 
Action 3.4 |  |  |  |  |  | 
Workplan for RRT programme- Example

## Slide 45
9.3 Group activity: RRT programme workplan development
Objective 4: Ensure RRT members readiness |  |  |  |  |  | 
Actions | Output | Responsible | Needed resources | Indicator | Date of completion | Challenges to be anticipated
Action 4.1: Continuously ensure that RRT members meet the health conditions and administrative considerations according to the set SOP | Health conditions and administrative considerations are met | Deployment/Surge Coordinator |  | %of RRT members who met the health conditions and administrative considerations |  | 
Action 4.2 Establish a stock of equipment and logistics necessary for the RRTs, including SOPs and those necessary for their safety and security and the availability of the required SOPs | A stock of equipment and logistics necessary for the RRTs is established | RRT management lead |  | # of days out of stock |  | 
Action 4.3 Provide a just -in- time training | RRT members are trained | Training Specialist/Coordinator |  | # of RRT members that received a just- in- time training before deployment |  | 
….. |  |  |  |  |  | 
Workplan for RRT programme- Example

## Slide 46
9.3 Group activity: RRT programme workplan development
Objective 5 :Monitor and evaluate the RRT program performance |  |  |  |  |  | 
Actions | Output | Responsible | Needed resources | Indicator | Date of completion | Challenges to be anticipated
Action 5.1 Develop/review the RRT management M&E framework | Framework is developed/reviewed | Monitoring and evaluation specialist |  | M&E framework available |  | 
Action 5.2 Monitor RRT program performance | RRT program performance is monitored | Monitoring and Evaluation specialist |  | RRT program monitoring annual report |  | 
Action 5.3 Conduct simulation exercises | Simulation exercises are conducted | RRT training specialist/ coordinator |  | # of plans/SOPs reviewed in light of simulation exercises recommendations |  | 
Action 5.4..... |  |  |  |  |  | 
Workplan for RRT programme- Example

## Slide 47
9.4 Group activity:
RRT programme budget plan development

## Slide 48
At the end of this session, you should be able to:
Identify what to consider while developing a budget plan for the RRT programme.
Develop a budget plan for the RRT programme.
Session objectives

## Slide 49
Operational
Sustained program funding
Office space
Roster management software
Funding for Training
Information Technology
Internet connectivity
Office supplies
Administrative Consideration
Healthcare, disability, and injury insurance coverage
Vaccination costs
Medical care costs
Mental healthcare costs
Medical/security evacuation coverage
Human Resources (salaries, per diems, etc.)
Rapid Response Team
RRT Management
Driver(s) (if used)
Translator(s) (if used)
Security (if needed)
Equipment – General
Cellphone
Cellphone credits
Laptop/computer
Global positioning system devices, if any
Hotspots
Hand sanitizer
Weather appropriate gear
Personal protective equipment (PPE_
Standardized forms
Media printing (poster, pamphlets, etc.)
Data entry system and reporting
(paper vs. electronic)
Equipment –Disease Specific
Clinical management supplies
Environmental management supplies
Laboratory supplies
Outbreak intervention supplies
Transportation
Flights (if needed)
Fuel (if using own vehicles)
Rental vehicles (if needed)
Travel allowance
Lodging
Hotels
Short term housing (if needed)
Dual lodging (if needed)
Meals
Meals and incidentals
Meal replacements, MREs (if needed)
Based on the country context, budgetary aspects should consider:
Budgetary considerations
9.4 Introduction to RRT programme budget plan development
Reminder!

## Slide 50: Remember that the main steps are:
    Identify roles and activities needed to sustain the programme
    Prioritize the roles/activities
    Determine how to allocate the budget
9.4 Introduction to RRT programme budget plan development

## Slide 51: Instructions for group work
    You will be given a template of budgetary plan.
Using the template and taking into account budgetary considerations:
    Select one specific action from the list of the RRT Workplan you developed earlier.
    Identify and list all the necessary resources required for each activity.
    Estimate the cost for each resource, ensuring to consider all possible expenses according to budget headings and subcategories.
    Estimate the total budget for the action.
    You will need to:
    identify roles and activities needed to sustain the programme
    prioritize the roles/activities
    determine how to allocate the budget
9.4 Group activity: Development of the RRT programme budget plan

## Slide 52: Instructions for group work
    Each group will assign a rapporteur to present in plenary the outcomes of the group work/discussion.
    Duration: 35’ group work; 10' presentations
    Output: Budgeting of activities of one of the actions proposed in the RRT Programme workplan.
9.4 Group activity: Development of the RRT programme budget plan

## Slide 53: Example of budgetary plan template
9.4 Introduction to RRT programme budget plan development

## Slide 54
9.5 Next Steps

## Slide 55
    At the end of this session, you should be able to:
    Identify next steps for RRT programme establishment/ strengthening
    Identify challenges to be anticipated
Session objectives

## Slide 56: Reminder-Planning for the SOP Development Process
Operation-specific SOPs can be created by simply writing down the steps taken when performing specific tasks in your operation and following the prescribed template.
Assess areas in your operation for which standard procedures are necessary. Start with those in which you are currently communicating most often or are agency priorities.
Interview subject matter experts (SMEs) on how procedures should be done.
9.5 Next Steps – SOP development
Notes: An easy way to approach SOP development is by starting by simply writing down the steps taken when performing specific tasks
Your team should also consider areas within your operation where standard procedures are necessary.
Similar to how this training has been, it should be an inclusive document – interview SME’s on how their SOP’s should be done.

## Slide 57: Reminder: RRT Management Planning and SOP Development
What is the process?
  Identify/share current preparedness and response plans, protocols, and activities, as well as challenges to efficient and effective response
  Identify gaps in current emergency response and potential solutions
  Develop drafts of guidelines, SOPs, checklists, reporting forms, etc., to address the gaps
Who should be involved in planning and SOP development?
  Key decision makers from Ministries and other organizations involved in public health emergency response
  National, sub-national, and local levels
9.5 Next Steps – SOP development
Notes: There are two core questions when it comes to planning and development:
What is the process? And Who should be involved?
The process should be iterative, identifying existing plans, protocols, emergency and non-emergency procedures, as well as potential gaps and solutions to make sure that this document is optimal and comprehensive.
Key decision makers as well as stakeholders from the national, sub-national, and local level should be represented to maximize engagement and be inclusive of potential touchpoint for RRT members.

## Slide 58: Plenary discussion
    Based on the previous activities, please copy the template from the next slides onto a flipchart and answer the following questions:
    What are the next steps for developing/finalizing the workshop outputs and SOPs?
    What challenges do you anticipate?
    What is the timeline for these steps?
    Assign a point of contact (POC) or a group of POCs responsible for the finalization of each next step.
    Duration: 45’
    Output: A roadmap to finalize the workshop outputs and RRT SOPs
9.5 Next Steps

## Slide 59
9.5 Next Steps- RRT programme planning
Finalization of the workshop outputs
Component | POC | Next Steps | Anticipated Challenges | Timeline
Composing the RRT management team |  |  |  | 
ToRs for RRT management team |  |  |  | 
RRT members job description |  |  |  | 
The RRT roster |  |  |  | 
RRT programme workplan |  |  |  | 
RRT programme budget plan |  |  |  | 
Notes: In plenary, the facilitator will invite attendees to assign a POC or group of POCs responsible for the development/finalization of each workshop output. The participants should complete this table as much as possible.

## Slide 60
Component | POC | Next Steps | Anticipated Challenges | Timeline
SOP #1 Staffing and Rostering |  |  |  | 
SOP #2: Administrative Consideration |  |  |  | 
SOP# 3: Training |  |  |  | 
SOP #4: Activation and Pre-Deployment |  |  |  | 
SOP #5: Deployment |  |  |  | 
SOP #6: Post Deployment |  |  |  | 
SOP #7: Monitoring, Evaluation and Improvement Planning |  |  |  | 
9.5 Next Steps – SOP development/finalization
Notes: In plenary, the facilitator will invite attendees to assign a POC or group of POCs responsible for the development of each SOP and a tentative deadline. The participants should complete this table as much as possible.

## Slide 61: Key messages
  The size of change management help dictate who is engaged, the planning efforts and the implementation pathways.
  To plan for an RRT programme, always start by conducting a response capacity assessment.
  To ensure effective RRT management, key stakeholders, available funding and regular review should be considered .

## Slide 62
Guidance for U.S. Centers for Disease Control and Prevention Staff for the Establishment and Management of Public Health Rapid Response Teams for Disease Outbreaks, U.S. CDC 2020
https://www.cdc.gov/coronavirus/2019-ncov/downloads/global-covid-19/RRTManagementGuidance-508.pdf
Framework for a Public Health Emergency Operations Center, World Health Organization, 2015.
https://www.who.int/publications/i/item/framework-for-a-public-health-emergency-operations-centre
Emergency Response Framework, 2nd edition, WHO 2017
https://apps.who.int/iris/bitstream/handle/10665/258604/9789241512299-eng.pdf
Integrated Disease Surveillance and Response Technical Guidelines, 3rd Edition, WHO 2019
https://apps.who.int/iris/handle/10665/325015
5 Critical steps in the change management process, Harvard Business School 2020
https://online.hbs.edu/blog/post/change-management-process

## Slide 63
Ready4Response, WHO online course
https://openwho.org/courses/ready4response-tier1-EN/overview
Incident Management System
https://openwho.org/courses/incident-management-system
The Public Health Emergency Operations Centre (PHEOC)
https://openwho.org/courses/PHEOC-EN
Introduction: Operational Readiness
https://openwho.org/courses/operational-readiness-introduction
WHO Standard Operating Procedures (SOPs) for Emergencies
https://openwho.org/courses/SOPs-for-emergencies
Additional learning resources

## Slide 64
US CDC disclaimer
This training package was made possible by grant/cooperative agreement number GH0002225-03 from the U.S. Centers for Disease Control and Prevention. Its contents do not necessarily reflect the official policies of the Department of Health and Human Services nor does mention of trade names, commercial practices, or organizations imply endorsement by the U.S. Government.

## Slide 65
WHO Health Security Learning Platform - Training Materials​
These WHO Training Materials are © World Health Organization (WHO) 2022. All rights reserved.​
Your use of these materials is subject to the “WHO Health Security Learning Platform, Training Materials – Terms of Use”, which you accepted when downloading them and which are available on the Health Security Learning Platform at: https://extranet.who.int/hslp ​
​
Should you adapt, modify, translate, or in any other way revise the contents of these materials, you shall not imply that WHO is any way affiliated with such modifications and shall not use the WHO name or emblem in such modified materials. ​
​
Should you adapt, modify, translate, or in any other way revise the contents of these materials, you shall acknowledge the source of the material providing the following attribution: “These training materials are a modified version of the Rapid Response Teams Managers Training Package (available at: https://extranet.who.int/hslp/), which is © the World Health Organization (WHO), 2022, and used with permission from WHO. WHO disclaims any responsibility for any modifications to, or revisions of, the WHO copyrighted materials.” ​
Further, please inform WHO of any modifications of these materials that you use publicly, for record-keeping purposes and continued development, by emailing ihrhrt@who.int​