## Sheet1
FSX06 EXERCISE ADMIN AND LOGISTICS CHECKLIST
NOTES: This template can be used to assess tasks and items necessary for an exercise.
What, where, when, who and how?
• Agreement and budget allocated
• Venue, date and time - agenda set
• Facilitators, participants and admin support
• Equipment required
• Tools, templates and guidance material
• Flexibility
Before the exercise
Task | Items and remarks | Date | Responsibility (who) | Status
Due
Concept note | Define the purpose and scope of activities
Resources | Facilitation team identified and confirmed
Guidance, tools and templates available
Budget prepared
Funding sources agreed
Guidance, tools and templates available
Venue | 3 x quotes received if venue to be rented |  |  | Completed
| Venue selected (security approved, appropriate size) |  |  | In process
| Final venue booked |  |  | Not started
Room layout agreed with venue manager
Venue setup
Supplies and equipment delivered and set up
Catering | Catering package (meals and refreshments)
3 x quotes received (if needed)
Catering confirmed and times provided
Optional group dinner booked
Invitations | Participants identified
Participants invited
Participant list and directory created
Admin note & reminder sent
Facilitator accommodation & transport | Visa letters sent (if needed)
Airport transfers (if needed) - both ways
Accommodation booked
DSA (if appropriate)
Participant accommodation & transport | Visa letters sent (if needed)
Airport transfers (if needed) - both ways
Accommodation booked
DSA (if appropriate)
Supplies | Event banner (including logos)
Welcome packs (folders) for each participant
4 x flipcharts on stands and paper
First aid kit
Digital camera / official photographer
Pad of paper and water per person
Rubbish & paper recycling bins
Large clock for the room
Stationery:
• Name badge holders
• Pens (might be supplied by the hotel?)
• Memory sticks (at least 4)
• Flipchart paper & markers
• Staplers & box of staples
• Adhesive tape (paper tape)
• Scissors
• Packet of A4 print paper
• Spare printer ink (black)
• Pack of large post-it notes
Equipment | Microphone and speakers (sound system)
LCD projector, cables and screen
Printer
Power-boards
Presentation remote
Facilitator laptops
Collect all equipment & return to owners
Print/ documents | Name badges
Registration sheet
Print agenda
Print inject matrix (1 set per control team member)
Print master scenario (1 copy per participant)
Guidance note
M&E survey
Translation | Documents translated
After the exercise
Task | Items and remarks | Date | Responsibility (who) | Status
Due
Resources | All expenses recorded
Produce a financial report if required
Venue | Collect and check invoice vs. quote
Confirm with finances whether invoice is OK for payment
Catering | Collect and check invoice vs. quote
Confirm with finances whether invoice is OK for payment
Supplies | Collect and allocate leftover stationery supplies
Equipment | Collect all equipment & return to owners
Print/ documents | Update participant contact list
Note on A1: I dont agree with the second column "after the workshop" - If an item status is done, than it doesn't require follow up after the workshop. Couldn't we rather add the after the exercise items/tasks at the bottom of the list as required? -Mark Shapiro