Results and Follow up

- ☐ Debrief the Exercise Management team

- ☐ Debrief senior-level management

- ☐ Develop the Exercise Report

- ☐ Close project administrative tasks and logistics

- ☐ If required, draft the Internal Mission Report

Full-scale/Field Exercise (FSX) Project Checklist

Exercise Conduct

Post-Exercise

Conduct

Conduct

- ☐ Welcome and opening

- ☐ Brief participants on the simulation exercise

- ☐ Start the exercise

- ☐ Run/control the exercise

- ☐ Capture the outcomes

- ☐ End the exercise

- ☐ Conduct an initial exercise debrief (i.e. Hot Wash)

- ☐ Conduct a main exercise debrief workshop

- ☐ Close the exercise

* The timeline above is for Full-scale exercises. Field-exercises are shorter than Full-scale exercises: planning begins 8 weeks prior to the exercise, material development takes 8-10 weeks, exercise conduct takes 1 week, and post-exercise reporting takes 2 weeks.

Full-scale/Field Exercise (FSX) Project Checklist

Planning

☐ Scope the FSX (i.e. Concept Note)

☐ Establish the Exercise Management Team

☐ Define the project management plan

☐ Identify the participants

☐ Define the evaluation strategy

☐ Manage administrative tasks and logistics

☐ If required, set the media, press release and communications strategy

☐ If required, assess safety and security

Material Development

☐ Review the Concept Note

☐ Research the context & gather reference materials

☐ Write the master scenario

☐ Develop the injects and inject matrix

☐ Fully develop and write out all planned injects

☐ Develop evaluation material

☐ Develop the exercise handbook and/or briefings

☐ If required, draft opening or closing remarks

Set up

☐ Setup the exercise venue(s)

☐ Setup the exercise control room

☐ Check all equipment

☐ Brief the exercise management team

2-4 weeks*

6 months prior to FSX*

1-2 weeks*

1 week*

4-5 months*

Pre-Exercise