Conduct

Planning

☐ Scope the DR (i.e. Concept Note)

☐ Establish the Exercise Management Team

☐ Define the project management plan

☐ Identify the participants

☐ Define the evaluation strategy

☐ Manage administrative tasks and logistics

☐ If required, set the media, press release and communications strategy

☐ If required, assess safety and security

Material Development

☐ Review the Concept Note

☐ Research the context & gather reference materials

☐ Write the master scenario

☐ Develop the injects and inject matrix

☐ Develop evaluation material

☐ Develop the exercise handbook and/or briefings

Set up

☐ Setup the exercise venue

☐ Setup the exercise control room

☐ Check all equipment

☐ Brief the exercise management team

1 day

2 weeks

1 or more days

1-2 months prior to DR

Pre-Exercise

Drill Exercise (DR) Project Checklist

Drill Exercise (DR) Project Checklist

1 week

Exercise Conduct

Results and Follow up

- ☐ Debrief the Exercise Management team

- ☐ Debrief senior-level management

- ☐ Develop the Exercise Report

- ☐ Close project administrative tasks and logistics

- ☐ If required, draft the Internal Mission Report

Post-Exercise

Conduct

- ☐ Brief participants on the simulation exercise

- ☐ Start the exercise

- ☐ Run/control the exercise

- ☐ Capture the outcomes

- ☐ End the exercise

- ☐ Conduct a debrief of the exercise

- ☐ Close the exercise